## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | FACTA System | 1 |  |  | 2014-02-21 08:00 | 2014-05-12 17:00 | 57d |  |  | 0 |  |  | 11700 | 80.375
21 | supporting tasks | 1.1 |  |  | 2014-02-21 08:00 | 2014-02-24 10:00 | 1d 2h |  |  | 0 |  |  | 900 | 3.0833
1 | project management | 1.1.1 |  | FS2 | 2014-02-21 08:00 | 2014-02-24 10:00 | 1d 2h | Employee A | 900 | 0 | 0 | 0 | 900 | 3.0833
22 | analysis | 1.2 |  |  | 2014-02-28 08:00 | 2014-02-28 17:00 | 1d |  |  | 0 |  |  | 75 | 0.375
2 | analysis - conceptual design | 1.2.1 | 1FS | FS3 | 2014-02-28 08:00 | 2014-02-28 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 | 0.041667
3 | analysis validated | 1.2.2 | 2FS | FS18 | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
23 | design | 1.3 |  |  | 2014-03-03 08:00 | 2014-03-07 17:00 | 5d |  |  | 0 |  |  | 300 | 4.375
4 | design - technical design | 1.3.1 |  | FS5 | 2014-03-03 08:00 | 2014-03-03 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 0.16667
5 | design validated | 1.3.2 | 4FS | FS18 | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
24 | development | 1.4 |  |  | 2014-03-03 08:00 | 2014-03-24 17:00 | 16d |  |  | 0 |  |  | 2250 | 21.375
6 | development - coding | 1.4.1 |  | FS10 | 2014-03-03 08:00 | 2014-03-03 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 | 0.16667
7 | development - coding | 1.4.2 |  | FS10 | 2014-03-03 08:00 | 2014-03-04 15:00 | 1d 6h | Employee G | 1050 | 0 | 0 | 0 | 1050 | 1.2917
8 | development - coding | 1.4.3 |  | FS10 | 2014-03-03 08:00 | 2014-03-04 12:00 | 1d 4h | Employee H | 900 | 0 | 0 | 0 | 900 | 1.1667
10 | development completed | 1.4.4 | 6FS;7FS;8FS | FS18 | 2014-03-24 17:00 | 2014-03-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
25 | ict test | 1.5 |  |  | 2014-02-28 08:00 | 2014-03-24 17:00 | 17d |  |  | 0 |  |  | 3525 | 24.375
11 | test ict - test preparation | 1.5.1 |  | FS13 | 2014-02-28 08:00 | 2014-03-06 10:00 | 4d 2h | Employee K | 2550 | 0 | 0 | 0 | 2550 | 6.0833
12 | test ict - test coordination | 1.5.2 |  | FS13 | 2014-03-03 08:00 | 2014-03-04 11:00 | 1d 3h | Employee B | 825 | 0 | 0 | 0 | 825 | 1.125
13 | test ict - test execution | 1.5.3 | 11FS;12FS | FS14 | 2014-03-24 08:00 | 2014-03-24 10:00 | 2h | Employee K | 150 | 0 | 0 | 0 | 150 | 0.083333
14 | ict test completed | 1.5.4 | 13FS | FS18 | 2014-03-24 17:00 | 2014-03-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
26 | implementation | 1.6 |  |  | 2014-03-31 08:00 | 2014-05-09 17:00 | 30d |  |  | 0 |  |  | 3450 | 39.375
15 | uat - test support | 1.6.1 |  | FS16 | 2014-03-31 08:00 | 2014-04-04 15:00 | 4d 6h | Employee K | 2850 | 0 | 0 | 0 | 2850 | 4.2917
16 | uat completed | 1.6.2 | 15FS | FS18 | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
17 | implementation - put in production | 1.6.3 |  | FS18 | 2014-03-31 08:00 | 2014-03-31 17:00 | 1d | Employee L | 600 | 0 | 0 | 0 | 600 | 0.375
18 | go live | 1.6.4 | 17FS;3FS;5FS;10FS;14FS;16FS | FS19;FS20 | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
27 | post implementation | 1.7 |  |  | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d |  |  | 0 |  |  | 1200 | 0.375
19 | post implementation - post go live support | 1.7.1 | 18FS |  | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee B | 600 | 0 | 0 | 0 | 600 | 0.375
20 | post implementation - post go live support | 1.7.2 | 18FS |  | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 | 0.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee A | Renewable | 1 | 0 | 90 | 1; | 900
2 | Employee B | Renewable | 1 | 0 | 75 | 12;19; | 1425
3 | Employee C | Renewable | 1 | 0 | 75 |  | 0
4 | Employee D | Renewable | 1 | 0 | 75 | 2; | 75
5 | Employee E | Renewable | 1 | 0 | 75 | 4; | 300
6 | Employee F | Renewable | 1 | 0 | 75 | 6; | 300
7 | Employee G | Renewable | 1 | 0 | 75 | 7; | 1050
8 | Employee H | Renewable | 1 | 0 | 75 | 8; | 900
9 | Employee I | Renewable | 1 | 0 | 75 |  | 0
10 | Employee J | Renewable | 1 | 0 | 75 |  | 0
11 | Employee K | Renewable | 1 | 0 | 75 | 11;13;15;20; | 6150
12 | Employee L | Renewable | 1 | 0 | 75 | 17; | 600

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | FACTA System | 456h |  |  |  |  | 99 | 100 | 101
21 | supporting tasks | 10h |  |  |  |  | 99 | 100 | 101
1 | project management | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | analysis | 8h |  |  |  |  | 99 | 100 | 101
2 | analysis - conceptual design | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | analysis validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | design | 40h |  |  |  |  | 99 | 100 | 101
4 | design - technical design | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | design validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | development | 128h |  |  |  |  | 99 | 100 | 101
6 | development - coding | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | development - coding | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | development - coding | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | development completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | ict test | 136h |  |  |  |  | 99 | 100 | 101
11 | test ict - test preparation | 34h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | test ict - test coordination | 11h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | test ict - test execution | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | ict test completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | implementation | 240h |  |  |  |  | 99 | 100 | 101
15 | uat - test support | 38h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | uat completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | implementation - put in production | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | go live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | post implementation | 8h |  |  |  |  | 99 | 100 | 101
19 | post implementation - post go live support | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | post implementation - post go live support | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2014-03-10 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | FACTA System | 2014-02-21 08:00 | 2014-05-12 17:00 | 57d |  |  | 0 |  |  | 11700 |  | 12d 4h | [5 empty] | 3600 |  | 40.67% |  | 4758 | 6900
21 | supporting tasks | 2014-02-21 08:00 | 2014-02-24 10:00 | 1d 2h |  |  | 0 |  |  | 900 |  | 12d | [5 empty] | 450 |  | 26% |  | 234 | 900
1 | project management | 2014-02-21 08:00 | 2014-02-24 10:00 | 1d 2h | Employee A | 900 | 0 | 0 | 0 | 900 | 2014-02-21 08:00 | 5h | 450 | 540 | 6h | 0 | 0 | 450 | 540 | 26% | Started | 234 | 900 | 100 | 50 | 26 | 100 | 50 | 26
22 | analysis | 2014-02-28 08:00 | 2014-02-28 17:00 | 1d |  |  | 0 |  |  | 75 |  | 4d 7h | [5 empty] | 75 |  | 100% |  | 75 | 75
2 | analysis - conceptual design | 2014-02-28 08:00 | 2014-02-28 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 | 2014-02-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
3 | analysis validated | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-28 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
23 | design | 2014-03-03 08:00 | 2014-03-07 17:00 | 5d |  |  | 0 |  |  | 300 |  | 4d 7h | [5 empty] | 75 |  | 100% |  | 300 | 300
4 | design - technical design | 2014-03-03 08:00 | 2014-03-03 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2014-03-03 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 300 | 300 | 100 | 25 | 100 | 100 | 25 | 100
5 | design validated | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-07 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
24 | development | 2014-03-03 08:00 | 2014-03-24 17:00 | 16d |  |  | 0 |  |  | 2250 |  | 6d 4h | [5 empty] | 1575 |  | 94.87% |  | 2134.5 | 2250
6 | development - coding | 2014-03-03 08:00 | 2014-03-03 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 | 2014-03-03 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 300 | 300 | 100 | 25 | 100 | 100 | 25 | 100
7 | development - coding | 2014-03-03 08:00 | 2014-03-04 15:00 | 1d 6h | Employee G | 1050 | 0 | 0 | 0 | 1050 | 2014-03-03 08:00 | 1d | 600 | 450 | 6h | 0 | 0 | 600 | 450 | 89% | Started | 934.5 | 1050 | 100 | 57.1429 | 89 | 100 | 57.1429 | 89
8 | development - coding | 2014-03-03 08:00 | 2014-03-04 12:00 | 1d 4h | Employee H | 900 | 0 | 0 | 0 | 900 | 2014-03-10 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 900 | 900 | 100 | 100 | 100 | 100 | 100 | 100
10 | development completed | 2014-03-24 17:00 | 2014-03-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | ict test | 2014-02-28 08:00 | 2014-03-24 17:00 | 17d |  |  | 0 |  |  | 3525 |  | 11d | [5 empty] | 1425 |  | 57.15% |  | 2014.5001 | 3375
11 | test ict - test preparation | 2014-02-28 08:00 | 2014-03-06 10:00 | 4d 2h | Employee K | 2550 | 0 | 0 | 0 | 2550 | 2014-02-24 08:00 | 2d 3h | 1425 | 300 | 4h | 0 | 0 | 1425 | 300 | 79% | Started | 2014.5001 | 2550 | 100 | 55.8824 | 79 | 100 | 55.8824 | 79
12 | test ict - test coordination | 2014-03-03 08:00 | 2014-03-04 11:00 | 1d 3h | Employee B | 825 | 0 | 0 | 0 | 825 |  | 0 | 0 | 825 | 1d 3h | 0 | 0 | 0 | 825 | 0% | Not Started | 0 | 825 | 100 |  | 0 | 100 |  | 0
13 | test ict - test execution | 2014-03-24 08:00 | 2014-03-24 10:00 | 2h | Employee K | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | ict test completed | 2014-03-24 17:00 | 2014-03-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | implementation | 2014-03-31 08:00 | 2014-05-09 17:00 | 30d |  |  | 0 |  |  | 3450 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
15 | uat - test support | 2014-03-31 08:00 | 2014-04-04 15:00 | 4d 6h | Employee K | 2850 | 0 | 0 | 0 | 2850 |  | 0 | 0 | 2850 | 4d 6h | 0 | 0 | 0 | 2850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | uat completed | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | implementation - put in production | 2014-03-31 08:00 | 2014-03-31 17:00 | 1d | Employee L | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | post implementation | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d |  |  | 0 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee B | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-04-07 22:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | FACTA System | 2014-02-21 08:00 | 2014-05-12 17:00 | 57d |  |  | 0 |  |  | 11700 |  | 32d | [5 empty] | 5385 |  | 87.74% |  | 10266 | 10500
21 | supporting tasks | 2014-02-21 08:00 | 2014-02-24 10:00 | 1d 2h |  |  | 0 |  |  | 900 |  | 32d | [5 empty] | 1260 |  | 74% |  | 666 | 900
1 | project management | 2014-02-21 08:00 | 2014-02-24 10:00 | 1d 2h | Employee A | 900 | 0 | 0 | 0 | 900 | 2014-02-21 08:00 | 1d 6h | 1260 | 90 | 1h | 0 | 0 | 1260 | 90 | 74% | Started | 666 | 900 | 100 | 140 | 74 | 100 | 140 | 74
22 | analysis | 2014-02-28 08:00 | 2014-02-28 17:00 | 1d |  |  | 0 |  |  | 75 |  | 4d 7h | [5 empty] | 75 |  | 100% |  | 75 | 75
2 | analysis - conceptual design | 2014-02-28 08:00 | 2014-02-28 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 | 2014-02-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
3 | analysis validated | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-28 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
23 | design | 2014-03-03 08:00 | 2014-03-07 17:00 | 5d |  |  | 0 |  |  | 300 |  | 4d 7h | [5 empty] | 75 |  | 100% |  | 300 | 300
4 | design - technical design | 2014-03-03 08:00 | 2014-03-03 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2014-03-03 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 300 | 300 | 100 | 25 | 100 | 100 | 25 | 100
5 | design validated | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-07 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
24 | development | 2014-03-03 08:00 | 2014-03-24 17:00 | 16d |  |  | 0 |  |  | 2250 |  | 15d 7h | [5 empty] | 1650 |  | 100% |  | 2250 | 2250
6 | development - coding | 2014-03-03 08:00 | 2014-03-03 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 | 2014-03-03 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 300 | 300 | 100 | 25 | 100 | 100 | 25 | 100
7 | development - coding | 2014-03-03 08:00 | 2014-03-04 15:00 | 1d 6h | Employee G | 1050 | 0 | 0 | 0 | 1050 | 2014-03-03 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 1050 | 1050 | 100 | 64.2857 | 100 | 100 | 64.2857 | 100
8 | development - coding | 2014-03-03 08:00 | 2014-03-04 12:00 | 1d 4h | Employee H | 900 | 0 | 0 | 0 | 900 | 2014-03-10 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 900 | 900 | 100 | 100 | 100 | 100 | 100 | 100
10 | development completed | 2014-03-24 17:00 | 2014-03-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
25 | ict test | 2014-02-28 08:00 | 2014-03-24 17:00 | 17d |  |  | 0 |  |  | 3525 |  | 20d 7h | [5 empty] | 2175 |  | 100% |  | 3525 | 3525
11 | test ict - test preparation | 2014-02-28 08:00 | 2014-03-06 10:00 | 4d 2h | Employee K | 2550 | 0 | 0 | 0 | 2550 | 2014-02-24 08:00 | 3d | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 100% | Finished | 2550 | 2550 | 100 | 70.5882 | 100 | 100 | 70.5882 | 100
12 | test ict - test coordination | 2014-03-03 08:00 | 2014-03-04 11:00 | 1d 3h | Employee B | 825 | 0 | 0 | 0 | 825 | 2014-03-17 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 825 | 825 | 100 | 27.2727 | 100 | 100 | 27.2727 | 100
13 | test ict - test execution | 2014-03-24 08:00 | 2014-03-24 10:00 | 2h | Employee K | 150 | 0 | 0 | 0 | 150 | 2014-03-24 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
14 | ict test completed | 2014-03-24 17:00 | 2014-03-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
26 | implementation | 2014-03-31 08:00 | 2014-05-09 17:00 | 30d |  |  | 0 |  |  | 3450 |  | 6d | [5 empty] | 150 |  | 100% |  | 3450 | 3450
15 | uat - test support | 2014-03-31 08:00 | 2014-04-04 15:00 | 4d 6h | Employee K | 2850 | 0 | 0 | 0 | 2850 | 2014-03-31 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 2850 | 2850 | 100 | 2.6316 | 100 | 100 | 2.6316 | 100
16 | uat completed | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | implementation - put in production | 2014-03-31 08:00 | 2014-03-31 17:00 | 1d | Employee L | 600 | 0 | 0 | 0 | 600 | 2014-03-31 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 600 | 600 | 100 | 12.5 | 100 | 100 | 12.5 | 100
18 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | post implementation | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d |  |  | 0 |  |  | 1200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee B | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-05-12 09:00 |  | TP Name | Tracking 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | FACTA System | 2014-02-21 08:00 | 2014-05-12 17:00 | 57d |  |  | 0 |  |  | 11700 |  | 57d | [5 empty] | 7035 |  | 100% |  | 11700 | 10650
21 | supporting tasks | 2014-02-21 08:00 | 2014-02-24 10:00 | 1d 2h |  |  | 0 |  |  | 900 |  | 2d 3h | [5 empty] | 1710 |  | 100% |  | 900 | 900
1 | project management | 2014-02-21 08:00 | 2014-02-24 10:00 | 1d 2h | Employee A | 900 | 0 | 0 | 0 | 900 | 2014-02-21 08:00 | 2d 3h | 1710 | 0 | 0 | 0 | 0 | 1710 | 0 | 100% | Finished | 900 | 900 | 100 | 190 | 100 | 100 | 190 | 100
22 | analysis | 2014-02-28 08:00 | 2014-02-28 17:00 | 1d |  |  | 0 |  |  | 75 |  | 4d 7h | [5 empty] | 75 |  | 100% |  | 75 | 75
2 | analysis - conceptual design | 2014-02-28 08:00 | 2014-02-28 09:00 | 1h | Employee D | 75 | 0 | 0 | 0 | 75 | 2014-02-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
3 | analysis validated | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-28 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
23 | design | 2014-03-03 08:00 | 2014-03-07 17:00 | 5d |  |  | 0 |  |  | 300 |  | 4d 7h | [5 empty] | 75 |  | 100% |  | 300 | 300
4 | design - technical design | 2014-03-03 08:00 | 2014-03-03 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2014-03-03 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 300 | 300 | 100 | 25 | 100 | 100 | 25 | 100
5 | design validated | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-07 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
24 | development | 2014-03-03 08:00 | 2014-03-24 17:00 | 16d |  |  | 0 |  |  | 2250 |  | 15d 7h | [5 empty] | 1650 |  | 100% |  | 2250 | 2250
6 | development - coding | 2014-03-03 08:00 | 2014-03-03 12:00 | 4h | Employee F | 300 | 0 | 0 | 0 | 300 | 2014-03-03 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 300 | 300 | 100 | 25 | 100 | 100 | 25 | 100
7 | development - coding | 2014-03-03 08:00 | 2014-03-04 15:00 | 1d 6h | Employee G | 1050 | 0 | 0 | 0 | 1050 | 2014-03-03 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 1050 | 1050 | 100 | 64.2857 | 100 | 100 | 64.2857 | 100
8 | development - coding | 2014-03-03 08:00 | 2014-03-04 12:00 | 1d 4h | Employee H | 900 | 0 | 0 | 0 | 900 | 2014-03-10 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 900 | 900 | 100 | 100 | 100 | 100 | 100 | 100
10 | development completed | 2014-03-24 17:00 | 2014-03-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
25 | ict test | 2014-02-28 08:00 | 2014-03-24 17:00 | 17d |  |  | 0 |  |  | 3525 |  | 20d 7h | [5 empty] | 2175 |  | 100% |  | 3525 | 3525
11 | test ict - test preparation | 2014-02-28 08:00 | 2014-03-06 10:00 | 4d 2h | Employee K | 2550 | 0 | 0 | 0 | 2550 | 2014-02-24 08:00 | 3d | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 100% | Finished | 2550 | 2550 | 100 | 70.5882 | 100 | 100 | 70.5882 | 100
12 | test ict - test coordination | 2014-03-03 08:00 | 2014-03-04 11:00 | 1d 3h | Employee B | 825 | 0 | 0 | 0 | 825 | 2014-03-17 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 825 | 825 | 100 | 27.2727 | 100 | 100 | 27.2727 | 100
13 | test ict - test execution | 2014-03-24 08:00 | 2014-03-24 10:00 | 2h | Employee K | 150 | 0 | 0 | 0 | 150 | 2014-03-24 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
14 | ict test completed | 2014-03-24 17:00 | 2014-03-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
26 | implementation | 2014-03-31 08:00 | 2014-05-09 17:00 | 30d |  |  | 0 |  |  | 3450 |  | 29d 7h | [5 empty] | 150 |  | 100% |  | 3450 | 3450
15 | uat - test support | 2014-03-31 08:00 | 2014-04-04 15:00 | 4d 6h | Employee K | 2850 | 0 | 0 | 0 | 2850 | 2014-03-31 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 2850 | 2850 | 100 | 2.6316 | 100 | 100 | 2.6316 | 100
16 | uat completed | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
17 | implementation - put in production | 2014-03-31 08:00 | 2014-03-31 17:00 | 1d | Employee L | 600 | 0 | 0 | 0 | 600 | 2014-03-31 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 600 | 600 | 100 | 12.5 | 100 | 100 | 12.5 | 100
18 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
27 | post implementation | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d |  |  | 0 |  |  | 1200 |  | 1d | [5 empty] | 1200 |  | 100% |  | 1200 | 150
19 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee B | 600 | 0 | 0 | 0 | 600 | 2014-05-12 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 75 | 100 | 100 | 100 | 100 | 100 | 100
20 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 | 2014-05-12 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 75 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2014-02-21 08:00 | 2014-03-10 22:00 | 6900 | 4758 | 3600 | 2014-03-03 17:00 | -2142 | 68.96% | 1158 | 132.2% | -5d | 58.33% | 72.33% | 2014-05-27 11:00 | 2014-06-17 14:00 | 2014-05-20 12:00 | 2014-05-16 15:00 | 2014-06-17 14:00 | 2014-05-23 12:00 | 2014-05-19 17:00 | 2014-07-08 15:00 | 2014-06-09 16:00 | 10542 | 8852.459 | 13667.213 | 15500.5714 | 11217.059 | 12604.2154 | 9408.0075 | 9513.1175 | 0.58333 | 1.3217 | 0.68957 | 0.72328 | -5 | 1.3217 | 1 | 0.58333 | 1
Tracking 2 | 2014-03-10 22:00 | 2014-04-07 22:00 | 10500 | 10266 | 5385 | 2014-04-04 10:00 | -234 | 97.77% | 4881 | 190.6% | -1d 6h | 94.53% | 97.71% | 2014-05-14 09:00 | 2014-05-14 10:00 | 2014-04-04 14:00 | 2014-05-13 15:00 | 2014-05-14 10:00 | 2014-04-25 15:00 | 2014-05-14 15:00 | 2014-05-16 10:00 | 2014-04-28 16:00 | 6819 | 6137.2005 | 6851.6861 | 6901.9587 | 6154.3459 | 6180.7162 | 6218.3972 | 6221.5478 | 0.94531 | 1.9064 | 0.97771 | 0.97706 | -1.75 | 1.9064 | 1 | 0.94531 | 1
Tracking 3 | 2014-04-07 22:00 | 2014-05-12 09:00 | 10650 | 11700 | 7035 | 2014-05-12 17:00 | 1050 | 109.9% | 4665 | 166.3% | 7h | 101.6% | 100% | 2014-05-05 16:00 | 2014-05-05 16:00 | 2014-04-07 10:00 | 2014-05-05 12:00 | 2014-05-05 16:00 | 2014-05-07 14:00 | 2014-05-12 09:00 | 2014-05-12 09:00 | 2014-05-12 09:00 | 7035 | 7035 | 7035 | 7035 | 7035 | 7035 | 7035 | 7035 | 1.0156 | 1.6631 | 1.0986 | 1 | 0.875 | 1.6631 | 1 | 1.0156 | 1