## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Generic Document Output System | 1 |  |  | 2013-04-29 08:00 | 2014-05-09 17:00 | 270d |  |  | 0 |  |  | 64620 | 375.375
28 | supporting tasks | 1.1 |  |  | 2013-08-19 08:00 | 2014-03-14 10:00 | 149d 2h |  |  | 0 |  |  | 9660 | 207.0833
1 | project management | 1.1.1 | 3FS;4FS;5FS;6FS;7FS | FS9;FS38;FS2 | 2013-08-19 08:00 | 2013-08-26 14:00 | 5d 5h | Employee A | 4050 | 0 | 0 | 0 | 4050 | 7.25
38 | validation and support | 1.1.2 | 1FS |  | 2014-03-10 08:00 | 2014-03-14 10:00 | 4d 2h | Employee B | 2550 | 0 | 0 | 0 | 2550 | 4.0833
2 | validation and support | 1.1.3 | 1FS |  | 2014-03-10 08:00 | 2014-03-14 10:00 | 4d 2h | Employee A | 3060 | 0 | 0 | 0 | 3060 | 4.0833
29 | analysis | 1.2 |  |  | 2013-04-29 08:00 | 2014-01-27 17:00 | 196d |  |  | 0 |  |  | 6060 | 273.375
3 | analysis - solution concept | 1.2.1 |  | FS1;FS9 | 2013-04-29 08:00 | 2013-04-29 14:00 | 5h | Employee A | 450 | 0 | 0 | 0 | 450 | 0.25
4 | analysis - solution concept | 1.2.2 |  | FS1;FS9 | 2013-04-29 08:00 | 2013-05-01 17:00 | 3d | Employee B | 1800 | 0 | 0 | 0 | 1800 | 2.375
5 | analysis - solution concept | 1.2.3 |  | FS1;FS9 | 2013-04-29 08:00 | 2013-05-01 17:00 | 3d | Employee C | 1800 | 0 | 0 | 0 | 1800 | 2.375
6 | analysis - solution concept | 1.2.4 |  | FS1;FS9 | 2013-04-29 08:00 | 2013-04-29 14:00 | 5h | Employee D | 375 | 0 | 0 | 0 | 375 | 0.25
7 | analysis - solution concept | 1.2.5 |  | FS1;FS9 | 2013-04-29 08:00 | 2013-05-01 09:00 | 2d 1h | Employee E | 1275 | 0 | 0 | 0 | 1275 | 2.0417
8 | analysis - business analysis | 1.2.6 |  | FS9 | 2013-12-30 08:00 | 2013-12-30 12:00 | 4h | Employee A | 360 | 0 | 0 | 0 | 360 | 0.16667
9 | analysis validated | 1.2.7 | 3FS;4FS;5FS;6FS;7FS;8FS;1FS | FS27 | 2014-01-27 17:00 | 2014-01-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
30 | design | 1.3 |  |  | 2014-01-21 08:00 | 2014-03-07 17:00 | 34d |  |  | 0 |  |  | 9150 | 45.375
10 | design - SAD/interface design | 1.3.1 |  | FS14 | 2014-01-21 08:00 | 2014-01-28 09:00 | 5d 1h | Employee H | 3075 | 0 | 0 | 0 | 3075 | 7.0417
11 | design - SAD/interface design | 1.3.2 |  | FS14 | 2014-01-21 08:00 | 2014-01-21 10:00 | 2h | Employee I | 150 | 0 | 0 | 0 | 150 | 0.083333
12 | design - CDM/process design | 1.3.3 |  | FS14 | 2014-01-21 08:00 | 2014-02-03 11:00 | 9d 3h | Employee F | 5625 | 0 | 0 | 0 | 5625 | 13.125
13 | design - CDM/process design | 1.3.4 |  | FS14 | 2014-01-21 08:00 | 2014-01-21 12:00 | 4h | Employee G | 300 | 0 | 0 | 0 | 300 | 0.16667
14 | design validated | 1.3.5 | 10FS;11FS;12FS;13FS | FS27 | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
31 | development | 1.4 |  |  | 2014-01-06 08:00 | 2014-04-14 17:00 | 71d |  |  | 0 |  |  | 36150 | 98.375
15 | development - coding DMS | 1.4.1 | 36FS;37FS;19FS | FS20 | 2014-03-10 08:00 | 2014-03-12 16:00 | 2d 7h | Employee C | 1725 | 0 | 0 | 0 | 1725 | 2.3333
16 | development - coding ESB | 1.4.2 | 36FS;37FS;19FS | FS20 | 2014-01-28 08:00 | 2014-02-10 11:00 | 9d 3h | Employee J | 5625 | 0 | 0 | 0 | 5625 | 13.125
17 | development - coding ESB | 1.4.3 | 36FS;37FS;19FS | FS20 | 2014-01-28 08:00 | 2014-03-10 17:00 | 30d | Employee E | 18000 | 0 | 0 | 0 | 18000 | 41.375
18 | development - coding OMS | 1.4.4 | 36FS;37FS;19FS | FS20 | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d | Employee K | 3000 | 0 | 0 | 0 | 3000 | 6.375
36 | development - bugfixing | 1.4.5 |  | FS15;FS16;FS17;FS18;FS20 | 2014-01-06 08:00 | 2014-01-16 15:00 | 8d 6h | Employee C | 5250 | 0 | 0 | 0 | 5250 | 10.2917
37 | development - bugfixing | 1.4.6 |  | FS15;FS16;FS17;FS18;FS20 | 2014-01-06 08:00 | 2014-01-09 09:00 | 3d 1h | Employee E | 1875 | 0 | 0 | 0 | 1875 | 3.0417
19 | development - bugfixing and support | 1.4.7 |  | FS15;FS16;FS17;FS18;FS20 | 2014-01-06 08:00 | 2014-01-07 09:00 | 1d 1h | Employee K | 675 | 0 | 0 | 0 | 675 | 1.0417
20 | development completed | 1.4.8 | 15FS;16FS;17FS;18FS;19FS;36FS;37FS | FS27 | 2014-04-14 17:00 | 2014-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
32 | test ict | 1.5 |  |  | 2014-02-20 08:00 | 2014-04-14 17:00 | 38d |  |  | 0 |  |  | 3600 | 53.375
21 | test ict - test coordination | 1.5.1 |  | FS23;FS22 | 2014-02-20 08:00 | 2014-02-21 10:00 | 1d 2h | Employee L | 750 | 0 | 0 | 0 | 750 | 1.0833
22 | test ict - test execution | 1.5.2 | 21FS | FS23 | 2014-03-24 08:00 | 2014-03-28 15:00 | 4d 6h | Employee L | 2850 | 0 | 0 | 0 | 2850 | 4.2917
23 | ict test completed | 1.5.3 | 21FS;22FS | FS27 | 2014-04-14 17:00 | 2014-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
33 | UAT | 1.6 |  |  | 2014-03-14 17:00 | 2014-04-25 17:00 | 30d |  |  | 0 |  |  | 0 | 42
24 | full handover | 1.6.1 |  | FS27 | 2014-03-14 17:00 | 2014-03-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
25 | release handover | 1.6.2 |  |  | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
26 | code freeze | 1.6.3 |  |  | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
34 | implementation | 1.7 |  |  | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0
27 | go live | 1.7.1 | 9FS;14FS;20FS;23FS;24FS |  | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee A | Renewable | 1 | 0 | 90 | 1;2;3;8; | 7920
2 | Employee B | Renewable | 1 | 0 | 75 | 38;4; | 4350
3 | Employee C | Renewable | 1 | 0 | 75 | 5;15;36; | 8775
4 | Employee D | Renewable | 1 | 0 | 75 | 6; | 375
5 | Employee E | Renewable | 1 | 0 | 75 | 7;17;37; | 21150
6 | Employee F | Renewable | 1 | 0 | 75 | 12; | 5625
7 | Employee G | Renewable | 1 | 0 | 75 | 13; | 300
8 | Employee H | Renewable | 1 | 0 | 75 | 10; | 3075
9 | Employee I | Renewable | 1 | 0 | 75 | 11; | 150
10 | Employee J | Renewable | 1 | 0 | 75 | 16; | 5625
11 | Employee K | Renewable | 1 | 0 | 75 | 18;19; | 3675
12 | Employee L | Renewable | 1 | 0 | 75 | 21;22; | 3600
13 | Employee M | Renewable | 1 | 0 | 75 |  | 0

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Generic Document Output System | 2160h |  |  |  |  | 99 | 100 | 101
28 | supporting tasks | 1194h |  |  |  |  | 99 | 100 | 101
1 | project management | 45h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | validation and support | 34h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | validation and support | 34h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | analysis | 1568h |  |  |  |  | 99 | 100 | 101
3 | analysis - solution concept | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | analysis - solution concept | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | analysis - solution concept | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | analysis - solution concept | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | analysis - solution concept | 17h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | analysis - business analysis | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | analysis validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | design | 272h |  |  |  |  | 99 | 100 | 101
10 | design - SAD/interface design | 41h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | design - SAD/interface design | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | design - CDM/process design | 75h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | design - CDM/process design | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | design validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | development | 568h |  |  |  |  | 99 | 100 | 101
15 | development - coding DMS | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | development - coding ESB | 75h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | development - coding ESB | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | development - coding OMS | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | development - bugfixing | 70h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | development - bugfixing | 25h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | development - bugfixing and support | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | development completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | test ict | 304h |  |  |  |  | 99 | 100 | 101
21 | test ict - test coordination | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | test ict - test execution | 38h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | ict test completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | UAT | 240h |  |  |  |  | 99 | 100 | 101
24 | full handover | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | release handover | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | code freeze | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | implementation | 0 |  |  |  |  | 99 | 100 | 101
27 | go live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2013-08-05 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Generic Document Output System | 2013-04-29 08:00 | 2014-05-09 17:00 | 270d |  |  | 0 |  |  | 64620 |  | 71d | [5 empty] | 2130 |  | 1.899% |  | 1227 | 5700
28 | supporting tasks | 2013-08-19 08:00 | 2014-03-14 10:00 | 149d 2h |  |  | 0 |  |  | 9660 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
1 | project management | 2013-08-19 08:00 | 2013-08-26 14:00 | 5d 5h | Employee A | 4050 | 0 | 0 | 0 | 4050 |  | 0 | 0 | 4050 | 5d 5h | 0 | 0 | 0 | 4050 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | validation and support | 2014-03-10 08:00 | 2014-03-14 10:00 | 4d 2h | Employee B | 2550 | 0 | 0 | 0 | 2550 |  | 0 | 0 | 2550 | 4d 2h | 0 | 0 | 0 | 2550 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | validation and support | 2014-03-10 08:00 | 2014-03-14 10:00 | 4d 2h | Employee A | 3060 | 0 | 0 | 0 | 3060 |  | 0 | 0 | 3060 | 4d 2h | 0 | 0 | 0 | 3060 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | analysis | 2013-04-29 08:00 | 2014-01-27 17:00 | 196d |  |  | 0 |  |  | 6060 |  | 71d | [5 empty] | 2130 |  | 20.25% |  | 1227 | 5700
3 | analysis - solution concept | 2013-04-29 08:00 | 2013-04-29 14:00 | 5h | Employee A | 450 | 0 | 0 | 0 | 450 | 2013-07-08 08:00 | 2h | 180 | 90 | 1h | 0 | 0 | 180 | 90 | 40% | Started | 180 | 450 | 100 | 40 | 40 | 100 | 40 | 40
4 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 17:00 | 3d | Employee B | 1800 | 0 | 0 | 0 | 1800 | 2013-04-29 08:00 | 2d 6h | 1650 | 75 | 1h | 0 | 0 | 1650 | 75 | 47% | Started | 846 | 1800 | 100 | 91.6667 | 47 | 100 | 91.6667 | 47
5 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 17:00 | 3d | Employee C | 1800 | 0 | 0 | 0 | 1800 |  | 0 | 0 | 1800 | 3d | 0 | 0 | 0 | 1800 | 0% | Not Started | 0 | 1800 | 100 |  | 0 | 100 |  | 0
6 | analysis - solution concept | 2013-04-29 08:00 | 2013-04-29 14:00 | 5h | Employee D | 375 | 0 | 0 | 0 | 375 | 2013-08-05 08:00 | 2h | 150 | 75 | 1h | 0 | 0 | 150 | 75 | 40% | Started | 150 | 375 | 100 | 40 | 40 | 100 | 40 | 40
7 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 09:00 | 2d 1h | Employee E | 1275 | 0 | 0 | 0 | 1275 | 2013-08-05 08:00 | 2h | 150 | 75 | 1h | 0 | 0 | 150 | 75 | 4% | Started | 51 | 1275 | 100 | 11.7647 | 4 | 100 | 11.7647 | 4
8 | analysis - business analysis | 2013-12-30 08:00 | 2013-12-30 12:00 | 4h | Employee A | 360 | 0 | 0 | 0 | 360 |  | 0 | 0 | 360 | 4h | 0 | 0 | 0 | 360 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | analysis validated | 2014-01-27 17:00 | 2014-01-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | design | 2014-01-21 08:00 | 2014-03-07 17:00 | 34d |  |  | 0 |  |  | 9150 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
10 | design - SAD/interface design | 2014-01-21 08:00 | 2014-01-28 09:00 | 5d 1h | Employee H | 3075 | 0 | 0 | 0 | 3075 |  | 0 | 0 | 3075 | 5d 1h | 0 | 0 | 0 | 3075 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | design - SAD/interface design | 2014-01-21 08:00 | 2014-01-21 10:00 | 2h | Employee I | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | design - CDM/process design | 2014-01-21 08:00 | 2014-02-03 11:00 | 9d 3h | Employee F | 5625 | 0 | 0 | 0 | 5625 |  | 0 | 0 | 5625 | 9d 3h | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | design - CDM/process design | 2014-01-21 08:00 | 2014-01-21 12:00 | 4h | Employee G | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | design validated | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | development | 2014-01-06 08:00 | 2014-04-14 17:00 | 71d |  |  | 0 |  |  | 36150 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
15 | development - coding DMS | 2014-03-10 08:00 | 2014-03-12 16:00 | 2d 7h | Employee C | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | development - coding ESB | 2014-01-28 08:00 | 2014-02-10 11:00 | 9d 3h | Employee J | 5625 | 0 | 0 | 0 | 5625 |  | 0 | 0 | 5625 | 9d 3h | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | development - coding ESB | 2014-01-28 08:00 | 2014-03-10 17:00 | 30d | Employee E | 18000 | 0 | 0 | 0 | 18000 |  | 0 | 0 | 18000 | 30d | 0 | 0 | 0 | 18000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | development - coding OMS | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d | Employee K | 3000 | 0 | 0 | 0 | 3000 |  | 0 | 0 | 3000 | 5d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | development - bugfixing | 2014-01-06 08:00 | 2014-01-16 15:00 | 8d 6h | Employee C | 5250 | 0 | 0 | 0 | 5250 |  | 0 | 0 | 5250 | 8d 6h | 0 | 0 | 0 | 5250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | development - bugfixing | 2014-01-06 08:00 | 2014-01-09 09:00 | 3d 1h | Employee E | 1875 | 0 | 0 | 0 | 1875 |  | 0 | 0 | 1875 | 3d 1h | 0 | 0 | 0 | 1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | development - bugfixing and support | 2014-01-06 08:00 | 2014-01-07 09:00 | 1d 1h | Employee K | 675 | 0 | 0 | 0 | 675 |  | 0 | 0 | 675 | 1d 1h | 0 | 0 | 0 | 675 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | development completed | 2014-04-14 17:00 | 2014-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | test ict | 2014-02-20 08:00 | 2014-04-14 17:00 | 38d |  |  | 0 |  |  | 3600 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | test ict - test coordination | 2014-02-20 08:00 | 2014-02-21 10:00 | 1d 2h | Employee L | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | test ict - test execution | 2014-03-24 08:00 | 2014-03-28 15:00 | 4d 6h | Employee L | 2850 | 0 | 0 | 0 | 2850 |  | 0 | 0 | 2850 | 4d 6h | 0 | 0 | 0 | 2850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | ict test completed | 2014-04-14 17:00 | 2014-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | UAT | 2014-03-14 17:00 | 2014-04-25 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | full handover | 2014-03-14 17:00 | 2014-03-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | release handover | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2013-12-23 22:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Generic Document Output System | 2013-04-29 08:00 | 2014-05-09 17:00 | 270d |  |  | 0 |  |  | 64620 |  | 171d | [5 empty] | 3360 |  | 3.429% |  | 2215.5 | 9750
28 | supporting tasks | 2013-08-19 08:00 | 2014-03-14 10:00 | 149d 2h |  |  | 0 |  |  | 9660 |  | 91d | [5 empty] | 360 |  | 2.516% |  | 243 | 4050
1 | project management | 2013-08-19 08:00 | 2013-08-26 14:00 | 5d 5h | Employee A | 4050 | 0 | 0 | 0 | 4050 | 2013-08-19 08:00 | 4h | 360 | 1710 | 2d 3h | 0 | 0 | 360 | 1710 | 6% | Started | 243 | 4050 | 100 | 8.8889 | 6 | 100 | 8.8889 | 6
38 | validation and support | 2014-03-10 08:00 | 2014-03-14 10:00 | 4d 2h | Employee B | 2550 | 0 | 0 | 0 | 2550 |  | 0 | 0 | 2550 | 4d 2h | 0 | 0 | 0 | 2550 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | validation and support | 2014-03-10 08:00 | 2014-03-14 10:00 | 4d 2h | Employee A | 3060 | 0 | 0 | 0 | 3060 |  | 0 | 0 | 3060 | 4d 2h | 0 | 0 | 0 | 3060 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | analysis | 2013-04-29 08:00 | 2014-01-27 17:00 | 196d |  |  | 0 |  |  | 6060 |  | 171d | [5 empty] | 3000 |  | 32.55% |  | 1972.5 | 5700
3 | analysis - solution concept | 2013-04-29 08:00 | 2013-04-29 14:00 | 5h | Employee A | 450 | 0 | 0 | 0 | 450 | 2013-07-08 08:00 | 5h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 450 | 450 | 100 | 100 | 100 | 100 | 100 | 100
4 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 17:00 | 3d | Employee B | 1800 | 0 | 0 | 0 | 1800 | 2013-04-29 08:00 | 3d | 1800 | 75 | 1h | 0 | 0 | 1800 | 75 | 51% | Started | 918 | 1800 | 100 | 100 | 51 | 100 | 100 | 51
5 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 17:00 | 3d | Employee C | 1800 | 0 | 0 | 0 | 1800 | 2013-09-23 08:00 | 5h | 375 | 75 | 1h | 0 | 0 | 375 | 75 | 21% | Started | 378 | 1800 | 100 | 20.8333 | 21 | 100 | 20.8333 | 21
6 | analysis - solution concept | 2013-04-29 08:00 | 2013-04-29 14:00 | 5h | Employee D | 375 | 0 | 0 | 0 | 375 | 2013-08-05 08:00 | 2h | 150 | 75 | 1h | 0 | 0 | 150 | 75 | 40% | Started | 150 | 375 | 100 | 40 | 40 | 100 | 40 | 40
7 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 09:00 | 2d 1h | Employee E | 1275 | 0 | 0 | 0 | 1275 | 2013-08-05 08:00 | 3h | 225 | 75 | 1h | 0 | 0 | 225 | 75 | 6% | Started | 76.5 | 1275 | 100 | 17.6471 | 6 | 100 | 17.6471 | 6
8 | analysis - business analysis | 2013-12-30 08:00 | 2013-12-30 12:00 | 4h | Employee A | 360 | 0 | 0 | 0 | 360 |  | 0 | 0 | 360 | 4h | 0 | 0 | 0 | 360 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | analysis validated | 2014-01-27 17:00 | 2014-01-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | design | 2014-01-21 08:00 | 2014-03-07 17:00 | 34d |  |  | 0 |  |  | 9150 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
10 | design - SAD/interface design | 2014-01-21 08:00 | 2014-01-28 09:00 | 5d 1h | Employee H | 3075 | 0 | 0 | 0 | 3075 |  | 0 | 0 | 3075 | 5d 1h | 0 | 0 | 0 | 3075 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | design - SAD/interface design | 2014-01-21 08:00 | 2014-01-21 10:00 | 2h | Employee I | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | design - CDM/process design | 2014-01-21 08:00 | 2014-02-03 11:00 | 9d 3h | Employee F | 5625 | 0 | 0 | 0 | 5625 |  | 0 | 0 | 5625 | 9d 3h | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | design - CDM/process design | 2014-01-21 08:00 | 2014-01-21 12:00 | 4h | Employee G | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | design validated | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | development | 2014-01-06 08:00 | 2014-04-14 17:00 | 71d |  |  | 0 |  |  | 36150 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
15 | development - coding DMS | 2014-03-10 08:00 | 2014-03-12 16:00 | 2d 7h | Employee C | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | development - coding ESB | 2014-01-28 08:00 | 2014-02-10 11:00 | 9d 3h | Employee J | 5625 | 0 | 0 | 0 | 5625 |  | 0 | 0 | 5625 | 9d 3h | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | development - coding ESB | 2014-01-28 08:00 | 2014-03-10 17:00 | 30d | Employee E | 18000 | 0 | 0 | 0 | 18000 |  | 0 | 0 | 18000 | 30d | 0 | 0 | 0 | 18000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | development - coding OMS | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d | Employee K | 3000 | 0 | 0 | 0 | 3000 |  | 0 | 0 | 3000 | 5d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | development - bugfixing | 2014-01-06 08:00 | 2014-01-16 15:00 | 8d 6h | Employee C | 5250 | 0 | 0 | 0 | 5250 |  | 0 | 0 | 5250 | 8d 6h | 0 | 0 | 0 | 5250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | development - bugfixing | 2014-01-06 08:00 | 2014-01-09 09:00 | 3d 1h | Employee E | 1875 | 0 | 0 | 0 | 1875 |  | 0 | 0 | 1875 | 3d 1h | 0 | 0 | 0 | 1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | development - bugfixing and support | 2014-01-06 08:00 | 2014-01-07 09:00 | 1d 1h | Employee K | 675 | 0 | 0 | 0 | 675 |  | 0 | 0 | 675 | 1d 1h | 0 | 0 | 0 | 675 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | development completed | 2014-04-14 17:00 | 2014-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | test ict | 2014-02-20 08:00 | 2014-04-14 17:00 | 38d |  |  | 0 |  |  | 3600 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | test ict - test coordination | 2014-02-20 08:00 | 2014-02-21 10:00 | 1d 2h | Employee L | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | test ict - test execution | 2014-03-24 08:00 | 2014-03-28 15:00 | 4d 6h | Employee L | 2850 | 0 | 0 | 0 | 2850 |  | 0 | 0 | 2850 | 4d 6h | 0 | 0 | 0 | 2850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | ict test completed | 2014-04-14 17:00 | 2014-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | UAT | 2014-03-14 17:00 | 2014-04-25 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | full handover | 2014-03-14 17:00 | 2014-03-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | release handover | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-02-03 22:00 |  | TP Name | Tracking 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Generic Document Output System | 2013-04-29 08:00 | 2014-05-09 17:00 | 270d |  |  | 0 |  |  | 64620 |  | 201d | [5 empty] | 11430 |  | 21.82% |  | 14098.4999 | 33060
28 | supporting tasks | 2013-08-19 08:00 | 2014-03-14 10:00 | 149d 2h |  |  | 0 |  |  | 9660 |  | 121d | [5 empty] | 1170 |  | 9.224% |  | 891 | 4050
1 | project management | 2013-08-19 08:00 | 2013-08-26 14:00 | 5d 5h | Employee A | 4050 | 0 | 0 | 0 | 4050 | 2013-08-19 08:00 | 1d 5h | 1170 | 900 | 1d 2h | 0 | 0 | 1170 | 900 | 22% | Started | 891 | 4050 | 100 | 28.8889 | 22 | 100 | 28.8889 | 22
38 | validation and support | 2014-03-10 08:00 | 2014-03-14 10:00 | 4d 2h | Employee B | 2550 | 0 | 0 | 0 | 2550 |  | 0 | 0 | 2550 | 4d 2h | 0 | 0 | 0 | 2550 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | validation and support | 2014-03-10 08:00 | 2014-03-14 10:00 | 4d 2h | Employee A | 3060 | 0 | 0 | 0 | 3060 |  | 0 | 0 | 3060 | 4d 2h | 0 | 0 | 0 | 3060 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | analysis | 2013-04-29 08:00 | 2014-01-27 17:00 | 196d |  |  | 0 |  |  | 6060 |  | 201d | [5 empty] | 4635 |  | 46.1% |  | 2793.75 | 6060
3 | analysis - solution concept | 2013-04-29 08:00 | 2013-04-29 14:00 | 5h | Employee A | 450 | 0 | 0 | 0 | 450 | 2013-07-08 08:00 | 5h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 450 | 450 | 100 | 100 | 100 | 100 | 100 | 100
4 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 17:00 | 3d | Employee B | 1800 | 0 | 0 | 0 | 1800 | 2013-04-29 08:00 | 3d | 1800 | 75 | 1h | 0 | 0 | 1800 | 75 | 51% | Started | 918 | 1800 | 100 | 100 | 51 | 100 | 100 | 51
5 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 17:00 | 3d | Employee C | 1800 | 0 | 0 | 0 | 1800 | 2013-09-23 08:00 | 5h | 375 | 75 | 1h | 0 | 0 | 375 | 75 | 21% | Started | 378 | 1800 | 100 | 20.8333 | 21 | 100 | 20.8333 | 21
6 | analysis - solution concept | 2013-04-29 08:00 | 2013-04-29 14:00 | 5h | Employee D | 375 | 0 | 0 | 0 | 375 | 2013-08-05 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
7 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 09:00 | 2d 1h | Employee E | 1275 | 0 | 0 | 0 | 1275 | 2013-08-05 08:00 | 2d 1h | 1275 | 75 | 1h | 0 | 0 | 1275 | 75 | 33% | Started | 420.75 | 1275 | 100 | 100 | 33 | 100 | 100 | 33
8 | analysis - business analysis | 2013-12-30 08:00 | 2013-12-30 12:00 | 4h | Employee A | 360 | 0 | 0 | 0 | 360 | 2013-12-30 08:00 | 4h | 360 | 90 | 1h | 0 | 0 | 360 | 90 | 70% | Started | 252 | 360 | 100 | 100 | 70 | 100 | 100 | 70
9 | analysis validated | 2014-01-27 17:00 | 2014-01-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | design | 2014-01-21 08:00 | 2014-03-07 17:00 | 34d |  |  | 0 |  |  | 9150 |  | 11d | [5 empty] | 2250 |  | 13.48% |  | 1233.75 | 9150
10 | design - SAD/interface design | 2014-01-21 08:00 | 2014-01-28 09:00 | 5d 1h | Employee H | 3075 | 0 | 0 | 0 | 3075 | 2014-01-20 08:00 | 2d 3h | 1425 | 75 | 1h | 0 | 0 | 1425 | 75 | 20% | Started | 615 | 3075 | 100 | 46.3415 | 20 | 100 | 46.3415 | 20
11 | design - SAD/interface design | 2014-01-21 08:00 | 2014-01-21 10:00 | 2h | Employee I | 150 | 0 | 0 | 0 | 150 | 2014-01-20 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
12 | design - CDM/process design | 2014-01-21 08:00 | 2014-02-03 11:00 | 9d 3h | Employee F | 5625 | 0 | 0 | 0 | 5625 | 2014-01-20 08:00 | 5h | 375 | 3000 | 5d | 0 | 0 | 375 | 3000 | 3% | Started | 168.75 | 5625 | 100 | 6.6667 | 3 | 100 | 6.6667 | 3
13 | design - CDM/process design | 2014-01-21 08:00 | 2014-01-21 12:00 | 4h | Employee G | 300 | 0 | 0 | 0 | 300 | 2014-01-20 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
14 | design validated | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | development | 2014-01-06 08:00 | 2014-04-14 17:00 | 71d |  |  | 0 |  |  | 36150 |  | 21d | [5 empty] | 3375 |  | 25.39% |  | 9179.9999 | 13800
15 | development - coding DMS | 2014-03-10 08:00 | 2014-03-12 16:00 | 2d 7h | Employee C | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | development - coding ESB | 2014-01-28 08:00 | 2014-02-10 11:00 | 9d 3h | Employee J | 5625 | 0 | 0 | 0 | 5625 | 2014-01-28 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 5625 | 3000 | 100 | 1.3333 | 100 | 100 | 1.3333 | 100
17 | development - coding ESB | 2014-01-28 08:00 | 2014-03-10 17:00 | 30d | Employee E | 18000 | 0 | 0 | 0 | 18000 | 2014-01-27 08:00 | 4d 3h | 2625 | 8100 | 13d 4h | 0 | 0 | 2625 | 8100 | 16% | Started | 2879.9999 | 3000 | 100 | 14.5833 | 16 | 100 | 14.5833 | 16
18 | development - coding OMS | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d | Employee K | 3000 | 0 | 0 | 0 | 3000 |  | 0 | 0 | 3000 | 5d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | development - bugfixing | 2014-01-06 08:00 | 2014-01-16 15:00 | 8d 6h | Employee C | 5250 | 0 | 0 | 0 | 5250 |  | 0 | 0 | 5250 | 8d 6h | 0 | 0 | 0 | 5250 | 0% | Not Started | 0 | 5250 | 100 |  | 0 | 100 |  | 0
37 | development - bugfixing | 2014-01-06 08:00 | 2014-01-09 09:00 | 3d 1h | Employee E | 1875 | 0 | 0 | 0 | 1875 |  | 0 | 0 | 1875 | 3d 1h | 0 | 0 | 0 | 1875 | 0% | Not Started | 0 | 1875 | 100 |  | 0 | 100 |  | 0
19 | development - bugfixing and support | 2014-01-06 08:00 | 2014-01-07 09:00 | 1d 1h | Employee K | 675 | 0 | 0 | 0 | 675 | 2014-01-06 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 675 | 675 | 100 | 100 | 100 | 100 | 100 | 100
20 | development completed | 2014-04-14 17:00 | 2014-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | test ict | 2014-02-20 08:00 | 2014-04-14 17:00 | 38d |  |  | 0 |  |  | 3600 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | test ict - test coordination | 2014-02-20 08:00 | 2014-02-21 10:00 | 1d 2h | Employee L | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | test ict - test execution | 2014-03-24 08:00 | 2014-03-28 15:00 | 4d 6h | Employee L | 2850 | 0 | 0 | 0 | 2850 |  | 0 | 0 | 2850 | 4d 6h | 0 | 0 | 0 | 2850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | ict test completed | 2014-04-14 17:00 | 2014-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | UAT | 2014-03-14 17:00 | 2014-04-25 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | full handover | 2014-03-14 17:00 | 2014-03-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | release handover | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2014-03-03 22:00 |  | TP Name | Tracking 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Generic Document Output System | 2013-04-29 08:00 | 2014-05-09 17:00 | 270d |  |  | 0 |  |  | 64620 |  | 221d | [5 empty] | 30525 |  | 47.67% |  | 30806.9995 | 51435
28 | supporting tasks | 2013-08-19 08:00 | 2014-03-14 10:00 | 149d 2h |  |  | 0 |  |  | 9660 |  | 141d | [5 empty] | 3840 |  | 35.5% |  | 3428.9999 | 4050
1 | project management | 2013-08-19 08:00 | 2013-08-26 14:00 | 5d 5h | Employee A | 4050 | 0 | 0 | 0 | 4050 | 2013-08-19 08:00 | 3d 2h | 2340 | 90 | 1h | 0 | 0 | 2340 | 90 | 45% | Started | 1822.5 | 4050 | 100 | 57.7778 | 45 | 100 | 57.7778 | 45
38 | validation and support | 2014-03-10 08:00 | 2014-03-14 10:00 | 4d 2h | Employee B | 2550 | 0 | 0 | 0 | 2550 | 2014-02-24 08:00 | 2d 4h | 1500 | 75 | 1h | 0 | 0 | 1500 | 75 | 63% | Started | 1606.5 | 0 | 100 | 58.8235 | 63 | 100 | 58.8235 | 63
2 | validation and support | 2014-03-10 08:00 | 2014-03-14 10:00 | 4d 2h | Employee A | 3060 | 0 | 0 | 0 | 3060 |  | 0 | 0 | 3060 | 4d 2h | 0 | 0 | 0 | 3060 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | analysis | 2013-04-29 08:00 | 2014-01-27 17:00 | 196d |  |  | 0 |  |  | 6060 |  | 221d | [5 empty] | 6135 |  | 57.57% |  | 3489 | 6060
3 | analysis - solution concept | 2013-04-29 08:00 | 2013-04-29 14:00 | 5h | Employee A | 450 | 0 | 0 | 0 | 450 | 2013-07-08 08:00 | 5h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 450 | 450 | 100 | 100 | 100 | 100 | 100 | 100
4 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 17:00 | 3d | Employee B | 1800 | 0 | 0 | 0 | 1800 | 2013-04-29 08:00 | 4d 5h | 2775 | 75 | 1h | 0 | 0 | 2775 | 75 | 79% | Started | 1422 | 1800 | 100 | 154.1667 | 79 | 100 | 154.1667 | 79
5 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 17:00 | 3d | Employee C | 1800 | 0 | 0 | 0 | 1800 | 2013-09-23 08:00 | 5h | 375 | 75 | 1h | 0 | 0 | 375 | 75 | 21% | Started | 378 | 1800 | 100 | 20.8333 | 21 | 100 | 20.8333 | 21
6 | analysis - solution concept | 2013-04-29 08:00 | 2013-04-29 14:00 | 5h | Employee D | 375 | 0 | 0 | 0 | 375 | 2013-08-05 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
7 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 09:00 | 2d 1h | Employee E | 1275 | 0 | 0 | 0 | 1275 | 2013-08-05 08:00 | 3d | 1800 | 75 | 1h | 0 | 0 | 1800 | 75 | 48% | Started | 612 | 1275 | 100 | 141.1765 | 48 | 100 | 141.1765 | 48
8 | analysis - business analysis | 2013-12-30 08:00 | 2013-12-30 12:00 | 4h | Employee A | 360 | 0 | 0 | 0 | 360 | 2013-12-30 08:00 | 4h | 360 | 90 | 1h | 0 | 0 | 360 | 90 | 70% | Started | 252 | 360 | 100 | 100 | 70 | 100 | 100 | 70
9 | analysis validated | 2014-01-27 17:00 | 2014-01-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | design | 2014-01-21 08:00 | 2014-03-07 17:00 | 34d |  |  | 0 |  |  | 9150 |  | 31d | [5 empty] | 8100 |  | 48.7% |  | 4456.5 | 9150
10 | design - SAD/interface design | 2014-01-21 08:00 | 2014-01-28 09:00 | 5d 1h | Employee H | 3075 | 0 | 0 | 0 | 3075 | 2014-01-20 08:00 | 4d 2h | 2550 | 75 | 1h | 0 | 0 | 2550 | 75 | 37% | Started | 1137.75 | 3075 | 100 | 82.9268 | 37 | 100 | 82.9268 | 37
11 | design - SAD/interface design | 2014-01-21 08:00 | 2014-01-21 10:00 | 2h | Employee I | 150 | 0 | 0 | 0 | 150 | 2014-01-20 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
12 | design - CDM/process design | 2014-01-21 08:00 | 2014-02-03 11:00 | 9d 3h | Employee F | 5625 | 0 | 0 | 0 | 5625 | 2014-01-20 08:00 | 8d 4h | 5100 | 75 | 1h | 0 | 0 | 5100 | 75 | 51% | Started | 2868.7499 | 5625 | 100 | 90.6667 | 51 | 100 | 90.6667 | 51
13 | design - CDM/process design | 2014-01-21 08:00 | 2014-01-21 12:00 | 4h | Employee G | 300 | 0 | 0 | 0 | 300 | 2014-01-20 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
14 | design validated | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | development | 2014-01-06 08:00 | 2014-04-14 17:00 | 71d |  |  | 0 |  |  | 36150 |  | 41d | [5 empty] | 12225 |  | 53.44% |  | 19319.9996 | 31425
15 | development - coding DMS | 2014-03-10 08:00 | 2014-03-12 16:00 | 2d 7h | Employee C | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | development - coding ESB | 2014-01-28 08:00 | 2014-02-10 11:00 | 9d 3h | Employee J | 5625 | 0 | 0 | 0 | 5625 | 2014-01-28 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 5625 | 5625 | 100 | 1.3333 | 100 | 100 | 1.3333 | 100
17 | development - coding ESB | 2014-01-28 08:00 | 2014-03-10 17:00 | 30d | Employee E | 18000 | 0 | 0 | 0 | 18000 | 2014-01-27 08:00 | 15d 5h | 9375 | 1275 | 2d 1h | 0 | 0 | 9375 | 1275 | 59% | Started | 10619.9995 | 15000 | 100 | 52.0833 | 59 | 100 | 52.0833 | 59
18 | development - coding OMS | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d | Employee K | 3000 | 0 | 0 | 0 | 3000 | 2014-02-17 08:00 | 3d 4h | 2100 | 1875 | 3d 1h | 0 | 0 | 2100 | 1875 | 80% | Started | 2400 | 3000 | 100 | 70 | 80 | 100 | 70 | 80
36 | development - bugfixing | 2014-01-06 08:00 | 2014-01-16 15:00 | 8d 6h | Employee C | 5250 | 0 | 0 | 0 | 5250 |  | 0 | 0 | 5250 | 8d 6h | 0 | 0 | 0 | 5250 | 0% | Not Started | 0 | 5250 | 100 |  | 0 | 100 |  | 0
37 | development - bugfixing | 2014-01-06 08:00 | 2014-01-09 09:00 | 3d 1h | Employee E | 1875 | 0 | 0 | 0 | 1875 |  | 0 | 0 | 1875 | 3d 1h | 0 | 0 | 0 | 1875 | 0% | Not Started | 0 | 1875 | 100 |  | 0 | 100 |  | 0
19 | development - bugfixing and support | 2014-01-06 08:00 | 2014-01-07 09:00 | 1d 1h | Employee K | 675 | 0 | 0 | 0 | 675 | 2014-01-06 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 675 | 675 | 100 | 100 | 100 | 100 | 100 | 100
20 | development completed | 2014-04-14 17:00 | 2014-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | test ict | 2014-02-20 08:00 | 2014-04-14 17:00 | 38d |  |  | 0 |  |  | 3600 |  | 11d | [5 empty] | 225 |  | 3.125% |  | 112.5 | 750
21 | test ict - test coordination | 2014-02-20 08:00 | 2014-02-21 10:00 | 1d 2h | Employee L | 750 | 0 | 0 | 0 | 750 | 2014-02-17 08:00 | 3h | 225 | 375 | 5h | 0 | 0 | 225 | 375 | 15% | Started | 112.5 | 750 | 100 | 30 | 15 | 100 | 30 | 15
22 | test ict - test execution | 2014-03-24 08:00 | 2014-03-28 15:00 | 4d 6h | Employee L | 2850 | 0 | 0 | 0 | 2850 |  | 0 | 0 | 2850 | 4d 6h | 0 | 0 | 0 | 2850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | ict test completed | 2014-04-14 17:00 | 2014-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | UAT | 2014-03-14 17:00 | 2014-04-25 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | full handover | 2014-03-14 17:00 | 2014-03-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | release handover | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2014-04-07 22:00 |  | TP Name | Tracking 5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Generic Document Output System | 2013-04-29 08:00 | 2014-05-09 17:00 | 270d |  |  | 0 |  |  | 64620 |  | 247d | [5 empty] | 60000 |  | 90.95% |  | 58774.8 | 64620
28 | supporting tasks | 2013-08-19 08:00 | 2014-03-14 10:00 | 149d 2h |  |  | 0 |  |  | 9660 |  | 166d | [5 empty] | 8250 |  | 87.67% |  | 8469.3002 | 9660
1 | project management | 2013-08-19 08:00 | 2013-08-26 14:00 | 5d 5h | Employee A | 4050 | 0 | 0 | 0 | 4050 | 2013-08-19 08:00 | 6d 5h | 4770 | 90 | 1h | 0 | 0 | 4770 | 90 | 91% | Started | 3685.5001 | 4050 | 100 | 117.7778 | 91 | 100 | 117.7778 | 91
38 | validation and support | 2014-03-10 08:00 | 2014-03-14 10:00 | 4d 2h | Employee B | 2550 | 0 | 0 | 0 | 2550 | 2014-02-24 08:00 | 4d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2550 | 2550 | 100 | 94.1176 | 100 | 100 | 94.1176 | 100
2 | validation and support | 2014-03-10 08:00 | 2014-03-14 10:00 | 4d 2h | Employee A | 3060 | 0 | 0 | 0 | 3060 | 2014-03-10 08:00 | 1d 4h | 1080 | 2700 | 3d 6h | 0 | 0 | 1080 | 2700 | 73% | Started | 2233.8001 | 3060 | 100 | 35.2941 | 73 | 100 | 35.2941 | 73
29 | analysis | 2013-04-29 08:00 | 2014-01-27 17:00 | 196d |  |  | 0 |  |  | 6060 |  | 246d | [5 empty] | 10275 |  | 98.74% |  | 5983.5 | 6060
3 | analysis - solution concept | 2013-04-29 08:00 | 2013-04-29 14:00 | 5h | Employee A | 450 | 0 | 0 | 0 | 450 | 2013-07-08 08:00 | 5h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 450 | 450 | 100 | 100 | 100 | 100 | 100 | 100
4 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 17:00 | 3d | Employee B | 1800 | 0 | 0 | 0 | 1800 | 2013-04-29 08:00 | 5d 7h | 3525 | 0 | 0 | 0 | 0 | 3525 | 0 | 100% | Finished | 1800 | 1800 | 100 | 195.8333 | 100 | 100 | 195.8333 | 100
5 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 17:00 | 3d | Employee C | 1800 | 0 | 0 | 0 | 1800 | 2013-09-23 08:00 | 3d 2h | 1950 | 0 | 0 | 0 | 0 | 1950 | 0 | 100% | Finished | 1800 | 1800 | 100 | 108.3333 | 100 | 100 | 108.3333 | 100
6 | analysis - solution concept | 2013-04-29 08:00 | 2013-04-29 14:00 | 5h | Employee D | 375 | 0 | 0 | 0 | 375 | 2013-08-05 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
7 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 09:00 | 2d 1h | Employee E | 1275 | 0 | 0 | 0 | 1275 | 2013-08-05 08:00 | 5d 7h | 3525 | 75 | 1h | 0 | 0 | 3525 | 75 | 94% | Started | 1198.5 | 1275 | 100 | 276.4706 | 94 | 100 | 276.4706 | 94
8 | analysis - business analysis | 2013-12-30 08:00 | 2013-12-30 12:00 | 4h | Employee A | 360 | 0 | 0 | 0 | 360 | 2013-12-30 08:00 | 5h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 360 | 360 | 100 | 125 | 100 | 100 | 125 | 100
9 | analysis validated | 2014-01-27 17:00 | 2014-01-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | design | 2014-01-21 08:00 | 2014-03-07 17:00 | 34d |  |  | 0 |  |  | 9150 |  | 56d | [5 empty] | 15975 |  | 92.51% |  | 8464.4998 | 9150
10 | design - SAD/interface design | 2014-01-21 08:00 | 2014-01-28 09:00 | 5d 1h | Employee H | 3075 | 0 | 0 | 0 | 3075 | 2014-01-20 08:00 | 11d | 6600 | 75 | 1h | 0 | 0 | 6600 | 75 | 96% | Started | 2951.9999 | 3075 | 100 | 214.6341 | 96 | 100 | 214.6341 | 96
11 | design - SAD/interface design | 2014-01-21 08:00 | 2014-01-21 10:00 | 2h | Employee I | 150 | 0 | 0 | 0 | 150 | 2014-01-20 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
12 | design - CDM/process design | 2014-01-21 08:00 | 2014-02-03 11:00 | 9d 3h | Employee F | 5625 | 0 | 0 | 0 | 5625 | 2014-01-20 08:00 | 14d 7h | 8925 | 75 | 1h | 0 | 0 | 8925 | 75 | 90% | Started | 5062.4999 | 5625 | 100 | 158.6667 | 90 | 100 | 158.6667 | 90
13 | design - CDM/process design | 2014-01-21 08:00 | 2014-01-21 12:00 | 4h | Employee G | 300 | 0 | 0 | 0 | 300 | 2014-01-20 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
14 | design validated | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | development | 2014-01-06 08:00 | 2014-04-14 17:00 | 71d |  |  | 0 |  |  | 36150 |  | 67d | [5 empty] | 23700 |  | 94.81% |  | 34275 | 36150
15 | development - coding DMS | 2014-03-10 08:00 | 2014-03-12 16:00 | 2d 7h | Employee C | 1725 | 0 | 0 | 0 | 1725 | 2014-03-31 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1725 | 1725 | 100 | 173.913 | 100 | 100 | 173.913 | 100
16 | development - coding ESB | 2014-01-28 08:00 | 2014-02-10 11:00 | 9d 3h | Employee J | 5625 | 0 | 0 | 0 | 5625 | 2014-01-28 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 5625 | 5625 | 100 | 1.3333 | 100 | 100 | 1.3333 | 100
17 | development - coding ESB | 2014-01-28 08:00 | 2014-03-10 17:00 | 30d | Employee E | 18000 | 0 | 0 | 0 | 18000 | 2014-01-27 08:00 | 26d 6h | 16050 | 0 | 0 | 0 | 0 | 16050 | 0 | 100% | Finished | 18000 | 18000 | 100 | 89.1667 | 100 | 100 | 89.1667 | 100
18 | development - coding OMS | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d | Employee K | 3000 | 0 | 0 | 0 | 3000 | 2014-02-17 08:00 | 4d 4h | 2700 | 0 | 0 | 0 | 0 | 2700 | 0 | 100% | Finished | 3000 | 3000 | 100 | 90 | 100 | 100 | 90 | 100
36 | development - bugfixing | 2014-01-06 08:00 | 2014-01-16 15:00 | 8d 6h | Employee C | 5250 | 0 | 0 | 0 | 5250 | 2014-04-07 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 5250 | 5250 | 100 | 22.8571 | 100 | 100 | 22.8571 | 100
37 | development - bugfixing | 2014-01-06 08:00 | 2014-01-09 09:00 | 3d 1h | Employee E | 1875 | 0 | 0 | 0 | 1875 |  | 0 | 0 | 1875 | 3d 1h | 0 | 0 | 0 | 1875 | 0% | Not Started | 0 | 1875 | 100 |  | 0 | 100 |  | 0
19 | development - bugfixing and support | 2014-01-06 08:00 | 2014-01-07 09:00 | 1d 1h | Employee K | 675 | 0 | 0 | 0 | 675 | 2014-01-06 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 675 | 675 | 100 | 100 | 100 | 100 | 100 | 100
20 | development completed | 2014-04-14 17:00 | 2014-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | test ict | 2014-02-20 08:00 | 2014-04-14 17:00 | 38d |  |  | 0 |  |  | 3600 |  | 36d | [5 empty] | 1800 |  | 43.96% |  | 1582.5001 | 3600
21 | test ict - test coordination | 2014-02-20 08:00 | 2014-02-21 10:00 | 1d 2h | Employee L | 750 | 0 | 0 | 0 | 750 | 2014-02-17 08:00 | 2d | 1200 | 75 | 1h | 0 | 0 | 1200 | 75 | 97% | Started | 727.5 | 750 | 100 | 160 | 97 | 100 | 160 | 97
22 | test ict - test execution | 2014-03-24 08:00 | 2014-03-28 15:00 | 4d 6h | Employee L | 2850 | 0 | 0 | 0 | 2850 | 2014-04-07 08:00 | 1d | 600 | 2250 | 3d 6h | 0 | 0 | 600 | 2250 | 30% | Started | 855 | 2850 | 100 | 21.0526 | 30 | 100 | 21.0526 | 30
23 | ict test completed | 2014-04-14 17:00 | 2014-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | UAT | 2014-03-14 17:00 | 2014-04-25 17:00 | 30d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | full handover | 2014-03-14 17:00 | 2014-03-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | release handover | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2014-05-12 08:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Generic Document Output System | 2013-04-29 08:00 | 2014-05-09 17:00 | 270d |  |  | 0 |  |  | 64620 |  | 269d 7h | [5 empty] | 64125 |  | 100% |  | 64620 | 64620
28 | supporting tasks | 2013-08-19 08:00 | 2014-03-14 10:00 | 149d 2h |  |  | 0 |  |  | 9660 |  | 147d 1h | [5 empty] | 9150 |  | 100% |  | 9660 | 9660
1 | project management | 2013-08-19 08:00 | 2013-08-26 14:00 | 5d 5h | Employee A | 4050 | 0 | 0 | 0 | 4050 | 2013-08-19 08:00 | 7d 2h | 5220 | 0 | 0 | 0 | 0 | 5220 | 0 | 100% | Finished | 4050 | 4050 | 100 | 128.8889 | 100 | 100 | 128.8889 | 100
38 | validation and support | 2014-03-10 08:00 | 2014-03-14 10:00 | 4d 2h | Employee B | 2550 | 0 | 0 | 0 | 2550 | 2014-02-24 08:00 | 4d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2550 | 2550 | 100 | 94.1176 | 100 | 100 | 94.1176 | 100
2 | validation and support | 2014-03-10 08:00 | 2014-03-14 10:00 | 4d 2h | Employee A | 3060 | 0 | 0 | 0 | 3060 | 2014-03-10 08:00 | 2d 1h | 1530 | 0 | 0 | 0 | 0 | 1530 | 0 | 100% | Finished | 3060 | 3060 | 100 | 50 | 100 | 100 | 50 | 100
29 | analysis | 2013-04-29 08:00 | 2014-01-27 17:00 | 196d |  |  | 0 |  |  | 6060 |  | 255d 7h | [5 empty] | 10500 |  | 100% |  | 6060 | 6060
3 | analysis - solution concept | 2013-04-29 08:00 | 2013-04-29 14:00 | 5h | Employee A | 450 | 0 | 0 | 0 | 450 | 2013-07-08 08:00 | 5h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 450 | 450 | 100 | 100 | 100 | 100 | 100 | 100
4 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 17:00 | 3d | Employee B | 1800 | 0 | 0 | 0 | 1800 | 2013-04-29 08:00 | 5d 7h | 3525 | 0 | 0 | 0 | 0 | 3525 | 0 | 100% | Finished | 1800 | 1800 | 100 | 195.8333 | 100 | 100 | 195.8333 | 100
5 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 17:00 | 3d | Employee C | 1800 | 0 | 0 | 0 | 1800 | 2013-09-23 08:00 | 3d 2h | 1950 | 0 | 0 | 0 | 0 | 1950 | 0 | 100% | Finished | 1800 | 1800 | 100 | 108.3333 | 100 | 100 | 108.3333 | 100
6 | analysis - solution concept | 2013-04-29 08:00 | 2013-04-29 14:00 | 5h | Employee D | 375 | 0 | 0 | 0 | 375 | 2013-08-05 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
7 | analysis - solution concept | 2013-04-29 08:00 | 2013-05-01 09:00 | 2d 1h | Employee E | 1275 | 0 | 0 | 0 | 1275 | 2013-08-05 08:00 | 6d 2h | 3750 | 0 | 0 | 0 | 0 | 3750 | 0 | 100% | Finished | 1275 | 1275 | 100 | 294.1176 | 100 | 100 | 294.1176 | 100
8 | analysis - business analysis | 2013-12-30 08:00 | 2013-12-30 12:00 | 4h | Employee A | 360 | 0 | 0 | 0 | 360 | 2013-12-30 08:00 | 5h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 360 | 360 | 100 | 125 | 100 | 100 | 125 | 100
9 | analysis validated | 2014-01-27 17:00 | 2014-01-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
30 | design | 2014-01-21 08:00 | 2014-03-07 17:00 | 34d |  |  | 0 |  |  | 9150 |  | 65d 7h | [5 empty] | 17325 |  | 100% |  | 9150 | 9150
10 | design - SAD/interface design | 2014-01-21 08:00 | 2014-01-28 09:00 | 5d 1h | Employee H | 3075 | 0 | 0 | 0 | 3075 | 2014-01-20 08:00 | 11d 4h | 6900 | 0 | 0 | 0 | 0 | 6900 | 0 | 100% | Finished | 3075 | 3075 | 100 | 224.3902 | 100 | 100 | 224.3902 | 100
11 | design - SAD/interface design | 2014-01-21 08:00 | 2014-01-21 10:00 | 2h | Employee I | 150 | 0 | 0 | 0 | 150 | 2014-01-20 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
12 | design - CDM/process design | 2014-01-21 08:00 | 2014-02-03 11:00 | 9d 3h | Employee F | 5625 | 0 | 0 | 0 | 5625 | 2014-01-20 08:00 | 16d 5h | 9975 | 0 | 0 | 0 | 0 | 9975 | 0 | 100% | Finished | 5625 | 5625 | 100 | 177.3333 | 100 | 100 | 177.3333 | 100
13 | design - CDM/process design | 2014-01-21 08:00 | 2014-01-21 12:00 | 4h | Employee G | 300 | 0 | 0 | 0 | 300 | 2014-01-20 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
14 | design validated | 2014-03-07 17:00 | 2014-03-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
31 | development | 2014-01-06 08:00 | 2014-04-14 17:00 | 71d |  |  | 0 |  |  | 36150 |  | 75d 7h | [5 empty] | 24450 |  | 100% |  | 36150 | 36150
15 | development - coding DMS | 2014-03-10 08:00 | 2014-03-12 16:00 | 2d 7h | Employee C | 1725 | 0 | 0 | 0 | 1725 | 2014-03-31 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 1725 | 1725 | 100 | 173.913 | 100 | 100 | 173.913 | 100
16 | development - coding ESB | 2014-01-28 08:00 | 2014-02-10 11:00 | 9d 3h | Employee J | 5625 | 0 | 0 | 0 | 5625 | 2014-01-28 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 5625 | 5625 | 100 | 1.3333 | 100 | 100 | 1.3333 | 100
17 | development - coding ESB | 2014-01-28 08:00 | 2014-03-10 17:00 | 30d | Employee E | 18000 | 0 | 0 | 0 | 18000 | 2014-01-27 08:00 | 26d 6h | 16050 | 0 | 0 | 0 | 0 | 16050 | 0 | 100% | Finished | 18000 | 18000 | 100 | 89.1667 | 100 | 100 | 89.1667 | 100
18 | development - coding OMS | 2014-02-18 08:00 | 2014-02-24 17:00 | 5d | Employee K | 3000 | 0 | 0 | 0 | 3000 | 2014-02-17 08:00 | 4d 4h | 2700 | 0 | 0 | 0 | 0 | 2700 | 0 | 100% | Finished | 3000 | 3000 | 100 | 90 | 100 | 100 | 90 | 100
36 | development - bugfixing | 2014-01-06 08:00 | 2014-01-16 15:00 | 8d 6h | Employee C | 5250 | 0 | 0 | 0 | 5250 | 2014-04-07 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 5250 | 5250 | 100 | 22.8571 | 100 | 100 | 22.8571 | 100
37 | development - bugfixing | 2014-01-06 08:00 | 2014-01-09 09:00 | 3d 1h | Employee E | 1875 | 0 | 0 | 0 | 1875 | 2014-04-14 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1875 | 1875 | 100 | 40 | 100 | 100 | 40 | 100
19 | development - bugfixing and support | 2014-01-06 08:00 | 2014-01-07 09:00 | 1d 1h | Employee K | 675 | 0 | 0 | 0 | 675 | 2014-01-06 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 675 | 675 | 100 | 100 | 100 | 100 | 100 | 100
20 | development completed | 2014-04-14 17:00 | 2014-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
32 | test ict | 2014-02-20 08:00 | 2014-04-14 17:00 | 38d |  |  | 0 |  |  | 3600 |  | 45d 7h | [5 empty] | 2700 |  | 100% |  | 3600 | 3600
21 | test ict - test coordination | 2014-02-20 08:00 | 2014-02-21 10:00 | 1d 2h | Employee L | 750 | 0 | 0 | 0 | 750 | 2014-02-17 08:00 | 2d 1h | 1275 | 0 | 0 | 0 | 0 | 1275 | 0 | 100% | Finished | 750 | 750 | 100 | 170 | 100 | 100 | 170 | 100
22 | test ict - test execution | 2014-03-24 08:00 | 2014-03-28 15:00 | 4d 6h | Employee L | 2850 | 0 | 0 | 0 | 2850 | 2014-04-07 08:00 | 2d 3h | 1425 | 0 | 0 | 0 | 0 | 1425 | 0 | 100% | Finished | 2850 | 2850 | 100 | 50 | 100 | 100 | 50 | 100
23 | ict test completed | 2014-04-14 17:00 | 2014-04-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | UAT | 2014-03-14 17:00 | 2014-04-25 17:00 | 30d |  |  | 0 |  |  | 0 |  | 3d | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | full handover | 2014-03-14 17:00 | 2014-03-14 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-22 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
25 | release handover | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-22 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
26 | code freeze | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
34 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2013-04-29 08:00 | 2013-08-05 22:00 | 5700 | 1227 | 2130 | 2013-04-29 11:00 | -4473 | 21.53% | -903 | 57.61% | -70d 5h | 0.5282% | 51.79% | 2014-06-05 15:00 | 2018-02-16 10:00 | 2021-09-01 11:00 | 2014-07-28 15:00 | 2018-02-16 10:00 | 2021-06-21 09:00 | 2014-08-18 14:00 | 2209-04-07 17:00 | 2353-04-10 09:00 | 65523 | 112176.528 | 296620.7086 | 12004537.9997 | 513348.5889 | 20837605.962 | 127935.2967 | 139373.5735 | 0.0052817 | 0.57606 | 0.21526 | 0.51795 | -70.625 | 0.57606 | 1 | 0.0052817 | 1
Tracking 2 | 2013-08-05 22:00 | 2013-12-23 22:00 | 9750 | 2215.5 | 3360 | 2013-04-29 15:00 | -7534.5 | 22.72% | -1144.5 | 65.94% | -170d 2h | 0.4386% | 69.17% | 2014-06-24 12:00 | 2017-11-16 10:00 | 2020-03-24 17:00 | 2014-11-12 09:00 | 2017-11-16 10:00 | 2019-11-21 15:00 | 2015-01-05 10:00 | 2249-04-13 17:00 | 2370-11-04 15:00 | 65764.5 | 98001.8972 | 277990.5054 | 14231586.0077 | 419861.2467 | 21581712.5691 | 112278.614 | 121465.9702 | 0.004386 | 0.65937 | 0.22723 | 0.69172 | -170.25 | 0.65937 | 1 | 0.004386 | 1
Tracking 3 | 2013-12-23 22:00 | 2014-02-03 22:00 | 33060 | 14098.4999 | 11430 | 2014-01-08 15:00 | -18961.5001 | 42.65% | 2668.4999 | 123.3% | -18d 2h | 90.92% | 30.95% | 2014-08-29 10:00 | 2015-10-01 09:00 | 2015-04-16 10:00 | 2014-10-20 10:00 | 2015-10-01 09:00 | 2015-06-09 11:00 | 2014-06-05 10:00 | 2014-06-17 17:00 | 2014-05-22 15:00 | 61951.5001 | 52389.0204 | 129899.3976 | 66996.7388 | 107476.049 | 56479.3193 | 58555.5382 | 54662.0401 | 0.9092 | 1.2335 | 0.42645 | 0.30953 | -18.25 | 1.2335 | 1 | 0.9092 | 1
Tracking 4 | 2014-02-03 22:00 | 2014-03-03 22:00 | 51435 | 30806.9995 | 30525 | 2014-01-31 12:00 | -20628.0005 | 59.9% | 281.9995 | 100.9% | -21d 4h | 90.27% | 47.64% | 2014-09-09 10:00 | 2015-01-19 15:00 | 2015-01-13 14:00 | 2014-09-11 14:00 | 2015-01-19 15:00 | 2015-01-15 14:00 | 2014-06-10 12:00 | 2014-06-20 09:00 | 2014-06-19 11:00 | 64338.0005 | 64028.4849 | 86978.7836 | 67982.0081 | 86462.02 | 67639.1361 | 66993.6209 | 64750.9837 | 0.90271 | 1.0092 | 0.59895 | 0.47643 | -21.5 | 1.0092 | 1 | 0.90271 | 1
Tracking 5 | 2014-03-03 22:00 | 2014-04-07 22:00 | 64620 | 58774.8 | 60000 | 2014-03-12 10:00 | -5845.2 | 90.95% | -1225.2 | 97.96% | -18d 6h | 92.38% | 94.85% | 2014-06-13 11:00 | 2014-06-17 16:00 | 2014-06-25 17:00 | 2014-06-11 10:00 | 2014-06-17 16:00 | 2014-06-18 16:00 | 2014-06-05 15:00 | 2014-06-11 10:00 | 2014-06-12 10:00 | 65845.2 | 65967.0471 | 66426.5097 | 66327.4772 | 66560.4746 | 66459.3777 | 66053.6075 | 66035.8103 | 0.92378 | 0.97958 | 0.90955 | 0.94853 | -18.75 | 0.97958 | 1 | 0.92378 | 1
Closure | 2014-04-07 22:00 | 2014-05-12 08:00 | 64620 | 64620 | 64125 | 2014-05-09 17:00 | 0 | 100% | 495 | 100.8% | 0 | 100% | 100% | 2014-05-09 17:00 | 2014-05-09 17:00 | 2014-05-07 16:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 64125 | 64125 | 64125 | 64125 | 64125 | 64125 | 64125 | 64125 | 1 | 1.0077 | 1 | 1 | 0 | 1.0077 | 1 | 1 | 1