## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Insurance Bundling System | 1 |  |  | 2013-04-19 08:00 | 2014-02-05 12:00 | 208d 4h |  |  | 0 |  |  | 281430 | 292.1667
31 | supporting tasks | 1.1 |  |  | 2013-07-16 08:00 | 2013-09-02 17:00 | 35d |  |  | 0 |  |  | 26190 | 48.375
1 | project management | 1.1.1 |  |  | 2013-07-16 08:00 | 2013-09-02 17:00 | 35d | Employee A | 25200 | 0 | 0 | 0 | 25200 | 48.375
2 | project management | 1.1.2 |  |  | 2013-07-16 08:00 | 2013-07-17 11:00 | 1d 3h | Employee B | 990 | 0 | 0 | 0 | 990 | 1.125
30 | analysis | 1.2 |  |  | 2013-04-19 08:00 | 2013-09-27 17:00 | 116d |  |  | 0 |  |  | 38340 | 161.375
3 | analysis - business analysis | 1.2.1 | 6FS;7FS;8FS;9FS;10FS;11FS;12FS | FS4 | 2013-07-01 08:00 | 2013-08-23 11:00 | 39d 3h | Employee D | 23625 | 0 | 0 | 0 | 23625 | 53.125
4 | analysis - datamodel | 1.2.2 | 3FS | FS5 | 2013-09-09 08:00 | 2013-09-13 11:00 | 4d 3h | Employee D | 2625 | 0 | 0 | 0 | 2625 | 4.125
5 | analysis - I/O services | 1.2.3 | 4FS | FS13 | 2013-09-23 08:00 | 2013-09-25 12:00 | 2d 4h | Employee D | 1500 | 0 | 0 | 0 | 1500 | 2.1667
6 | analysis - solution concept | 1.2.4 |  | FS3 | 2013-04-19 08:00 | 2013-04-22 10:00 | 1d 2h | Employee C | 750 | 0 | 0 | 0 | 750 | 3.0833
7 | analysis - solution concept | 1.2.5 |  | FS3 | 2013-04-19 08:00 | 2013-04-30 10:00 | 7d 2h | Employee E | 4350 | 0 | 0 | 0 | 4350 | 11.0833
8 | analysis - solution concept | 1.2.6 |  | FS3 | 2013-04-19 08:00 | 2013-04-26 12:00 | 5d 4h | Employee F | 3300 | 0 | 0 | 0 | 3300 | 7.1667
9 | analysis - solution concept | 1.2.7 |  | FS3 | 2013-04-19 08:00 | 2013-04-19 15:00 | 6h | Employee B | 540 | 0 | 0 | 0 | 540 | 0.29167
10 | analysis - solution concept | 1.2.8 |  | FS3 | 2013-04-19 08:00 | 2013-04-19 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 0.375
11 | analysis - solution concept | 1.2.9 |  | FS3 | 2013-04-19 08:00 | 2013-04-19 16:00 | 7h | Employee H | 525 | 0 | 0 | 0 | 525 | 0.33333
12 | analysis - solution concept | 1.2.10 |  | FS3 | 2013-04-19 08:00 | 2013-04-19 16:00 | 7h | Employee I | 525 | 0 | 0 | 0 | 525 | 0.33333
13 | analysis validated | 1.2.11 | 5FS | FS95 | 2013-09-27 17:00 | 2013-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
29 | design | 1.3 |  |  | 2013-04-19 08:00 | 2013-11-15 17:00 | 151d |  |  | 0 |  |  | 18600 | 210.375
14 | BPA | 1.3.1 | 16FS;17FS | FS28 | 2013-09-16 08:00 | 2013-09-17 10:00 | 1d 2h | Employee J | 750 | 0 | 0 | 0 | 750 | 1.0833
15 | CDM | 1.3.2 |  | FS28 | 2013-10-14 08:00 | 2013-10-14 16:00 | 7h | Employee J | 525 | 0 | 0 | 0 | 525 | 0.33333
16 | classic | 1.3.3 | 19FS;20FS | FS14;FS22;FS27 | 2013-08-21 08:00 | 2013-08-23 14:00 | 2d 5h | Employee K | 1575 | 0 | 0 | 0 | 1575 | 2.25
17 | classic | 1.3.4 | 19FS;20FS | FS14;FS22;FS27 | 2013-08-21 08:00 | 2013-08-26 10:00 | 3d 2h | Employee L | 1950 | 0 | 0 | 0 | 1950 | 5.0833
18 | SAD/interface design | 1.3.5 |  | FS28 | 2013-10-21 08:00 | 2013-10-25 11:00 | 4d 3h | Employee L | 2625 | 0 | 0 | 0 | 2625 | 4.125
19 | BPA | 1.3.6 |  | FS16;FS17 | 2013-04-19 08:00 | 2013-04-19 09:00 | 1h | Employee J | 75 | 0 | 0 | 0 | 75 | 0.041667
20 | CDM | 1.3.7 |  | FS16;FS17 | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Employee J | 225 | 0 | 0 | 0 | 225 | 0.125
21 | get NB | 1.3.8 |  | FS28 | 2013-09-30 08:00 | 2013-10-03 16:00 | 3d 7h | Employee M | 2325 | 0 | 0 | 0 | 2325 | 3.3333
22 | PO - BPA | 1.3.9 | 16FS;17FS | FS28 | 2013-09-18 08:00 | 2013-09-18 16:00 | 7h | Employee J | 525 | 0 | 0 | 0 | 525 | 0.33333
23 | PO - CDM | 1.3.10 |  | FS28 | 2013-10-01 08:00 | 2013-10-01 14:00 | 5h | Employee J | 375 | 0 | 0 | 0 | 375 | 0.25
24 | quote - BPA | 1.3.11 |  | FS28 | 2013-10-03 08:00 | 2013-10-04 09:00 | 1d 1h | Employee J | 675 | 0 | 0 | 0 | 675 | 1.0417
25 | quote - CDM | 1.3.12 |  | FS28 | 2013-10-14 08:00 | 2013-10-15 11:00 | 1d 3h | Employee J | 825 | 0 | 0 | 0 | 825 | 1.125
26 | quote - NB | 1.3.13 |  | FS28 | 2013-10-07 08:00 | 2013-10-07 16:00 | 7h | Employee M | 525 | 0 | 0 | 0 | 525 | 0.33333
27 | web - user interface design | 1.3.14 | 16FS;17FS | FS28 | 2013-09-16 08:00 | 2013-09-25 09:00 | 7d 1h | Employee L | 4275 | 0 | 0 | 0 | 4275 | 9.0417
96 | web - user interface integratie | 1.3.15 |  | FS28 | 2013-11-12 08:00 | 2013-11-14 10:00 | 2d 2h | Employee L | 1350 | 0 | 0 | 0 | 1350 | 2.0833
28 | design validated | 1.3.16 | 15FS;18FS;96FS;14FS;21FS;22FS;23FS;24FS;25FS;26FS;27FS | FS95 | 2013-11-15 17:00 | 2013-11-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
66 | build | 1.4 |  |  | 2013-09-24 08:00 | 2013-12-16 17:00 | 60d |  |  | 0 |  |  | 81825 | 83.375
32 | GP - classic | 1.4.1 |  | FS65 | 2013-10-14 08:00 | 2013-10-29 10:00 | 11d 2h | Employee N | 6750 | 0 | 0 | 0 | 6750 | 15.0833
33 | GP - classic | 1.4.2 |  | FS65 | 2013-10-14 08:00 | 2013-10-14 16:00 | 7h | Employee E | 525 | 0 | 0 | 0 | 525 | 0.33333
34 | GP - ESB | 1.4.3 |  | FS65 | 2013-11-04 08:00 | 2013-11-05 17:00 | 2d | Employee O | 1200 | 0 | 0 | 0 | 1200 | 1.375
35 | GP - technical assembly test | 1.4.4 |  | FS65 | 2013-11-18 08:00 | 2013-11-18 11:00 | 3h | Employee O | 225 | 0 | 0 | 0 | 225 | 0.125
36 | classic - arbeidsongeval | 1.4.5 |  | FS65 | 2013-09-30 08:00 | 2013-09-30 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 0.16667
37 | classic - arbeidsongeval | 1.4.6 |  | FS65 | 2013-09-30 08:00 | 2013-10-10 14:00 | 8d 5h | Employee P | 5175 | 0 | 0 | 0 | 5175 | 10.25
38 | classic - auto | 1.4.7 |  | FS65 | 2013-10-07 08:00 | 2013-10-09 10:00 | 2d 2h | Employee E | 1350 | 0 | 0 | 0 | 1350 | 2.0833
39 | classic - auto | 1.4.8 |  | FS65 | 2013-10-07 08:00 | 2013-10-18 10:00 | 9d 2h | Employee P | 5550 | 0 | 0 | 0 | 5550 | 11.0833
40 | classic - brand | 1.4.9 |  | FS65 | 2013-10-28 08:00 | 2013-10-29 10:00 | 1d 2h | Employee E | 750 | 0 | 0 | 0 | 750 | 1.0833
41 | classic - brand | 1.4.10 |  | FS65 | 2013-10-28 08:00 | 2013-10-28 16:00 | 7h | Employee P | 525 | 0 | 0 | 0 | 525 | 0.33333
42 | classic - cleansing data | 1.4.11 |  | FS65 | 2013-11-04 08:00 | 2013-11-15 11:00 | 9d 3h | Employee N | 5625 | 0 | 0 | 0 | 5625 | 11.125
43 | classic - cleansing | 1.4.12 |  | FS65 | 2013-11-04 08:00 | 2013-11-15 12:00 | 9d 4h | Employee E | 5700 | 0 | 0 | 0 | 5700 | 11.1667
44 | classic - cleansing voorbereiding | 1.4.13 |  | FS65 | 2013-09-30 08:00 | 2013-10-02 16:00 | 2d 7h | Employee N | 1725 | 0 | 0 | 0 | 1725 | 2.3333
45 | classic - cleansing voorbereiding | 1.4.14 |  | FS65 | 2013-09-30 08:00 | 2013-10-04 14:00 | 4d 5h | Employee E | 2775 | 0 | 0 | 0 | 2775 | 4.25
46 | dashboard - BO | 1.4.15 |  | FS65 | 2013-11-12 08:00 | 2013-11-12 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 | 0.29167
47 | dashboard - UI | 1.4.16 |  | FS65 | 2013-11-25 08:00 | 2013-11-25 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 0.16667
48 | dashboard - UI | 1.4.17 |  | FS65 | 2013-11-25 08:00 | 2013-12-16 15:00 | 15d 6h | Employee P | 9450 | 0 | 0 | 0 | 9450 | 21.2917
49 | classic - BO leeg gezin | 1.4.18 |  | FS65 | 2013-09-26 08:00 | 2013-09-26 16:00 | 7h | Employee N | 525 | 0 | 0 | 0 | 525 | 0.33333
50 | classic - BO leeg gezin | 1.4.19 |  | FS65 | 2013-09-26 08:00 | 2013-09-26 10:00 | 2h | Employee E | 150 | 0 | 0 | 0 | 150 | 0.083333
51 | classic - BO | 1.4.20 |  | FS65 | 2013-10-21 08:00 | 2013-11-04 11:00 | 10d 3h | Employee E | 6225 | 0 | 0 | 0 | 6225 | 14.125
52 | classic - annuleren | 1.4.21 |  | FS65 | 2013-11-25 08:00 | 2013-11-27 11:00 | 2d 3h | Employee E | 1425 | 0 | 0 | 0 | 1425 | 2.125
53 | classic - voltooien | 1.4.22 |  | FS65 | 2013-11-18 08:00 | 2013-11-20 11:00 | 2d 3h | Employee E | 1425 | 0 | 0 | 0 | 1425 | 2.125
54 | classic - UI detail | 1.4.23 |  | FS65 | 2013-09-25 08:00 | 2013-09-25 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 | 0.29167
55 | classic - UI | 1.4.24 |  | FS65 | 2013-09-24 08:00 | 2013-09-26 09:00 | 2d 1h | Employee E | 1275 | 0 | 0 | 0 | 1275 | 2.0417
56 | classic - inhoud | 1.4.25 |  | FS65 | 2013-09-30 08:00 | 2013-10-08 15:00 | 6d 6h | Employee E | 4050 | 0 | 0 | 0 | 4050 | 8.2917
57 | classic - leden | 1.4.26 |  | FS65 | 2013-11-12 08:00 | 2013-11-12 17:00 | 1d | Employee P | 600 | 0 | 0 | 0 | 600 | 0.375
58 | classic - varia | 1.4.27 |  | FS65 | 2013-10-22 08:00 | 2013-10-22 14:00 | 5h | Employee E | 375 | 0 | 0 | 0 | 375 | 0.25
59 | classic - varia | 1.4.28 |  | FS65 | 2013-10-22 08:00 | 2013-10-29 14:00 | 5d 5h | Employee P | 3375 | 0 | 0 | 0 | 3375 | 7.25
61 | get NB - ESB | 1.4.29 |  | FS65 | 2013-11-18 08:00 | 2013-11-20 17:00 | 3d | Employee V | 1800 | 0 | 0 | 0 | 1800 | 2.375
62 | PO - classic | 1.4.30 |  | FS65 | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d | Employee E | 3000 | 0 | 0 | 0 | 3000 | 4.375
63 | quote - ESB | 1.4.31 |  | FS65 | 2013-11-18 08:00 | 2013-11-19 14:00 | 1d 5h | Employee O | 975 | 0 | 0 | 0 | 975 | 1.25
64 | web | 1.4.32 |  | FS65 | 2013-11-18 08:00 | 2013-11-19 17:00 | 2d | Employee H | 1200 | 0 | 0 | 0 | 1200 | 1.375
97 | web | 1.4.33 |  | FS65 | 2013-11-18 08:00 | 2013-12-02 17:00 | 11d | Employee Q | 6600 | 0 | 0 | 0 | 6600 | 14.375
65 | build validated | 1.4.34 | 32FS;38FS;37FS;36FS;35FS;34FS;33FS;39FS;40FS;41FS;42FS;43FS;44FS;45FS;46FS;47FS;48FS;49FS;50FS;51FS;52FS;53FS;54FS;55FS;56FS;57FS;58FS;59FS;61FS;62FS;63FS;64FS;97FS | FS95 | 2013-12-16 17:00 | 2013-12-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
93 | test ict | 1.5 |  |  | 2013-10-10 08:00 | 2014-01-24 17:00 | 77d |  |  | 0 |  |  | 90675 | 106.375
67 | test coordination | 1.5.1 |  | FS68;FS69;FS70;FS71 | 2013-10-14 08:00 | 2013-10-25 09:00 | 9d 1h | Employee R | 5475 | 0 | 0 | 0 | 5475 | 11.0417
68 | test execution | 1.5.2 | 72FS;67FS | FS83 | 2013-11-18 08:00 | 2013-12-13 12:00 | 19d 4h | Employee S | 11700 | 0 | 0 | 0 | 11700 | 25.1667
69 | test execution | 1.5.3 | 73FS;67FS | FS83 | 2013-11-18 08:00 | 2013-12-18 16:00 | 22d 7h | Employee R | 13725 | 0 | 0 | 0 | 13725 | 30.3333
70 | test execution | 1.5.4 | 74FS;67FS | FS83 | 2013-11-18 08:00 | 2013-12-16 09:00 | 20d 1h | Employee T | 12075 | 0 | 0 | 0 | 12075 | 28.0417
71 | test execution | 1.5.5 | 75FS;67FS | FS83 | 2013-11-18 08:00 | 2013-11-18 16:00 | 7h | Employee L | 525 | 0 | 0 | 0 | 525 | 0.33333
72 | test preparation | 1.5.6 |  | FS68 | 2013-10-10 08:00 | 2013-10-10 14:00 | 5h | Employee S | 375 | 0 | 0 | 0 | 375 | 0.25
73 | test preparation | 1.5.7 |  | FS69 | 2013-10-10 08:00 | 2013-10-21 17:00 | 8d | Employee R | 4800 | 0 | 0 | 0 | 4800 | 11.375
74 | test preparation | 1.5.8 |  | FS70 | 2013-10-10 08:00 | 2013-10-30 10:00 | 14d 2h | Employee T | 8550 | 0 | 0 | 0 | 8550 | 20.0833
75 | test preparation | 1.5.9 |  | FS71 | 2013-10-10 08:00 | 2013-10-14 15:00 | 2d 6h | Employee U | 1650 | 0 | 0 | 0 | 1650 | 4.2917
76 | bugfixing | 1.5.10 |  | FS83 | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee V | 1725 | 0 | 0 | 0 | 1725 | 2.3333
77 | bugfixing | 1.5.11 |  | FS83 | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee W | 1725 | 0 | 0 | 0 | 1725 | 2.3333
78 | bugfixing | 1.5.12 |  | FS83 | 2013-12-02 08:00 | 2013-12-02 15:00 | 6h | Employee Q | 450 | 0 | 0 | 0 | 450 | 0.29167
79 | bugfixing | 1.5.13 |  | FS83 | 2013-12-02 08:00 | 2013-12-09 14:00 | 5d 5h | Employee N | 3375 | 0 | 0 | 0 | 3375 | 7.25
80 | bugfixing | 1.5.14 |  | FS83 | 2013-12-02 08:00 | 2014-01-06 12:00 | 25d 4h | Employee E | 15300 | 0 | 0 | 0 | 15300 | 35.1667
81 | bugfixing | 1.5.15 |  | FS83 | 2013-12-02 08:00 | 2013-12-02 12:00 | 4h | Employee X | 300 | 0 | 0 | 0 | 300 | 0.16667
82 | bugfixing | 1.5.16 |  | FS83 | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee L | 1725 | 0 | 0 | 0 | 1725 | 2.3333
98 | bugfixing | 1.5.17 |  | FS83 | 2013-12-02 08:00 | 2013-12-17 17:00 | 12d | Employee P | 7200 | 0 | 0 | 0 | 7200 | 15.375
83 | ict test completed | 1.5.18 | 98FS;68FS;69FS;70FS;71FS;76FS;77FS;78FS;79FS;80FS;81FS;82FS | FS95 | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
94 | ondersteuning | 1.6 |  |  | 2013-09-17 08:00 | 2013-10-17 10:00 | 22d 2h |  |  | 0 |  |  | 17400 | 30.0833
84 | ondersteuning tijdens design/build/test | 1.6.1 |  | FS95 | 2013-09-17 08:00 | 2013-09-17 09:00 | 1h | Employee J | 75 | 0 | 0 | 0 | 75 | 0.041667
85 | ondersteuning tijdens design/build/test | 1.6.2 |  | FS95 | 2013-09-17 08:00 | 2013-09-17 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 | 0.375
86 | ondersteuning tijdens design/build/test | 1.6.3 |  | FS95 | 2013-09-17 08:00 | 2013-09-24 14:00 | 5d 5h | Employee G | 3375 | 0 | 0 | 0 | 3375 | 7.25
87 | ondersteuning tijdens design/build/test | 1.6.4 |  | FS95 | 2013-09-17 08:00 | 2013-10-17 10:00 | 22d 2h | Employee D | 13350 | 0 | 0 | 0 | 13350 | 30.0833
100 | implementation | 1.7 |  |  | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  |  | 0 |  |  | 0
95 | go live | 1.7.1 | 84FS;85FS;86FS;87FS;13FS;28FS;65FS;83FS | FS88;FS89;FS90;FS91;FS92 | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
101 | post implementation | 1.8 |  |  | 2014-01-27 08:00 | 2014-02-05 12:00 | 7d 4h |  |  | 0 |  |  | 8400 | 9.1667
88 | post implementation - post go live support | 1.8.1 | 95FS |  | 2014-01-27 08:00 | 2014-02-05 12:00 | 7d 4h | Employee E | 4500 | 0 | 0 | 0 | 4500 | 9.1667
89 | post implementation - post go live support | 1.8.2 | 95FS |  | 2014-01-27 08:00 | 2014-01-29 11:00 | 2d 3h | Employee R | 1425 | 0 | 0 | 0 | 1425 | 2.125
90 | post implementation - post go live support | 1.8.3 | 95FS |  | 2014-01-27 08:00 | 2014-01-28 09:00 | 1d 1h | Employee T | 675 | 0 | 0 | 0 | 675 | 1.0417
91 | post implementation - post go live support | 1.8.4 | 95FS |  | 2014-01-27 08:00 | 2014-01-27 10:00 | 2h | Employee L | 150 | 0 | 0 | 0 | 150 | 0.083333
92 | post implementation - post go live support | 1.8.5 | 95FS |  | 2014-01-27 08:00 | 2014-01-29 15:00 | 2d 6h | Employee D | 1650 | 0 | 0 | 0 | 1650 | 2.2917

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee A | Renewable | 1 | 0 | 90 | 1; | 25200
2 | Employee B | Renewable | 1 | 0 | 90 | 2;9; | 1530
3 | Employee C | Renewable | 1 | 0 | 75 | 6;85; | 1350
4 | Employee D | Renewable | 1 | 0 | 75 | 3;4;5;87;92; | 42750
5 | Employee E | Renewable | 1 | 0 | 75 | 7;33;36;38;40;43;45;46;47;50;51;52;53;54;55;56;58;62;80;88; | 54675
6 | Employee F | Renewable | 1 | 0 | 75 | 8; | 3300
7 | Employee G | Renewable | 1 | 0 | 75 | 10;86; | 3975
8 | Employee H | Renewable | 1 | 0 | 75 | 11;64; | 1725
9 | Employee I | Renewable | 1 | 0 | 75 | 12; | 525
10 | Employee J | Renewable | 1 | 0 | 75 | 14;15;19;20;22;23;24;25;84; | 4050
11 | Employee K | Renewable | 1 | 0 | 75 | 16; | 1575
12 | Employee L | Renewable | 1 | 0 | 75 | 17;18;27;96;71;82;91; | 12600
13 | Employee M | Renewable | 1 | 0 | 75 | 21;26; | 2850
14 | Employee N | Renewable | 1 | 0 | 75 | 32;42;44;49;79; | 18000
15 | Employee O | Renewable | 1 | 0 | 75 | 34;35;63; | 2400
16 | Employee P | Renewable | 1 | 0 | 75 | 37;39;41;48;57;59;98; | 31875
17 | Employee Q | Renewable | 1 | 0 | 75 | 97;78; | 7050
18 | Employee R | Renewable | 1 | 0 | 75 | 67;69;73;89; | 25425
19 | Employee S | Renewable | 1 | 0 | 75 | 68;72; | 12075
20 | Employee T | Renewable | 1 | 0 | 75 | 70;74;90; | 21300
21 | Employee U | Renewable | 1 | 0 | 75 | 75; | 1650
22 | Employee V | Renewable | 1 | 0 | 75 | 61;76; | 3525
23 | Employee W | Renewable | 1 | 0 | 75 | 77; | 1725
24 | Employee X | Renewable | 1 | 0 | 75 | 81; | 300

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Insurance Bundling System | 1668h |  |  |  |  | 99 | 100 | 101
31 | supporting tasks | 280h |  |  |  |  | 99 | 100 | 101
1 | project management | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | project management | 11h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | analysis | 928h |  |  |  |  | 99 | 100 | 101
3 | analysis - business analysis | 315h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | analysis - datamodel | 35h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | analysis - I/O services | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | analysis - solution concept | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | analysis - solution concept | 58h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | analysis - solution concept | 44h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | analysis - solution concept | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | analysis - solution concept | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | analysis - solution concept | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | analysis - solution concept | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | analysis validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | design | 1208h |  |  |  |  | 99 | 100 | 101
14 | BPA | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | CDM | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | classic | 21h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | classic | 26h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | SAD/interface design | 35h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | BPA | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | CDM | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | get NB | 31h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | PO - BPA | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | PO - CDM | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | quote - BPA | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | quote - CDM | 11h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | quote - NB | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | web - user interface design | 57h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
96 | web - user interface integratie | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | design validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | build | 480h |  |  |  |  | 99 | 100 | 101
32 | GP - classic | 90h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | GP - classic | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | GP - ESB | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | GP - technical assembly test | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | classic - arbeidsongeval | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | classic - arbeidsongeval | 69h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | classic - auto | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | classic - auto | 74h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | classic - brand | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | classic - brand | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | classic - cleansing data | 75h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | classic - cleansing | 76h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | classic - cleansing voorbereiding | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | classic - cleansing voorbereiding | 37h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | dashboard - BO | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | dashboard - UI | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | dashboard - UI | 126h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | classic - BO leeg gezin | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | classic - BO leeg gezin | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | classic - BO | 83h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | classic - annuleren | 19h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | classic - voltooien | 19h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | classic - UI detail | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | classic - UI | 17h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | classic - inhoud | 54h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | classic - leden | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | classic - varia | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | classic - varia | 45h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | get NB - ESB | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | PO - classic | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | quote - ESB | 13h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | web | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
97 | web | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | build validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
93 | test ict | 616h |  |  |  |  | 99 | 100 | 101
67 | test coordination | 73h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
68 | test execution | 156h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | test execution | 183h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
70 | test execution | 161h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | test execution | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
72 | test preparation | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
73 | test preparation | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | test preparation | 114h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
75 | test preparation | 22h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
76 | bugfixing | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
77 | bugfixing | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
78 | bugfixing | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
79 | bugfixing | 45h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
80 | bugfixing | 204h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
81 | bugfixing | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
82 | bugfixing | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
98 | bugfixing | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
83 | ict test completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
94 | ondersteuning | 178h |  |  |  |  | 99 | 100 | 101
84 | ondersteuning tijdens design/build/test | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
85 | ondersteuning tijdens design/build/test | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | ondersteuning tijdens design/build/test | 45h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
87 | ondersteuning tijdens design/build/test | 178h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
100 | implementation | 0 |  |  |  |  | 99 | 100 | 101
95 | go live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
101 | post implementation | 60h |  |  |  |  | 99 | 100 | 101
88 | post implementation - post go live support | 60h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
89 | post implementation - post go live support | 19h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
90 | post implementation - post go live support | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
91 | post implementation - post go live support | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
92 | post implementation - post go live support | 22h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2013-07-01 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Insurance Bundling System | 2013-04-19 08:00 | 2014-02-05 12:00 | 208d 4h |  |  | 0 |  |  | 281430 |  | 52d | [5 empty] | 3150 |  | 0.8368% |  | 2355 | 11490
31 | supporting tasks | 2013-07-16 08:00 | 2013-09-02 17:00 | 35d |  |  | 0 |  |  | 26190 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
1 | project management | 2013-07-16 08:00 | 2013-09-02 17:00 | 35d | Employee A | 25200 | 0 | 0 | 0 | 25200 |  | 0 | 0 | 25200 | 35d | 0 | 0 | 0 | 25200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | project management | 2013-07-16 08:00 | 2013-07-17 11:00 | 1d 3h | Employee B | 990 | 0 | 0 | 0 | 990 |  | 0 | 0 | 990 | 1d 3h | 0 | 0 | 0 | 990 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | analysis | 2013-04-19 08:00 | 2013-09-27 17:00 | 116d |  |  | 0 |  |  | 38340 |  | 52d | [5 empty] | 3150 |  | 6.142% |  | 2355 | 11190
3 | analysis - business analysis | 2013-07-01 08:00 | 2013-08-23 11:00 | 39d 3h | Employee D | 23625 | 0 | 0 | 0 | 23625 | 2013-07-01 08:00 | 2d 1h | 1275 | 75 | 1h | 0 | 0 | 1275 | 75 | 2% | Started | 472.5 | 600 | 100 | 5.3968 | 2 | 100 | 5.3968 | 2
4 | analysis - datamodel | 2013-09-09 08:00 | 2013-09-13 11:00 | 4d 3h | Employee D | 2625 | 0 | 0 | 0 | 2625 |  | 0 | 0 | 2625 | 4d 3h | 0 | 0 | 0 | 2625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | analysis - I/O services | 2013-09-23 08:00 | 2013-09-25 12:00 | 2d 4h | Employee D | 1500 | 0 | 0 | 0 | 1500 |  | 0 | 0 | 1500 | 2d 4h | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-22 10:00 | 1d 2h | Employee C | 750 | 0 | 0 | 0 | 750 | 2013-07-01 08:00 | 1h | 75 | 675 | 1d 1h | 0 | 0 | 75 | 675 | 11% | Started | 82.5 | 750 | 100 | 10 | 11 | 100 | 10 | 11
7 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-30 10:00 | 7d 2h | Employee E | 4350 | 0 | 0 | 0 | 4350 | 2013-04-22 08:00 | 7h | 525 | 3825 | 6d 3h | 0 | 0 | 525 | 3825 | 12.07% | Started | 525 | 4350 | 100 | 12.069 | 12.069 | 100 | 12.069 | 12.069
8 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-26 12:00 | 5d 4h | Employee F | 3300 | 0 | 0 | 0 | 3300 | 2013-04-19 08:00 | 2h | 150 | 3150 | 5d 2h | 0 | 0 | 150 | 3150 | 4.545% | Started | 150 | 3300 | 100 | 4.5455 | 4.5455 | 100 | 4.5455 | 4.5455
9 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 15:00 | 6h | Employee B | 540 | 0 | 0 | 0 | 540 |  | 0 | 0 | 540 | 6h | 0 | 0 | 0 | 540 | 0% | Not Started | 0 | 540 | 100 |  | 0 | 100 |  | 0
10 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2013-04-19 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 100 | 100
11 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 16:00 | 7h | Employee H | 525 | 0 | 0 | 0 | 525 | 2013-04-22 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
12 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 16:00 | 7h | Employee I | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 525 | 100 |  | 0 | 100 |  | 0
13 | analysis validated | 2013-09-27 17:00 | 2013-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | design | 2013-04-19 08:00 | 2013-11-15 17:00 | 151d |  |  | 0 |  |  | 18600 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 300
14 | BPA | 2013-09-16 08:00 | 2013-09-17 10:00 | 1d 2h | Employee J | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | CDM | 2013-10-14 08:00 | 2013-10-14 16:00 | 7h | Employee J | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | classic | 2013-08-21 08:00 | 2013-08-23 14:00 | 2d 5h | Employee K | 1575 | 0 | 0 | 0 | 1575 |  | 0 | 0 | 1575 | 2d 5h | 0 | 0 | 0 | 1575 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | classic | 2013-08-21 08:00 | 2013-08-26 10:00 | 3d 2h | Employee L | 1950 | 0 | 0 | 0 | 1950 |  | 0 | 0 | 1950 | 3d 2h | 0 | 0 | 0 | 1950 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | SAD/interface design | 2013-10-21 08:00 | 2013-10-25 11:00 | 4d 3h | Employee L | 2625 | 0 | 0 | 0 | 2625 |  | 0 | 0 | 2625 | 4d 3h | 0 | 0 | 0 | 2625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | BPA | 2013-04-19 08:00 | 2013-04-19 09:00 | 1h | Employee J | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 75 | 100 |  | 0 | 100 |  | 0
20 | CDM | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Employee J | 225 | 0 | 0 | 0 | 225 |  | 0 | 0 | 225 | 3h | 0 | 0 | 0 | 225 | 0% | Not Started | 0 | 225 | 100 |  | 0 | 100 |  | 0
21 | get NB | 2013-09-30 08:00 | 2013-10-03 16:00 | 3d 7h | Employee M | 2325 | 0 | 0 | 0 | 2325 |  | 0 | 0 | 2325 | 3d 7h | 0 | 0 | 0 | 2325 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | PO - BPA | 2013-09-18 08:00 | 2013-09-18 16:00 | 7h | Employee J | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | PO - CDM | 2013-10-01 08:00 | 2013-10-01 14:00 | 5h | Employee J | 375 | 0 | 0 | 0 | 375 |  | 0 | 0 | 375 | 5h | 0 | 0 | 0 | 375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | quote - BPA | 2013-10-03 08:00 | 2013-10-04 09:00 | 1d 1h | Employee J | 675 | 0 | 0 | 0 | 675 |  | 0 | 0 | 675 | 1d 1h | 0 | 0 | 0 | 675 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | quote - CDM | 2013-10-14 08:00 | 2013-10-15 11:00 | 1d 3h | Employee J | 825 | 0 | 0 | 0 | 825 |  | 0 | 0 | 825 | 1d 3h | 0 | 0 | 0 | 825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | quote - NB | 2013-10-07 08:00 | 2013-10-07 16:00 | 7h | Employee M | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | web - user interface design | 2013-09-16 08:00 | 2013-09-25 09:00 | 7d 1h | Employee L | 4275 | 0 | 0 | 0 | 4275 |  | 0 | 0 | 4275 | 7d 1h | 0 | 0 | 0 | 4275 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | web - user interface integratie | 2013-11-12 08:00 | 2013-11-14 10:00 | 2d 2h | Employee L | 1350 | 0 | 0 | 0 | 1350 |  | 0 | 0 | 1350 | 2d 2h | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | design validated | 2013-11-15 17:00 | 2013-11-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | build | 2013-09-24 08:00 | 2013-12-16 17:00 | 60d |  |  | 0 |  |  | 81825 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | GP - classic | 2013-10-14 08:00 | 2013-10-29 10:00 | 11d 2h | Employee N | 6750 | 0 | 0 | 0 | 6750 |  | 0 | 0 | 6750 | 11d 2h | 0 | 0 | 0 | 6750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | GP - classic | 2013-10-14 08:00 | 2013-10-14 16:00 | 7h | Employee E | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | GP - ESB | 2013-11-04 08:00 | 2013-11-05 17:00 | 2d | Employee O | 1200 | 0 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 2d | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | GP - technical assembly test | 2013-11-18 08:00 | 2013-11-18 11:00 | 3h | Employee O | 225 | 0 | 0 | 0 | 225 |  | 0 | 0 | 225 | 3h | 0 | 0 | 0 | 225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | classic - arbeidsongeval | 2013-09-30 08:00 | 2013-09-30 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | classic - arbeidsongeval | 2013-09-30 08:00 | 2013-10-10 14:00 | 8d 5h | Employee P | 5175 | 0 | 0 | 0 | 5175 |  | 0 | 0 | 5175 | 8d 5h | 0 | 0 | 0 | 5175 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | classic - auto | 2013-10-07 08:00 | 2013-10-09 10:00 | 2d 2h | Employee E | 1350 | 0 | 0 | 0 | 1350 |  | 0 | 0 | 1350 | 2d 2h | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | classic - auto | 2013-10-07 08:00 | 2013-10-18 10:00 | 9d 2h | Employee P | 5550 | 0 | 0 | 0 | 5550 |  | 0 | 0 | 5550 | 9d 2h | 0 | 0 | 0 | 5550 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | classic - brand | 2013-10-28 08:00 | 2013-10-29 10:00 | 1d 2h | Employee E | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | classic - brand | 2013-10-28 08:00 | 2013-10-28 16:00 | 7h | Employee P | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | classic - cleansing data | 2013-11-04 08:00 | 2013-11-15 11:00 | 9d 3h | Employee N | 5625 | 0 | 0 | 0 | 5625 |  | 0 | 0 | 5625 | 9d 3h | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | classic - cleansing | 2013-11-04 08:00 | 2013-11-15 12:00 | 9d 4h | Employee E | 5700 | 0 | 0 | 0 | 5700 |  | 0 | 0 | 5700 | 9d 4h | 0 | 0 | 0 | 5700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | classic - cleansing voorbereiding | 2013-09-30 08:00 | 2013-10-02 16:00 | 2d 7h | Employee N | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | classic - cleansing voorbereiding | 2013-09-30 08:00 | 2013-10-04 14:00 | 4d 5h | Employee E | 2775 | 0 | 0 | 0 | 2775 |  | 0 | 0 | 2775 | 4d 5h | 0 | 0 | 0 | 2775 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | dashboard - BO | 2013-11-12 08:00 | 2013-11-12 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 |  | 0 | 0 | 450 | 6h | 0 | 0 | 0 | 450 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | dashboard - UI | 2013-11-25 08:00 | 2013-11-25 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | dashboard - UI | 2013-11-25 08:00 | 2013-12-16 15:00 | 15d 6h | Employee P | 9450 | 0 | 0 | 0 | 9450 |  | 0 | 0 | 9450 | 15d 6h | 0 | 0 | 0 | 9450 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | classic - BO leeg gezin | 2013-09-26 08:00 | 2013-09-26 16:00 | 7h | Employee N | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | classic - BO leeg gezin | 2013-09-26 08:00 | 2013-09-26 10:00 | 2h | Employee E | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | classic - BO | 2013-10-21 08:00 | 2013-11-04 11:00 | 10d 3h | Employee E | 6225 | 0 | 0 | 0 | 6225 |  | 0 | 0 | 6225 | 10d 3h | 0 | 0 | 0 | 6225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | classic - annuleren | 2013-11-25 08:00 | 2013-11-27 11:00 | 2d 3h | Employee E | 1425 | 0 | 0 | 0 | 1425 |  | 0 | 0 | 1425 | 2d 3h | 0 | 0 | 0 | 1425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | classic - voltooien | 2013-11-18 08:00 | 2013-11-20 11:00 | 2d 3h | Employee E | 1425 | 0 | 0 | 0 | 1425 |  | 0 | 0 | 1425 | 2d 3h | 0 | 0 | 0 | 1425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | classic - UI detail | 2013-09-25 08:00 | 2013-09-25 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 |  | 0 | 0 | 450 | 6h | 0 | 0 | 0 | 450 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | classic - UI | 2013-09-24 08:00 | 2013-09-26 09:00 | 2d 1h | Employee E | 1275 | 0 | 0 | 0 | 1275 |  | 0 | 0 | 1275 | 2d 1h | 0 | 0 | 0 | 1275 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | classic - inhoud | 2013-09-30 08:00 | 2013-10-08 15:00 | 6d 6h | Employee E | 4050 | 0 | 0 | 0 | 4050 |  | 0 | 0 | 4050 | 6d 6h | 0 | 0 | 0 | 4050 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | classic - leden | 2013-11-12 08:00 | 2013-11-12 17:00 | 1d | Employee P | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | classic - varia | 2013-10-22 08:00 | 2013-10-22 14:00 | 5h | Employee E | 375 | 0 | 0 | 0 | 375 |  | 0 | 0 | 375 | 5h | 0 | 0 | 0 | 375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | classic - varia | 2013-10-22 08:00 | 2013-10-29 14:00 | 5d 5h | Employee P | 3375 | 0 | 0 | 0 | 3375 |  | 0 | 0 | 3375 | 5d 5h | 0 | 0 | 0 | 3375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | get NB - ESB | 2013-11-18 08:00 | 2013-11-20 17:00 | 3d | Employee V | 1800 | 0 | 0 | 0 | 1800 |  | 0 | 0 | 1800 | 3d | 0 | 0 | 0 | 1800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | PO - classic | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d | Employee E | 3000 | 0 | 0 | 0 | 3000 |  | 0 | 0 | 3000 | 5d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | quote - ESB | 2013-11-18 08:00 | 2013-11-19 14:00 | 1d 5h | Employee O | 975 | 0 | 0 | 0 | 975 |  | 0 | 0 | 975 | 1d 5h | 0 | 0 | 0 | 975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | web | 2013-11-18 08:00 | 2013-11-19 17:00 | 2d | Employee H | 1200 | 0 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 2d | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | web | 2013-11-18 08:00 | 2013-12-02 17:00 | 11d | Employee Q | 6600 | 0 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 11d | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | build validated | 2013-12-16 17:00 | 2013-12-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | test ict | 2013-10-10 08:00 | 2014-01-24 17:00 | 77d |  |  | 0 |  |  | 90675 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
67 | test coordination | 2013-10-14 08:00 | 2013-10-25 09:00 | 9d 1h | Employee R | 5475 | 0 | 0 | 0 | 5475 |  | 0 | 0 | 5475 | 9d 1h | 0 | 0 | 0 | 5475 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | test execution | 2013-11-18 08:00 | 2013-12-13 12:00 | 19d 4h | Employee S | 11700 | 0 | 0 | 0 | 11700 |  | 0 | 0 | 11700 | 19d 4h | 0 | 0 | 0 | 11700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | test execution | 2013-11-18 08:00 | 2013-12-18 16:00 | 22d 7h | Employee R | 13725 | 0 | 0 | 0 | 13725 |  | 0 | 0 | 13725 | 22d 7h | 0 | 0 | 0 | 13725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | test execution | 2013-11-18 08:00 | 2013-12-16 09:00 | 20d 1h | Employee T | 12075 | 0 | 0 | 0 | 12075 |  | 0 | 0 | 12075 | 20d 1h | 0 | 0 | 0 | 12075 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | test execution | 2013-11-18 08:00 | 2013-11-18 16:00 | 7h | Employee L | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | test preparation | 2013-10-10 08:00 | 2013-10-10 14:00 | 5h | Employee S | 375 | 0 | 0 | 0 | 375 |  | 0 | 0 | 375 | 5h | 0 | 0 | 0 | 375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | test preparation | 2013-10-10 08:00 | 2013-10-21 17:00 | 8d | Employee R | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 8d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | test preparation | 2013-10-10 08:00 | 2013-10-30 10:00 | 14d 2h | Employee T | 8550 | 0 | 0 | 0 | 8550 |  | 0 | 0 | 8550 | 14d 2h | 0 | 0 | 0 | 8550 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | test preparation | 2013-10-10 08:00 | 2013-10-14 15:00 | 2d 6h | Employee U | 1650 | 0 | 0 | 0 | 1650 |  | 0 | 0 | 1650 | 2d 6h | 0 | 0 | 0 | 1650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee V | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee W | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | bugfixing | 2013-12-02 08:00 | 2013-12-02 15:00 | 6h | Employee Q | 450 | 0 | 0 | 0 | 450 |  | 0 | 0 | 450 | 6h | 0 | 0 | 0 | 450 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | bugfixing | 2013-12-02 08:00 | 2013-12-09 14:00 | 5d 5h | Employee N | 3375 | 0 | 0 | 0 | 3375 |  | 0 | 0 | 3375 | 5d 5h | 0 | 0 | 0 | 3375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | bugfixing | 2013-12-02 08:00 | 2014-01-06 12:00 | 25d 4h | Employee E | 15300 | 0 | 0 | 0 | 15300 |  | 0 | 0 | 15300 | 25d 4h | 0 | 0 | 0 | 15300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | bugfixing | 2013-12-02 08:00 | 2013-12-02 12:00 | 4h | Employee X | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee L | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | bugfixing | 2013-12-02 08:00 | 2013-12-17 17:00 | 12d | Employee P | 7200 | 0 | 0 | 0 | 7200 |  | 0 | 0 | 7200 | 12d | 0 | 0 | 0 | 7200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | ict test completed | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | ondersteuning | 2013-09-17 08:00 | 2013-10-17 10:00 | 22d 2h |  |  | 0 |  |  | 17400 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
84 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-17 09:00 | 1h | Employee J | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-17 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-24 14:00 | 5d 5h | Employee G | 3375 | 0 | 0 | 0 | 3375 |  | 0 | 0 | 3375 | 5d 5h | 0 | 0 | 0 | 3375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-10-17 10:00 | 22d 2h | Employee D | 13350 | 0 | 0 | 0 | 13350 |  | 0 | 0 | 13350 | 22d 2h | 0 | 0 | 0 | 13350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | implementation | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | go live | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | post implementation | 2014-01-27 08:00 | 2014-02-05 12:00 | 7d 4h |  |  | 0 |  |  | 8400 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | post implementation - post go live support | 2014-01-27 08:00 | 2014-02-05 12:00 | 7d 4h | Employee E | 4500 | 0 | 0 | 0 | 4500 |  | 0 | 0 | 4500 | 7d 4h | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-29 11:00 | 2d 3h | Employee R | 1425 | 0 | 0 | 0 | 1425 |  | 0 | 0 | 1425 | 2d 3h | 0 | 0 | 0 | 1425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-28 09:00 | 1d 1h | Employee T | 675 | 0 | 0 | 0 | 675 |  | 0 | 0 | 675 | 1d 1h | 0 | 0 | 0 | 675 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-27 10:00 | 2h | Employee L | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-29 15:00 | 2d 6h | Employee D | 1650 | 0 | 0 | 0 | 1650 |  | 0 | 0 | 1650 | 2d 6h | 0 | 0 | 0 | 1650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2013-09-02 22:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Insurance Bundling System | 2013-04-19 08:00 | 2014-02-05 12:00 | 208d 4h |  |  | 0 |  |  | 281430 |  | 97d | [5 empty] | 25110 |  | 8.937% |  | 25152.0005 | 64230
31 | supporting tasks | 2013-07-16 08:00 | 2013-09-02 17:00 | 35d |  |  | 0 |  |  | 26190 |  | 36d | [5 empty] | 3870 |  | 14.36% |  | 3762 | 26190
1 | project management | 2013-07-16 08:00 | 2013-09-02 17:00 | 35d | Employee A | 25200 | 0 | 0 | 0 | 25200 | 2013-07-15 08:00 | 4d | 2880 | 4500 | 6d 2h | 0 | 0 | 2880 | 4500 | 11% | Started | 2772 | 25200 | 100 | 11.4286 | 11 | 100 | 11.4286 | 11
2 | project management | 2013-07-16 08:00 | 2013-07-17 11:00 | 1d 3h | Employee B | 990 | 0 | 0 | 0 | 990 | 2013-08-19 08:00 | 1d 3h | 990 | 0 | 0 | 0 | 0 | 990 | 0 | 100% | Finished | 990 | 990 | 100 | 100 | 100 | 100 | 100 | 100
30 | analysis | 2013-04-19 08:00 | 2013-09-27 17:00 | 116d |  |  | 0 |  |  | 38340 |  | 97d | [5 empty] | 21165 |  | 55.59% |  | 21315.0005 | 34215
3 | analysis - business analysis | 2013-07-01 08:00 | 2013-08-23 11:00 | 39d 3h | Employee D | 23625 | 0 | 0 | 0 | 23625 | 2013-07-01 08:00 | 22d 7h | 13725 | 9900 | 16d 4h | 0 | 0 | 13725 | 9900 | 58.1% | Started | 13725.0006 | 23625 | 100 | 58.0952 | 58.0952 | 100 | 58.0952 | 58.0952
4 | analysis - datamodel | 2013-09-09 08:00 | 2013-09-13 11:00 | 4d 3h | Employee D | 2625 | 0 | 0 | 0 | 2625 |  | 0 | 0 | 2625 | 4d 3h | 0 | 0 | 0 | 2625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | analysis - I/O services | 2013-09-23 08:00 | 2013-09-25 12:00 | 2d 4h | Employee D | 1500 | 0 | 0 | 0 | 1500 |  | 0 | 0 | 1500 | 2d 4h | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-22 10:00 | 1d 2h | Employee C | 750 | 0 | 0 | 0 | 750 | 2013-07-01 08:00 | 1d | 600 | 150 | 2h | 0 | 0 | 600 | 150 | 80% | Started | 600 | 750 | 100 | 80 | 80 | 100 | 80 | 80
7 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-30 10:00 | 7d 2h | Employee E | 4350 | 0 | 0 | 0 | 4350 | 2013-04-22 08:00 | 2d 5h | 1575 | 2775 | 4d 5h | 0 | 0 | 1575 | 2775 | 36.21% | Started | 1574.9999 | 4350 | 100 | 36.2069 | 36.2069 | 100 | 36.2069 | 36.2069
8 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-26 12:00 | 5d 4h | Employee F | 3300 | 0 | 0 | 0 | 3300 | 2013-04-19 08:00 | 5d 2h | 3150 | 0 | 0 | 0 | 0 | 3150 | 0 | 100% | Finished | 3300 | 3300 | 100 | 95.4545 | 100 | 100 | 95.4545 | 100
9 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 15:00 | 6h | Employee B | 540 | 0 | 0 | 0 | 540 | 2013-07-29 08:00 | 6h | 540 | 0 | 0 | 0 | 0 | 540 | 0 | 100% | Finished | 540 | 540 | 100 | 100 | 100 | 100 | 100 | 100
10 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2013-04-19 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 100 | 100
11 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 16:00 | 7h | Employee H | 525 | 0 | 0 | 0 | 525 | 2013-04-22 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
12 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 16:00 | 7h | Employee I | 525 | 0 | 0 | 0 | 525 | 2013-07-29 08:00 | 6h | 450 | 75 | 1h | 0 | 0 | 450 | 75 | 85.71% | Started | 450 | 525 | 100 | 85.7143 | 85.7143 | 100 | 85.7143 | 85.7143
13 | analysis validated | 2013-09-27 17:00 | 2013-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | design | 2013-04-19 08:00 | 2013-11-15 17:00 | 151d |  |  | 0 |  |  | 18600 |  | 11d | [5 empty] | 75 |  | 0.4032% |  | 75 | 3825
14 | BPA | 2013-09-16 08:00 | 2013-09-17 10:00 | 1d 2h | Employee J | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | CDM | 2013-10-14 08:00 | 2013-10-14 16:00 | 7h | Employee J | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | classic | 2013-08-21 08:00 | 2013-08-23 14:00 | 2d 5h | Employee K | 1575 | 0 | 0 | 0 | 1575 | 2013-08-19 08:00 | 1h | 75 | 1500 | 2d 4h | 0 | 0 | 75 | 1500 | 4.762% | Started | 75 | 1575 | 100 | 4.7619 | 4.7619 | 100 | 4.7619 | 4.7619
17 | classic | 2013-08-21 08:00 | 2013-08-26 10:00 | 3d 2h | Employee L | 1950 | 0 | 0 | 0 | 1950 |  | 0 | 0 | 1950 | 3d 2h | 0 | 0 | 0 | 1950 | 0% | Not Started | 0 | 1950 | 100 |  | 0 | 100 |  | 0
18 | SAD/interface design | 2013-10-21 08:00 | 2013-10-25 11:00 | 4d 3h | Employee L | 2625 | 0 | 0 | 0 | 2625 |  | 0 | 0 | 2625 | 4d 3h | 0 | 0 | 0 | 2625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | BPA | 2013-04-19 08:00 | 2013-04-19 09:00 | 1h | Employee J | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 75 | 100 |  | 0 | 100 |  | 0
20 | CDM | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Employee J | 225 | 0 | 0 | 0 | 225 |  | 0 | 0 | 225 | 3h | 0 | 0 | 0 | 225 | 0% | Not Started | 0 | 225 | 100 |  | 0 | 100 |  | 0
21 | get NB | 2013-09-30 08:00 | 2013-10-03 16:00 | 3d 7h | Employee M | 2325 | 0 | 0 | 0 | 2325 |  | 0 | 0 | 2325 | 3d 7h | 0 | 0 | 0 | 2325 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | PO - BPA | 2013-09-18 08:00 | 2013-09-18 16:00 | 7h | Employee J | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | PO - CDM | 2013-10-01 08:00 | 2013-10-01 14:00 | 5h | Employee J | 375 | 0 | 0 | 0 | 375 |  | 0 | 0 | 375 | 5h | 0 | 0 | 0 | 375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | quote - BPA | 2013-10-03 08:00 | 2013-10-04 09:00 | 1d 1h | Employee J | 675 | 0 | 0 | 0 | 675 |  | 0 | 0 | 675 | 1d 1h | 0 | 0 | 0 | 675 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | quote - CDM | 2013-10-14 08:00 | 2013-10-15 11:00 | 1d 3h | Employee J | 825 | 0 | 0 | 0 | 825 |  | 0 | 0 | 825 | 1d 3h | 0 | 0 | 0 | 825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | quote - NB | 2013-10-07 08:00 | 2013-10-07 16:00 | 7h | Employee M | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | web - user interface design | 2013-09-16 08:00 | 2013-09-25 09:00 | 7d 1h | Employee L | 4275 | 0 | 0 | 0 | 4275 |  | 0 | 0 | 4275 | 7d 1h | 0 | 0 | 0 | 4275 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | web - user interface integratie | 2013-11-12 08:00 | 2013-11-14 10:00 | 2d 2h | Employee L | 1350 | 0 | 0 | 0 | 1350 |  | 0 | 0 | 1350 | 2d 2h | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | design validated | 2013-11-15 17:00 | 2013-11-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | build | 2013-09-24 08:00 | 2013-12-16 17:00 | 60d |  |  | 0 |  |  | 81825 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | GP - classic | 2013-10-14 08:00 | 2013-10-29 10:00 | 11d 2h | Employee N | 6750 | 0 | 0 | 0 | 6750 |  | 0 | 0 | 6750 | 11d 2h | 0 | 0 | 0 | 6750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | GP - classic | 2013-10-14 08:00 | 2013-10-14 16:00 | 7h | Employee E | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | GP - ESB | 2013-11-04 08:00 | 2013-11-05 17:00 | 2d | Employee O | 1200 | 0 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 2d | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | GP - technical assembly test | 2013-11-18 08:00 | 2013-11-18 11:00 | 3h | Employee O | 225 | 0 | 0 | 0 | 225 |  | 0 | 0 | 225 | 3h | 0 | 0 | 0 | 225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | classic - arbeidsongeval | 2013-09-30 08:00 | 2013-09-30 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | classic - arbeidsongeval | 2013-09-30 08:00 | 2013-10-10 14:00 | 8d 5h | Employee P | 5175 | 0 | 0 | 0 | 5175 |  | 0 | 0 | 5175 | 8d 5h | 0 | 0 | 0 | 5175 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | classic - auto | 2013-10-07 08:00 | 2013-10-09 10:00 | 2d 2h | Employee E | 1350 | 0 | 0 | 0 | 1350 |  | 0 | 0 | 1350 | 2d 2h | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | classic - auto | 2013-10-07 08:00 | 2013-10-18 10:00 | 9d 2h | Employee P | 5550 | 0 | 0 | 0 | 5550 |  | 0 | 0 | 5550 | 9d 2h | 0 | 0 | 0 | 5550 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | classic - brand | 2013-10-28 08:00 | 2013-10-29 10:00 | 1d 2h | Employee E | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | classic - brand | 2013-10-28 08:00 | 2013-10-28 16:00 | 7h | Employee P | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | classic - cleansing data | 2013-11-04 08:00 | 2013-11-15 11:00 | 9d 3h | Employee N | 5625 | 0 | 0 | 0 | 5625 |  | 0 | 0 | 5625 | 9d 3h | 0 | 0 | 0 | 5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | classic - cleansing | 2013-11-04 08:00 | 2013-11-15 12:00 | 9d 4h | Employee E | 5700 | 0 | 0 | 0 | 5700 |  | 0 | 0 | 5700 | 9d 4h | 0 | 0 | 0 | 5700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | classic - cleansing voorbereiding | 2013-09-30 08:00 | 2013-10-02 16:00 | 2d 7h | Employee N | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | classic - cleansing voorbereiding | 2013-09-30 08:00 | 2013-10-04 14:00 | 4d 5h | Employee E | 2775 | 0 | 0 | 0 | 2775 |  | 0 | 0 | 2775 | 4d 5h | 0 | 0 | 0 | 2775 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | dashboard - BO | 2013-11-12 08:00 | 2013-11-12 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 |  | 0 | 0 | 450 | 6h | 0 | 0 | 0 | 450 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | dashboard - UI | 2013-11-25 08:00 | 2013-11-25 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | dashboard - UI | 2013-11-25 08:00 | 2013-12-16 15:00 | 15d 6h | Employee P | 9450 | 0 | 0 | 0 | 9450 |  | 0 | 0 | 9450 | 15d 6h | 0 | 0 | 0 | 9450 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | classic - BO leeg gezin | 2013-09-26 08:00 | 2013-09-26 16:00 | 7h | Employee N | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | classic - BO leeg gezin | 2013-09-26 08:00 | 2013-09-26 10:00 | 2h | Employee E | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | classic - BO | 2013-10-21 08:00 | 2013-11-04 11:00 | 10d 3h | Employee E | 6225 | 0 | 0 | 0 | 6225 |  | 0 | 0 | 6225 | 10d 3h | 0 | 0 | 0 | 6225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | classic - annuleren | 2013-11-25 08:00 | 2013-11-27 11:00 | 2d 3h | Employee E | 1425 | 0 | 0 | 0 | 1425 |  | 0 | 0 | 1425 | 2d 3h | 0 | 0 | 0 | 1425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | classic - voltooien | 2013-11-18 08:00 | 2013-11-20 11:00 | 2d 3h | Employee E | 1425 | 0 | 0 | 0 | 1425 |  | 0 | 0 | 1425 | 2d 3h | 0 | 0 | 0 | 1425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | classic - UI detail | 2013-09-25 08:00 | 2013-09-25 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 |  | 0 | 0 | 450 | 6h | 0 | 0 | 0 | 450 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | classic - UI | 2013-09-24 08:00 | 2013-09-26 09:00 | 2d 1h | Employee E | 1275 | 0 | 0 | 0 | 1275 |  | 0 | 0 | 1275 | 2d 1h | 0 | 0 | 0 | 1275 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | classic - inhoud | 2013-09-30 08:00 | 2013-10-08 15:00 | 6d 6h | Employee E | 4050 | 0 | 0 | 0 | 4050 |  | 0 | 0 | 4050 | 6d 6h | 0 | 0 | 0 | 4050 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | classic - leden | 2013-11-12 08:00 | 2013-11-12 17:00 | 1d | Employee P | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | classic - varia | 2013-10-22 08:00 | 2013-10-22 14:00 | 5h | Employee E | 375 | 0 | 0 | 0 | 375 |  | 0 | 0 | 375 | 5h | 0 | 0 | 0 | 375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | classic - varia | 2013-10-22 08:00 | 2013-10-29 14:00 | 5d 5h | Employee P | 3375 | 0 | 0 | 0 | 3375 |  | 0 | 0 | 3375 | 5d 5h | 0 | 0 | 0 | 3375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | get NB - ESB | 2013-11-18 08:00 | 2013-11-20 17:00 | 3d | Employee V | 1800 | 0 | 0 | 0 | 1800 |  | 0 | 0 | 1800 | 3d | 0 | 0 | 0 | 1800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | PO - classic | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d | Employee E | 3000 | 0 | 0 | 0 | 3000 |  | 0 | 0 | 3000 | 5d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | quote - ESB | 2013-11-18 08:00 | 2013-11-19 14:00 | 1d 5h | Employee O | 975 | 0 | 0 | 0 | 975 |  | 0 | 0 | 975 | 1d 5h | 0 | 0 | 0 | 975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | web | 2013-11-18 08:00 | 2013-11-19 17:00 | 2d | Employee H | 1200 | 0 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 2d | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | web | 2013-11-18 08:00 | 2013-12-02 17:00 | 11d | Employee Q | 6600 | 0 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 11d | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | build validated | 2013-12-16 17:00 | 2013-12-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | test ict | 2013-10-10 08:00 | 2014-01-24 17:00 | 77d |  |  | 0 |  |  | 90675 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
67 | test coordination | 2013-10-14 08:00 | 2013-10-25 09:00 | 9d 1h | Employee R | 5475 | 0 | 0 | 0 | 5475 |  | 0 | 0 | 5475 | 9d 1h | 0 | 0 | 0 | 5475 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | test execution | 2013-11-18 08:00 | 2013-12-13 12:00 | 19d 4h | Employee S | 11700 | 0 | 0 | 0 | 11700 |  | 0 | 0 | 11700 | 19d 4h | 0 | 0 | 0 | 11700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | test execution | 2013-11-18 08:00 | 2013-12-18 16:00 | 22d 7h | Employee R | 13725 | 0 | 0 | 0 | 13725 |  | 0 | 0 | 13725 | 22d 7h | 0 | 0 | 0 | 13725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | test execution | 2013-11-18 08:00 | 2013-12-16 09:00 | 20d 1h | Employee T | 12075 | 0 | 0 | 0 | 12075 |  | 0 | 0 | 12075 | 20d 1h | 0 | 0 | 0 | 12075 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | test execution | 2013-11-18 08:00 | 2013-11-18 16:00 | 7h | Employee L | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | test preparation | 2013-10-10 08:00 | 2013-10-10 14:00 | 5h | Employee S | 375 | 0 | 0 | 0 | 375 |  | 0 | 0 | 375 | 5h | 0 | 0 | 0 | 375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | test preparation | 2013-10-10 08:00 | 2013-10-21 17:00 | 8d | Employee R | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 8d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | test preparation | 2013-10-10 08:00 | 2013-10-30 10:00 | 14d 2h | Employee T | 8550 | 0 | 0 | 0 | 8550 |  | 0 | 0 | 8550 | 14d 2h | 0 | 0 | 0 | 8550 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | test preparation | 2013-10-10 08:00 | 2013-10-14 15:00 | 2d 6h | Employee U | 1650 | 0 | 0 | 0 | 1650 |  | 0 | 0 | 1650 | 2d 6h | 0 | 0 | 0 | 1650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee V | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee W | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | bugfixing | 2013-12-02 08:00 | 2013-12-02 15:00 | 6h | Employee Q | 450 | 0 | 0 | 0 | 450 |  | 0 | 0 | 450 | 6h | 0 | 0 | 0 | 450 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | bugfixing | 2013-12-02 08:00 | 2013-12-09 14:00 | 5d 5h | Employee N | 3375 | 0 | 0 | 0 | 3375 |  | 0 | 0 | 3375 | 5d 5h | 0 | 0 | 0 | 3375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | bugfixing | 2013-12-02 08:00 | 2014-01-06 12:00 | 25d 4h | Employee E | 15300 | 0 | 0 | 0 | 15300 |  | 0 | 0 | 15300 | 25d 4h | 0 | 0 | 0 | 15300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | bugfixing | 2013-12-02 08:00 | 2013-12-02 12:00 | 4h | Employee X | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee L | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | bugfixing | 2013-12-02 08:00 | 2013-12-17 17:00 | 12d | Employee P | 7200 | 0 | 0 | 0 | 7200 |  | 0 | 0 | 7200 | 12d | 0 | 0 | 0 | 7200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | ict test completed | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | ondersteuning | 2013-09-17 08:00 | 2013-10-17 10:00 | 22d 2h |  |  | 0 |  |  | 17400 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
84 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-17 09:00 | 1h | Employee J | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-17 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-24 14:00 | 5d 5h | Employee G | 3375 | 0 | 0 | 0 | 3375 |  | 0 | 0 | 3375 | 5d 5h | 0 | 0 | 0 | 3375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-10-17 10:00 | 22d 2h | Employee D | 13350 | 0 | 0 | 0 | 13350 |  | 0 | 0 | 13350 | 22d 2h | 0 | 0 | 0 | 13350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | implementation | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | go live | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | post implementation | 2014-01-27 08:00 | 2014-02-05 12:00 | 7d 4h |  |  | 0 |  |  | 8400 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | post implementation - post go live support | 2014-01-27 08:00 | 2014-02-05 12:00 | 7d 4h | Employee E | 4500 | 0 | 0 | 0 | 4500 |  | 0 | 0 | 4500 | 7d 4h | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-29 11:00 | 2d 3h | Employee R | 1425 | 0 | 0 | 0 | 1425 |  | 0 | 0 | 1425 | 2d 3h | 0 | 0 | 0 | 1425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-28 09:00 | 1d 1h | Employee T | 675 | 0 | 0 | 0 | 675 |  | 0 | 0 | 675 | 1d 1h | 0 | 0 | 0 | 675 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-27 10:00 | 2h | Employee L | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-29 15:00 | 2d 6h | Employee D | 1650 | 0 | 0 | 0 | 1650 |  | 0 | 0 | 1650 | 2d 6h | 0 | 0 | 0 | 1650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2013-11-04 22:00 |  | TP Name | Tracking 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Insurance Bundling System | 2013-04-19 08:00 | 2014-02-05 12:00 | 208d 4h |  |  | 0 |  |  | 281430 |  | 142d 6h | [5 empty] | 107580 |  | 38.57% |  | 108541.3398 | 166680
31 | supporting tasks | 2013-07-16 08:00 | 2013-09-02 17:00 | 35d |  |  | 0 |  |  | 26190 |  | 81d | [5 empty] | 7740 |  | 29.76% |  | 7794.0003 | 26190
1 | project management | 2013-07-16 08:00 | 2013-09-02 17:00 | 35d | Employee A | 25200 | 0 | 0 | 0 | 25200 | 2013-07-15 08:00 | 9d 3h | 6750 | 18450 | 25d 5h | 0 | 0 | 6750 | 18450 | 27% | Started | 6804.0003 | 25200 | 100 | 26.7857 | 27 | 100 | 26.7857 | 27
2 | project management | 2013-07-16 08:00 | 2013-07-17 11:00 | 1d 3h | Employee B | 990 | 0 | 0 | 0 | 990 | 2013-08-19 08:00 | 1d 3h | 990 | 0 | 0 | 0 | 0 | 990 | 0 | 100% | Finished | 990 | 990 | 100 | 100 | 100 | 100 | 100 | 100
30 | analysis | 2013-04-19 08:00 | 2013-09-27 17:00 | 116d |  |  | 0 |  |  | 38340 |  | 142d | [5 empty] | 36915 |  | 96.26% |  | 36904.5001 | 38340
3 | analysis - business analysis | 2013-07-01 08:00 | 2013-08-23 11:00 | 39d 3h | Employee D | 23625 | 0 | 0 | 0 | 23625 | 2013-07-01 08:00 | 39d 5h | 23775 | 0 | 0 | 0 | 0 | 23775 | 0 | 100% | Finished | 23625 | 23625 | 100 | 100.6349 | 100 | 100 | 100.6349 | 100
4 | analysis - datamodel | 2013-09-09 08:00 | 2013-09-13 11:00 | 4d 3h | Employee D | 2625 | 0 | 0 | 0 | 2625 | 2013-10-21 08:00 | 4d 3h | 2625 | 0 | 0 | 0 | 0 | 2625 | 0 | 100% | Finished | 2625 | 2625 | 100 | 100 | 100 | 100 | 100 | 100
5 | analysis - I/O services | 2013-09-23 08:00 | 2013-09-25 12:00 | 2d 4h | Employee D | 1500 | 0 | 0 | 0 | 1500 | 2013-10-28 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 100% | Finished | 1500 | 1500 | 100 | 110 | 100 | 100 | 110 | 100
6 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-22 10:00 | 1d 2h | Employee C | 750 | 0 | 0 | 0 | 750 | 2013-07-01 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
7 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-30 10:00 | 7d 2h | Employee E | 4350 | 0 | 0 | 0 | 4350 | 2013-04-22 08:00 | 4d 5h | 2775 | 1275 | 2d 1h | 0 | 0 | 2775 | 1275 | 67% | Started | 2914.5001 | 4350 | 100 | 63.7931 | 67 | 100 | 63.7931 | 67
8 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-26 12:00 | 5d 4h | Employee F | 3300 | 0 | 0 | 0 | 3300 | 2013-04-19 08:00 | 5d 2h | 3150 | 0 | 0 | 0 | 0 | 3150 | 0 | 100% | Finished | 3300 | 3300 | 100 | 95.4545 | 100 | 100 | 95.4545 | 100
9 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 15:00 | 6h | Employee B | 540 | 0 | 0 | 0 | 540 | 2013-07-29 08:00 | 6h | 540 | 0 | 0 | 0 | 0 | 540 | 0 | 100% | Finished | 540 | 540 | 100 | 100 | 100 | 100 | 100 | 100
10 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2013-04-19 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 100 | 100
11 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 16:00 | 7h | Employee H | 525 | 0 | 0 | 0 | 525 | 2013-04-22 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
12 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 16:00 | 7h | Employee I | 525 | 0 | 0 | 0 | 525 | 2013-07-29 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
13 | analysis validated | 2013-09-27 17:00 | 2013-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | design | 2013-04-19 08:00 | 2013-11-15 17:00 | 151d |  |  | 0 |  |  | 18600 |  | 56d | [5 empty] | 15675 |  | 82.89% |  | 15417.8573 | 17250
14 | BPA | 2013-09-16 08:00 | 2013-09-17 10:00 | 1d 2h | Employee J | 750 | 0 | 0 | 0 | 750 | 2013-09-16 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
15 | CDM | 2013-10-14 08:00 | 2013-10-14 16:00 | 7h | Employee J | 525 | 0 | 0 | 0 | 525 | 2013-10-07 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
16 | classic | 2013-08-21 08:00 | 2013-08-23 14:00 | 2d 5h | Employee K | 1575 | 0 | 0 | 0 | 1575 | 2013-08-19 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 100% | Finished | 1575 | 1575 | 100 | 104.7619 | 100 | 100 | 104.7619 | 100
17 | classic | 2013-08-21 08:00 | 2013-08-26 10:00 | 3d 2h | Employee L | 1950 | 0 | 0 | 0 | 1950 | 2013-10-07 08:00 | 3d 3h | 2025 | 0 | 0 | 0 | 0 | 2025 | 0 | 100% | Finished | 1950 | 1950 | 100 | 103.8462 | 100 | 100 | 103.8462 | 100
18 | SAD/interface design | 2013-10-21 08:00 | 2013-10-25 11:00 | 4d 3h | Employee L | 2625 | 0 | 0 | 0 | 2625 | 2013-10-07 08:00 | 4d 4h | 2700 | 0 | 0 | 0 | 0 | 2700 | 0 | 100% | Finished | 2625 | 2625 | 100 | 102.8571 | 100 | 100 | 102.8571 | 100
19 | BPA | 2013-04-19 08:00 | 2013-04-19 09:00 | 1h | Employee J | 75 | 0 | 0 | 0 | 75 | 2013-09-30 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
20 | CDM | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Employee J | 225 | 0 | 0 | 0 | 225 | 2013-09-30 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 225 | 225 | 100 | 100 | 100 | 100 | 100 | 100
21 | get NB | 2013-09-30 08:00 | 2013-10-03 16:00 | 3d 7h | Employee M | 2325 | 0 | 0 | 0 | 2325 | 2013-09-30 08:00 | 3d 7h | 2325 | 0 | 0 | 0 | 0 | 2325 | 0 | 100% | Finished | 2325 | 2325 | 100 | 100 | 100 | 100 | 100 | 100
22 | PO - BPA | 2013-09-18 08:00 | 2013-09-18 16:00 | 7h | Employee J | 525 | 0 | 0 | 0 | 525 | 2013-09-16 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
23 | PO - CDM | 2013-10-01 08:00 | 2013-10-01 14:00 | 5h | Employee J | 375 | 0 | 0 | 0 | 375 | 2013-09-30 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
24 | quote - BPA | 2013-10-03 08:00 | 2013-10-04 09:00 | 1d 1h | Employee J | 675 | 0 | 0 | 0 | 675 | 2013-09-30 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 675 | 675 | 100 | 100 | 100 | 100 | 100 | 100
25 | quote - CDM | 2013-10-14 08:00 | 2013-10-15 11:00 | 1d 3h | Employee J | 825 | 0 | 0 | 0 | 825 | 2013-10-07 08:00 | 1d 3h | 825 | 0 | 0 | 0 | 0 | 825 | 0 | 100% | Finished | 825 | 825 | 100 | 100 | 100 | 100 | 100 | 100
26 | quote - NB | 2013-10-07 08:00 | 2013-10-07 16:00 | 7h | Employee M | 525 | 0 | 0 | 0 | 525 | 2013-09-30 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 525 | 525 | 100 | 114.2857 | 100 | 100 | 114.2857 | 100
27 | web - user interface design | 2013-09-16 08:00 | 2013-09-25 09:00 | 7d 1h | Employee L | 4275 | 0 | 0 | 0 | 4275 | 2013-09-16 08:00 | 4d | 2400 | 1800 | 3d | 0 | 0 | 2400 | 1800 | 57.14% | Started | 2442.8573 | 4275 | 100 | 56.1404 | 57.1429 | 100 | 56.1404 | 57.1429
96 | web - user interface integratie | 2013-11-12 08:00 | 2013-11-14 10:00 | 2d 2h | Employee L | 1350 | 0 | 0 | 0 | 1350 |  | 0 | 0 | 1350 | 2d 2h | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | design validated | 2013-11-15 17:00 | 2013-11-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | build | 2013-09-24 08:00 | 2013-12-16 17:00 | 60d |  |  | 0 |  |  | 81825 |  | 31d 6h | [5 empty] | 37875 |  | 49.11% |  | 40186.2322 | 46650
32 | GP - classic | 2013-10-14 08:00 | 2013-10-29 10:00 | 11d 2h | Employee N | 6750 | 0 | 0 | 0 | 6750 | 2013-10-21 08:00 | 5d 4h | 3300 | 3300 | 5d 4h | 0 | 0 | 3300 | 3300 | 49% | Started | 3307.5001 | 6750 | 100 | 48.8889 | 49 | 100 | 48.8889 | 49
33 | GP - classic | 2013-10-14 08:00 | 2013-10-14 16:00 | 7h | Employee E | 525 | 0 | 0 | 0 | 525 | 2013-10-21 08:00 | 5h | 375 | 150 | 2h | 0 | 0 | 375 | 150 | 71.43% | Started | 375 | 525 | 100 | 71.4286 | 71.4286 | 100 | 71.4286 | 71.4286
34 | GP - ESB | 2013-11-04 08:00 | 2013-11-05 17:00 | 2d | Employee O | 1200 | 0 | 0 | 0 | 1200 | 2013-10-21 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1200 | 600 | 100 | 100 | 100 | 100 | 100 | 100
35 | GP - technical assembly test | 2013-11-18 08:00 | 2013-11-18 11:00 | 3h | Employee O | 225 | 0 | 0 | 0 | 225 | 2013-11-04 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 225 | 0 | 100 | 100 | 100 | 100 | 100 | 100
36 | classic - arbeidsongeval | 2013-09-30 08:00 | 2013-09-30 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2013-10-14 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
37 | classic - arbeidsongeval | 2013-09-30 08:00 | 2013-10-10 14:00 | 8d 5h | Employee P | 5175 | 0 | 0 | 0 | 5175 | 2013-09-30 08:00 | 8d 5h | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
38 | classic - auto | 2013-10-07 08:00 | 2013-10-09 10:00 | 2d 2h | Employee E | 1350 | 0 | 0 | 0 | 1350 | 2013-10-07 08:00 | 2d 2h | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 100% | Finished | 1350 | 1350 | 100 | 100 | 100 | 100 | 100 | 100
39 | classic - auto | 2013-10-07 08:00 | 2013-10-18 10:00 | 9d 2h | Employee P | 5550 | 0 | 0 | 0 | 5550 | 2013-10-07 08:00 | 9d | 5400 | 150 | 2h | 0 | 0 | 5400 | 150 | 97.3% | Started | 5400.0001 | 5550 | 100 | 97.2973 | 97.2973 | 100 | 97.2973 | 97.2973
40 | classic - brand | 2013-10-28 08:00 | 2013-10-29 10:00 | 1d 2h | Employee E | 750 | 0 | 0 | 0 | 750 | 2013-10-07 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
41 | classic - brand | 2013-10-28 08:00 | 2013-10-28 16:00 | 7h | Employee P | 525 | 0 | 0 | 0 | 525 | 2013-10-28 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
42 | classic - cleansing data | 2013-11-04 08:00 | 2013-11-15 11:00 | 9d 3h | Employee N | 5625 | 0 | 0 | 0 | 5625 | 2013-09-30 08:00 | 2d 2h | 1350 | 4050 | 6d 6h | 0 | 0 | 1350 | 4050 | 60% | Started | 3375.0001 | 600 | 100 | 24 | 60 | 100 | 24 | 60
43 | classic - cleansing | 2013-11-04 08:00 | 2013-11-15 12:00 | 9d 4h | Employee E | 5700 | 0 | 0 | 0 | 5700 |  | 0 | 0 | 5700 | 9d 4h | 0 | 0 | 0 | 5700 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
44 | classic - cleansing voorbereiding | 2013-09-30 08:00 | 2013-10-02 16:00 | 2d 7h | Employee N | 1725 | 0 | 0 | 0 | 1725 | 2013-10-07 08:00 | 6d 5h | 3975 | 75 | 1h | 0 | 0 | 3975 | 75 | 21% | Started | 362.25 | 1725 | 100 | 230.4348 | 21 | 100 | 230.4348 | 21
45 | classic - cleansing voorbereiding | 2013-09-30 08:00 | 2013-10-04 14:00 | 4d 5h | Employee E | 2775 | 0 | 0 | 0 | 2775 | 2013-10-07 08:00 | 2d 5h | 1575 | 1200 | 2d | 0 | 0 | 1575 | 1200 | 56.76% | Started | 1575.0001 | 2775 | 100 | 56.7568 | 56.7568 | 100 | 56.7568 | 56.7568
46 | dashboard - BO | 2013-11-12 08:00 | 2013-11-12 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 |  | 0 | 0 | 450 | 6h | 0 | 0 | 0 | 450 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | dashboard - UI | 2013-11-25 08:00 | 2013-11-25 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2013-11-04 08:00 | 1h | 75 | 225 | 3h | 0 | 0 | 75 | 225 | 25% | Started | 75 | 0 | 100 | 25 | 25 | 100 | 25 | 25
48 | dashboard - UI | 2013-11-25 08:00 | 2013-12-16 15:00 | 15d 6h | Employee P | 9450 | 0 | 0 | 0 | 9450 | 2013-11-04 08:00 | 4d 1h | 2475 | 8850 | 14d 6h | 0 | 0 | 2475 | 8850 | 21.85% | Started | 2065.2318 | 0 | 100 | 26.1905 | 21.8543 | 100 | 26.1905 | 21.8543
49 | classic - BO leeg gezin | 2013-09-26 08:00 | 2013-09-26 16:00 | 7h | Employee N | 525 | 0 | 0 | 0 | 525 | 2013-09-23 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
50 | classic - BO leeg gezin | 2013-09-26 08:00 | 2013-09-26 10:00 | 2h | Employee E | 150 | 0 | 0 | 0 | 150 | 2013-10-14 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
51 | classic - BO | 2013-10-21 08:00 | 2013-11-04 11:00 | 10d 3h | Employee E | 6225 | 0 | 0 | 0 | 6225 |  | 0 | 0 | 6225 | 10d 3h | 0 | 0 | 0 | 6225 | 0% | Not Started | 0 | 6225 | 100 |  | 0 | 100 |  | 0
52 | classic - annuleren | 2013-11-25 08:00 | 2013-11-27 11:00 | 2d 3h | Employee E | 1425 | 0 | 0 | 0 | 1425 | 2013-11-04 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1425 | 0 | 100 | 52.6316 | 100 | 100 | 52.6316 | 100
53 | classic - voltooien | 2013-11-18 08:00 | 2013-11-20 11:00 | 2d 3h | Employee E | 1425 | 0 | 0 | 0 | 1425 | 2013-11-04 08:00 | 6h | 450 | 975 | 1d 5h | 0 | 0 | 450 | 975 | 65% | Started | 926.25 | 0 | 100 | 31.5789 | 65 | 100 | 31.5789 | 65
54 | classic - UI detail | 2013-09-25 08:00 | 2013-09-25 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 | 2013-09-23 08:00 | 6h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 450 | 450 | 100 | 100 | 100 | 100 | 100 | 100
55 | classic - UI | 2013-09-24 08:00 | 2013-09-26 09:00 | 2d 1h | Employee E | 1275 | 0 | 0 | 0 | 1275 | 2013-09-23 08:00 | 2d 1h | 1275 | 0 | 0 | 0 | 0 | 1275 | 0 | 100% | Finished | 1275 | 1275 | 100 | 100 | 100 | 100 | 100 | 100
56 | classic - inhoud | 2013-09-30 08:00 | 2013-10-08 15:00 | 6d 6h | Employee E | 4050 | 0 | 0 | 0 | 4050 | 2013-09-30 08:00 | 4d 5h | 2775 | 0 | 0 | 0 | 0 | 2775 | 0 | 100% | Finished | 4050 | 4050 | 100 | 68.5185 | 100 | 100 | 68.5185 | 100
57 | classic - leden | 2013-11-12 08:00 | 2013-11-12 17:00 | 1d | Employee P | 600 | 0 | 0 | 0 | 600 | 2013-11-04 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 0 | 100 | 100 | 100 | 100 | 100 | 100
58 | classic - varia | 2013-10-22 08:00 | 2013-10-22 14:00 | 5h | Employee E | 375 | 0 | 0 | 0 | 375 | 2013-10-14 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
59 | classic - varia | 2013-10-22 08:00 | 2013-10-29 14:00 | 5d 5h | Employee P | 3375 | 0 | 0 | 0 | 3375 | 2013-10-14 08:00 | 2d 3h | 1425 | 0 | 0 | 0 | 0 | 1425 | 0 | 100% | Finished | 3375 | 3375 | 100 | 42.2222 | 100 | 100 | 42.2222 | 100
61 | get NB - ESB | 2013-11-18 08:00 | 2013-11-20 17:00 | 3d | Employee V | 1800 | 0 | 0 | 0 | 1800 |  | 0 | 0 | 1800 | 3d | 0 | 0 | 0 | 1800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | PO - classic | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d | Employee E | 3000 | 0 | 0 | 0 | 3000 |  | 0 | 0 | 3000 | 5d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 3000 | 100 |  | 0 | 100 |  | 0
63 | quote - ESB | 2013-11-18 08:00 | 2013-11-19 14:00 | 1d 5h | Employee O | 975 | 0 | 0 | 0 | 975 | 2013-11-04 08:00 | 1d 6h | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 100% | Finished | 975 | 0 | 100 | 107.6923 | 100 | 100 | 107.6923 | 100
64 | web | 2013-11-18 08:00 | 2013-11-19 17:00 | 2d | Employee H | 1200 | 0 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 2d | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | web | 2013-11-18 08:00 | 2013-12-02 17:00 | 11d | Employee Q | 6600 | 0 | 0 | 0 | 6600 |  | 0 | 0 | 6600 | 11d | 0 | 0 | 0 | 6600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | build validated | 2013-12-16 17:00 | 2013-12-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | test ict | 2013-10-10 08:00 | 2014-01-24 17:00 | 77d |  |  | 0 |  |  | 90675 |  | 21d | [5 empty] | 7575 |  | 7.499% |  | 6799.5001 | 20850
67 | test coordination | 2013-10-14 08:00 | 2013-10-25 09:00 | 9d 1h | Employee R | 5475 | 0 | 0 | 0 | 5475 | 2013-10-14 08:00 | 1d 5h | 975 | 450 | 6h | 0 | 0 | 975 | 450 | 18% | Started | 985.5 | 5475 | 100 | 17.8082 | 18 | 100 | 17.8082 | 18
68 | test execution | 2013-11-18 08:00 | 2013-12-13 12:00 | 19d 4h | Employee S | 11700 | 0 | 0 | 0 | 11700 |  | 0 | 0 | 11700 | 19d 4h | 0 | 0 | 0 | 11700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | test execution | 2013-11-18 08:00 | 2013-12-18 16:00 | 22d 7h | Employee R | 13725 | 0 | 0 | 0 | 13725 |  | 0 | 0 | 13725 | 22d 7h | 0 | 0 | 0 | 13725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | test execution | 2013-11-18 08:00 | 2013-12-16 09:00 | 20d 1h | Employee T | 12075 | 0 | 0 | 0 | 12075 |  | 0 | 0 | 12075 | 20d 1h | 0 | 0 | 0 | 12075 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | test execution | 2013-11-18 08:00 | 2013-11-18 16:00 | 7h | Employee L | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | test preparation | 2013-10-10 08:00 | 2013-10-10 14:00 | 5h | Employee S | 375 | 0 | 0 | 0 | 375 |  | 0 | 0 | 375 | 5h | 0 | 0 | 0 | 375 | 0% | Not Started | 0 | 375 | 100 |  | 0 | 100 |  | 0
73 | test preparation | 2013-10-10 08:00 | 2013-10-21 17:00 | 8d | Employee R | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 8d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 4800 | 100 |  | 0 | 100 |  | 0
74 | test preparation | 2013-10-10 08:00 | 2013-10-30 10:00 | 14d 2h | Employee T | 8550 | 0 | 0 | 0 | 8550 | 2013-10-07 08:00 | 11d | 6600 | 1800 | 3d | 0 | 0 | 6600 | 1800 | 68% | Started | 5814.0001 | 8550 | 100 | 77.193 | 68 | 100 | 77.193 | 68
75 | test preparation | 2013-10-10 08:00 | 2013-10-14 15:00 | 2d 6h | Employee U | 1650 | 0 | 0 | 0 | 1650 |  | 0 | 0 | 1650 | 2d 6h | 0 | 0 | 0 | 1650 | 0% | Not Started | 0 | 1650 | 100 |  | 0 | 100 |  | 0
76 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee V | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee W | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | bugfixing | 2013-12-02 08:00 | 2013-12-02 15:00 | 6h | Employee Q | 450 | 0 | 0 | 0 | 450 |  | 0 | 0 | 450 | 6h | 0 | 0 | 0 | 450 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | bugfixing | 2013-12-02 08:00 | 2013-12-09 14:00 | 5d 5h | Employee N | 3375 | 0 | 0 | 0 | 3375 |  | 0 | 0 | 3375 | 5d 5h | 0 | 0 | 0 | 3375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | bugfixing | 2013-12-02 08:00 | 2014-01-06 12:00 | 25d 4h | Employee E | 15300 | 0 | 0 | 0 | 15300 |  | 0 | 0 | 15300 | 25d 4h | 0 | 0 | 0 | 15300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | bugfixing | 2013-12-02 08:00 | 2013-12-02 12:00 | 4h | Employee X | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee L | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | bugfixing | 2013-12-02 08:00 | 2013-12-17 17:00 | 12d | Employee P | 7200 | 0 | 0 | 0 | 7200 |  | 0 | 0 | 7200 | 12d | 0 | 0 | 0 | 7200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | ict test completed | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | ondersteuning | 2013-09-17 08:00 | 2013-10-17 10:00 | 22d 2h |  |  | 0 |  |  | 17400 |  | 36d | [5 empty] | 1800 |  | 8.272% |  | 1439.25 | 17400
84 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-17 09:00 | 1h | Employee J | 75 | 0 | 0 | 0 | 75 | 2013-09-16 08:00 | 4h | 300 | 225 | 3h | 0 | 0 | 300 | 225 | 51% | Started | 38.25 | 75 | 100 | 400 | 51 | 100 | 400 | 51
85 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-17 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
86 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-24 14:00 | 5d 5h | Employee G | 3375 | 0 | 0 | 0 | 3375 | 2013-11-04 08:00 | 1d | 600 | 2775 | 4d 5h | 0 | 0 | 600 | 2775 | 17.78% | Started | 600 | 3375 | 100 | 17.7778 | 17.7778 | 100 | 17.7778 | 17.7778
87 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-10-17 10:00 | 22d 2h | Employee D | 13350 | 0 | 0 | 0 | 13350 | 2013-11-04 08:00 | 1d 4h | 900 | 12300 | 20d 4h | 0 | 0 | 900 | 12300 | 6% | Started | 801 | 13350 | 100 | 6.7416 | 6 | 100 | 6.7416 | 6
100 | implementation | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | go live | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | post implementation | 2014-01-27 08:00 | 2014-02-05 12:00 | 7d 4h |  |  | 0 |  |  | 8400 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | post implementation - post go live support | 2014-01-27 08:00 | 2014-02-05 12:00 | 7d 4h | Employee E | 4500 | 0 | 0 | 0 | 4500 |  | 0 | 0 | 4500 | 7d 4h | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-29 11:00 | 2d 3h | Employee R | 1425 | 0 | 0 | 0 | 1425 |  | 0 | 0 | 1425 | 2d 3h | 0 | 0 | 0 | 1425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-28 09:00 | 1d 1h | Employee T | 675 | 0 | 0 | 0 | 675 |  | 0 | 0 | 675 | 1d 1h | 0 | 0 | 0 | 675 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-27 10:00 | 2h | Employee L | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-29 15:00 | 2d 6h | Employee D | 1650 | 0 | 0 | 0 | 1650 |  | 0 | 0 | 1650 | 2d 6h | 0 | 0 | 0 | 1650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2014-01-07 09:00 |  | TP Name | Tracking 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Insurance Bundling System | 2013-04-19 08:00 | 2014-02-05 12:00 | 208d 4h |  |  | 0 |  |  | 281430 |  | 187d 1h | [5 empty] | 226785 |  | 78.3% |  | 220359.4996 | 273030
31 | supporting tasks | 2013-07-16 08:00 | 2013-09-02 17:00 | 35d |  |  | 0 |  |  | 26190 |  | 126d 1h | [5 empty] | 19170 |  | 72.95% |  | 19105.3028 | 26190
1 | project management | 2013-07-16 08:00 | 2013-09-02 17:00 | 35d | Employee A | 25200 | 0 | 0 | 0 | 25200 | 2013-07-15 08:00 | 25d 2h | 18180 | 7110 | 9d 7h | 0 | 0 | 18180 | 7110 | 71.89% | Started | 18115.3028 | 25200 | 100 | 72.1429 | 71.8861 | 100 | 72.1429 | 71.8861
2 | project management | 2013-07-16 08:00 | 2013-07-17 11:00 | 1d 3h | Employee B | 990 | 0 | 0 | 0 | 990 | 2013-08-19 08:00 | 1d 3h | 990 | 0 | 0 | 0 | 0 | 990 | 0 | 100% | Finished | 990 | 990 | 100 | 100 | 100 | 100 | 100 | 100
30 | analysis | 2013-04-19 08:00 | 2013-09-27 17:00 | 116d |  |  | 0 |  |  | 38340 |  | 187d 1h | [5 empty] | 36915 |  | 96.26% |  | 36904.5001 | 38340
3 | analysis - business analysis | 2013-07-01 08:00 | 2013-08-23 11:00 | 39d 3h | Employee D | 23625 | 0 | 0 | 0 | 23625 | 2013-07-01 08:00 | 39d 5h | 23775 | 0 | 0 | 0 | 0 | 23775 | 0 | 100% | Finished | 23625 | 23625 | 100 | 100.6349 | 100 | 100 | 100.6349 | 100
4 | analysis - datamodel | 2013-09-09 08:00 | 2013-09-13 11:00 | 4d 3h | Employee D | 2625 | 0 | 0 | 0 | 2625 | 2013-10-21 08:00 | 4d 3h | 2625 | 0 | 0 | 0 | 0 | 2625 | 0 | 100% | Finished | 2625 | 2625 | 100 | 100 | 100 | 100 | 100 | 100
5 | analysis - I/O services | 2013-09-23 08:00 | 2013-09-25 12:00 | 2d 4h | Employee D | 1500 | 0 | 0 | 0 | 1500 | 2013-10-28 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 100% | Finished | 1500 | 1500 | 100 | 110 | 100 | 100 | 110 | 100
6 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-22 10:00 | 1d 2h | Employee C | 750 | 0 | 0 | 0 | 750 | 2013-07-01 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
7 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-30 10:00 | 7d 2h | Employee E | 4350 | 0 | 0 | 0 | 4350 | 2013-04-22 08:00 | 4d 5h | 2775 | 1275 | 2d 1h | 0 | 0 | 2775 | 1275 | 67% | Started | 2914.5001 | 4350 | 100 | 63.7931 | 67 | 100 | 63.7931 | 67
8 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-26 12:00 | 5d 4h | Employee F | 3300 | 0 | 0 | 0 | 3300 | 2013-04-19 08:00 | 5d 2h | 3150 | 0 | 0 | 0 | 0 | 3150 | 0 | 100% | Finished | 3300 | 3300 | 100 | 95.4545 | 100 | 100 | 95.4545 | 100
9 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 15:00 | 6h | Employee B | 540 | 0 | 0 | 0 | 540 | 2013-07-29 08:00 | 6h | 540 | 0 | 0 | 0 | 0 | 540 | 0 | 100% | Finished | 540 | 540 | 100 | 100 | 100 | 100 | 100 | 100
10 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2013-04-19 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 100 | 100
11 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 16:00 | 7h | Employee H | 525 | 0 | 0 | 0 | 525 | 2013-04-22 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
12 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 16:00 | 7h | Employee I | 525 | 0 | 0 | 0 | 525 | 2013-07-29 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
13 | analysis validated | 2013-09-27 17:00 | 2013-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-11-05 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
29 | design | 2013-04-19 08:00 | 2013-11-15 17:00 | 151d |  |  | 0 |  |  | 18600 |  | 68d 7h | [5 empty] | 18900 |  | 100% |  | 18600 | 18600
14 | BPA | 2013-09-16 08:00 | 2013-09-17 10:00 | 1d 2h | Employee J | 750 | 0 | 0 | 0 | 750 | 2013-09-16 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
15 | CDM | 2013-10-14 08:00 | 2013-10-14 16:00 | 7h | Employee J | 525 | 0 | 0 | 0 | 525 | 2013-10-07 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
16 | classic | 2013-08-21 08:00 | 2013-08-23 14:00 | 2d 5h | Employee K | 1575 | 0 | 0 | 0 | 1575 | 2013-08-19 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 100% | Finished | 1575 | 1575 | 100 | 104.7619 | 100 | 100 | 104.7619 | 100
17 | classic | 2013-08-21 08:00 | 2013-08-26 10:00 | 3d 2h | Employee L | 1950 | 0 | 0 | 0 | 1950 | 2013-10-07 08:00 | 3d 3h | 2025 | 0 | 0 | 0 | 0 | 2025 | 0 | 100% | Finished | 1950 | 1950 | 100 | 103.8462 | 100 | 100 | 103.8462 | 100
18 | SAD/interface design | 2013-10-21 08:00 | 2013-10-25 11:00 | 4d 3h | Employee L | 2625 | 0 | 0 | 0 | 2625 | 2013-10-07 08:00 | 4d 4h | 2700 | 0 | 0 | 0 | 0 | 2700 | 0 | 100% | Finished | 2625 | 2625 | 100 | 102.8571 | 100 | 100 | 102.8571 | 100
19 | BPA | 2013-04-19 08:00 | 2013-04-19 09:00 | 1h | Employee J | 75 | 0 | 0 | 0 | 75 | 2013-09-30 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
20 | CDM | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Employee J | 225 | 0 | 0 | 0 | 225 | 2013-09-30 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 225 | 225 | 100 | 100 | 100 | 100 | 100 | 100
21 | get NB | 2013-09-30 08:00 | 2013-10-03 16:00 | 3d 7h | Employee M | 2325 | 0 | 0 | 0 | 2325 | 2013-09-30 08:00 | 3d 7h | 2325 | 0 | 0 | 0 | 0 | 2325 | 0 | 100% | Finished | 2325 | 2325 | 100 | 100 | 100 | 100 | 100 | 100
22 | PO - BPA | 2013-09-18 08:00 | 2013-09-18 16:00 | 7h | Employee J | 525 | 0 | 0 | 0 | 525 | 2013-09-16 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
23 | PO - CDM | 2013-10-01 08:00 | 2013-10-01 14:00 | 5h | Employee J | 375 | 0 | 0 | 0 | 375 | 2013-09-30 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
24 | quote - BPA | 2013-10-03 08:00 | 2013-10-04 09:00 | 1d 1h | Employee J | 675 | 0 | 0 | 0 | 675 | 2013-09-30 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 675 | 675 | 100 | 100 | 100 | 100 | 100 | 100
25 | quote - CDM | 2013-10-14 08:00 | 2013-10-15 11:00 | 1d 3h | Employee J | 825 | 0 | 0 | 0 | 825 | 2013-10-07 08:00 | 1d 3h | 825 | 0 | 0 | 0 | 0 | 825 | 0 | 100% | Finished | 825 | 825 | 100 | 100 | 100 | 100 | 100 | 100
26 | quote - NB | 2013-10-07 08:00 | 2013-10-07 16:00 | 7h | Employee M | 525 | 0 | 0 | 0 | 525 | 2013-09-30 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 525 | 525 | 100 | 114.2857 | 100 | 100 | 114.2857 | 100
27 | web - user interface design | 2013-09-16 08:00 | 2013-09-25 09:00 | 7d 1h | Employee L | 4275 | 0 | 0 | 0 | 4275 | 2013-09-16 08:00 | 7d 1h | 4275 | 0 | 0 | 0 | 0 | 4275 | 0 | 100% | Finished | 4275 | 4275 | 100 | 100 | 100 | 100 | 100 | 100
96 | web - user interface integratie | 2013-11-12 08:00 | 2013-11-14 10:00 | 2d 2h | Employee L | 1350 | 0 | 0 | 0 | 1350 | 2013-11-18 08:00 | 2d 2h | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 100% | Finished | 1350 | 1350 | 100 | 100 | 100 | 100 | 100 | 100
28 | design validated | 2013-11-15 17:00 | 2013-11-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-11-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | build | 2013-09-24 08:00 | 2013-12-16 17:00 | 60d |  |  | 0 |  |  | 81825 |  | 76d 1h | [5 empty] | 81975 |  | 93.6% |  | 76592.2501 | 81825
32 | GP - classic | 2013-10-14 08:00 | 2013-10-29 10:00 | 11d 2h | Employee N | 6750 | 0 | 0 | 0 | 6750 | 2013-10-21 08:00 | 11d 2h | 6750 | 0 | 0 | 0 | 0 | 6750 | 0 | 100% | Finished | 6750 | 6750 | 100 | 100 | 100 | 100 | 100 | 100
33 | GP - classic | 2013-10-14 08:00 | 2013-10-14 16:00 | 7h | Employee E | 525 | 0 | 0 | 0 | 525 | 2013-10-21 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
34 | GP - ESB | 2013-11-04 08:00 | 2013-11-05 17:00 | 2d | Employee O | 1200 | 0 | 0 | 0 | 1200 | 2013-10-21 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1200 | 1200 | 100 | 100 | 100 | 100 | 100 | 100
35 | GP - technical assembly test | 2013-11-18 08:00 | 2013-11-18 11:00 | 3h | Employee O | 225 | 0 | 0 | 0 | 225 | 2013-11-04 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 225 | 225 | 100 | 100 | 100 | 100 | 100 | 100
36 | classic - arbeidsongeval | 2013-09-30 08:00 | 2013-09-30 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2013-10-14 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
37 | classic - arbeidsongeval | 2013-09-30 08:00 | 2013-10-10 14:00 | 8d 5h | Employee P | 5175 | 0 | 0 | 0 | 5175 | 2013-09-30 08:00 | 8d 5h | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
38 | classic - auto | 2013-10-07 08:00 | 2013-10-09 10:00 | 2d 2h | Employee E | 1350 | 0 | 0 | 0 | 1350 | 2013-10-07 08:00 | 2d 2h | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 100% | Finished | 1350 | 1350 | 100 | 100 | 100 | 100 | 100 | 100
39 | classic - auto | 2013-10-07 08:00 | 2013-10-18 10:00 | 9d 2h | Employee P | 5550 | 0 | 0 | 0 | 5550 | 2013-10-07 08:00 | 9d 2h | 5550 | 0 | 0 | 0 | 0 | 5550 | 0 | 100% | Finished | 5550 | 5550 | 100 | 100 | 100 | 100 | 100 | 100
40 | classic - brand | 2013-10-28 08:00 | 2013-10-29 10:00 | 1d 2h | Employee E | 750 | 0 | 0 | 0 | 750 | 2013-10-07 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
41 | classic - brand | 2013-10-28 08:00 | 2013-10-28 16:00 | 7h | Employee P | 525 | 0 | 0 | 0 | 525 | 2013-10-28 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
42 | classic - cleansing data | 2013-11-04 08:00 | 2013-11-15 11:00 | 9d 3h | Employee N | 5625 | 0 | 0 | 0 | 5625 | 2013-09-30 08:00 | 2d 2h | 1350 | 4050 | 6d 6h | 0 | 0 | 1350 | 4050 | 60% | Started | 3375.0001 | 5625 | 100 | 24 | 60 | 100 | 24 | 60
43 | classic - cleansing | 2013-11-04 08:00 | 2013-11-15 12:00 | 9d 4h | Employee E | 5700 | 0 | 0 | 0 | 5700 | 2013-11-18 08:00 | 4d 7h | 2925 | 2475 | 4d 1h | 0 | 0 | 2925 | 2475 | 51% | Started | 2906.9999 | 5700 | 100 | 51.3158 | 51 | 100 | 51.3158 | 51
44 | classic - cleansing voorbereiding | 2013-09-30 08:00 | 2013-10-02 16:00 | 2d 7h | Employee N | 1725 | 0 | 0 | 0 | 1725 | 2013-10-07 08:00 | 27d 4h | 16500 | 75 | 1h | 0 | 0 | 16500 | 75 | 89% | Started | 1535.25 | 1725 | 100 | 956.5217 | 89 | 100 | 956.5217 | 89
45 | classic - cleansing voorbereiding | 2013-09-30 08:00 | 2013-10-04 14:00 | 4d 5h | Employee E | 2775 | 0 | 0 | 0 | 2775 | 2013-10-07 08:00 | 4d 5h | 2775 | 0 | 0 | 0 | 0 | 2775 | 0 | 100% | Finished | 2775 | 2775 | 100 | 100 | 100 | 100 | 100 | 100
46 | dashboard - BO | 2013-11-12 08:00 | 2013-11-12 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 | 2013-11-11 08:00 | 6h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 450 | 450 | 100 | 100 | 100 | 100 | 100 | 100
47 | dashboard - UI | 2013-11-25 08:00 | 2013-11-25 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2013-11-04 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
48 | dashboard - UI | 2013-11-25 08:00 | 2013-12-16 15:00 | 15d 6h | Employee P | 9450 | 0 | 0 | 0 | 9450 | 2013-11-04 08:00 | 15d 7h | 9525 | 0 | 0 | 0 | 0 | 9525 | 0 | 100% | Finished | 9450 | 9450 | 100 | 100.7937 | 100 | 100 | 100.7937 | 100
49 | classic - BO leeg gezin | 2013-09-26 08:00 | 2013-09-26 16:00 | 7h | Employee N | 525 | 0 | 0 | 0 | 525 | 2013-09-23 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
50 | classic - BO leeg gezin | 2013-09-26 08:00 | 2013-09-26 10:00 | 2h | Employee E | 150 | 0 | 0 | 0 | 150 | 2013-10-14 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
51 | classic - BO | 2013-10-21 08:00 | 2013-11-04 11:00 | 10d 3h | Employee E | 6225 | 0 | 0 | 0 | 6225 | 2013-11-11 08:00 | 4d 7h | 2925 | 0 | 0 | 0 | 0 | 2925 | 0 | 100% | Finished | 6225 | 6225 | 100 | 46.988 | 100 | 100 | 46.988 | 100
52 | classic - annuleren | 2013-11-25 08:00 | 2013-11-27 11:00 | 2d 3h | Employee E | 1425 | 0 | 0 | 0 | 1425 | 2013-11-04 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1425 | 1425 | 100 | 52.6316 | 100 | 100 | 52.6316 | 100
53 | classic - voltooien | 2013-11-18 08:00 | 2013-11-20 11:00 | 2d 3h | Employee E | 1425 | 0 | 0 | 0 | 1425 | 2013-11-04 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 1425 | 1425 | 100 | 47.3684 | 100 | 100 | 47.3684 | 100
54 | classic - UI detail | 2013-09-25 08:00 | 2013-09-25 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 | 2013-09-23 08:00 | 6h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 450 | 450 | 100 | 100 | 100 | 100 | 100 | 100
55 | classic - UI | 2013-09-24 08:00 | 2013-09-26 09:00 | 2d 1h | Employee E | 1275 | 0 | 0 | 0 | 1275 | 2013-09-23 08:00 | 2d 1h | 1275 | 0 | 0 | 0 | 0 | 1275 | 0 | 100% | Finished | 1275 | 1275 | 100 | 100 | 100 | 100 | 100 | 100
56 | classic - inhoud | 2013-09-30 08:00 | 2013-10-08 15:00 | 6d 6h | Employee E | 4050 | 0 | 0 | 0 | 4050 | 2013-09-30 08:00 | 4d 5h | 2775 | 0 | 0 | 0 | 0 | 2775 | 0 | 100% | Finished | 4050 | 4050 | 100 | 68.5185 | 100 | 100 | 68.5185 | 100
57 | classic - leden | 2013-11-12 08:00 | 2013-11-12 17:00 | 1d | Employee P | 600 | 0 | 0 | 0 | 600 | 2013-11-04 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 100 | 100
58 | classic - varia | 2013-10-22 08:00 | 2013-10-22 14:00 | 5h | Employee E | 375 | 0 | 0 | 0 | 375 | 2013-10-14 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
59 | classic - varia | 2013-10-22 08:00 | 2013-10-29 14:00 | 5d 5h | Employee P | 3375 | 0 | 0 | 0 | 3375 | 2013-10-14 08:00 | 2d 3h | 1425 | 0 | 0 | 0 | 0 | 1425 | 0 | 100% | Finished | 3375 | 3375 | 100 | 42.2222 | 100 | 100 | 42.2222 | 100
61 | get NB - ESB | 2013-11-18 08:00 | 2013-11-20 17:00 | 3d | Employee V | 1800 | 0 | 0 | 0 | 1800 | 2013-11-18 08:00 | 3d | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 100% | Finished | 1800 | 1800 | 100 | 100 | 100 | 100 | 100 | 100
62 | PO - classic | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d | Employee E | 3000 | 0 | 0 | 0 | 3000 | 2013-11-18 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
63 | quote - ESB | 2013-11-18 08:00 | 2013-11-19 14:00 | 1d 5h | Employee O | 975 | 0 | 0 | 0 | 975 | 2013-11-04 08:00 | 1d 6h | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 100% | Finished | 975 | 975 | 100 | 107.6923 | 100 | 100 | 107.6923 | 100
64 | web | 2013-11-18 08:00 | 2013-11-19 17:00 | 2d | Employee H | 1200 | 0 | 0 | 0 | 1200 | 2013-11-18 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1200 | 1200 | 100 | 100 | 100 | 100 | 100 | 100
97 | web | 2013-11-18 08:00 | 2013-12-02 17:00 | 11d | Employee Q | 6600 | 0 | 0 | 0 | 6600 | 2013-11-11 08:00 | 11d 3h | 6825 | 0 | 0 | 0 | 0 | 6825 | 0 | 100% | Finished | 6600 | 6600 | 100 | 103.4091 | 100 | 100 | 103.4091 | 100
65 | build validated | 2013-12-16 17:00 | 2013-12-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-12-16 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
93 | test ict | 2013-10-10 08:00 | 2014-01-24 17:00 | 77d |  |  | 0 |  |  | 90675 |  | 66d 1h | [5 empty] | 59250 |  | 65.13% |  | 59056.1532 | 90675
67 | test coordination | 2013-10-14 08:00 | 2013-10-25 09:00 | 9d 1h | Employee R | 5475 | 0 | 0 | 0 | 5475 | 2013-10-14 08:00 | 6d 2h | 3750 | 75 | 1h | 0 | 0 | 3750 | 75 | 68% | Started | 3723 | 5475 | 100 | 68.4932 | 68 | 100 | 68.4932 | 68
68 | test execution | 2013-11-18 08:00 | 2013-12-13 12:00 | 19d 4h | Employee S | 11700 | 0 | 0 | 0 | 11700 | 2013-12-23 08:00 | 3d 3h | 2025 | 1275 | 2d 1h | 0 | 0 | 2025 | 1275 | 75% | Started | 8775 | 11700 | 100 | 17.3077 | 75 | 100 | 17.3077 | 75
69 | test execution | 2013-11-18 08:00 | 2013-12-18 16:00 | 22d 7h | Employee R | 13725 | 0 | 0 | 0 | 13725 | 2013-12-02 08:00 | 15d 7h | 9525 | 825 | 1d 3h | 0 | 0 | 9525 | 825 | 51% | Started | 6999.7499 | 13725 | 100 | 69.3989 | 51 | 100 | 69.3989 | 51
70 | test execution | 2013-11-18 08:00 | 2013-12-16 09:00 | 20d 1h | Employee T | 12075 | 0 | 0 | 0 | 12075 | 2013-11-25 08:00 | 18d 2h | 10950 | 75 | 1h | 0 | 0 | 10950 | 75 | 60% | Started | 7245.0003 | 12075 | 100 | 90.6832 | 60 | 100 | 90.6832 | 60
71 | test execution | 2013-11-18 08:00 | 2013-11-18 16:00 | 7h | Employee L | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 525 | 100 |  | 0 | 100 |  | 0
72 | test preparation | 2013-10-10 08:00 | 2013-10-10 14:00 | 5h | Employee S | 375 | 0 | 0 | 0 | 375 | 2013-11-18 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
73 | test preparation | 2013-10-10 08:00 | 2013-10-21 17:00 | 8d | Employee R | 4800 | 0 | 0 | 0 | 4800 | 2013-11-11 08:00 | 9d 7h | 5925 | 0 | 0 | 0 | 0 | 5925 | 0 | 100% | Finished | 4800 | 4800 | 100 | 123.4375 | 100 | 100 | 123.4375 | 100
74 | test preparation | 2013-10-10 08:00 | 2013-10-30 10:00 | 14d 2h | Employee T | 8550 | 0 | 0 | 0 | 8550 | 2013-10-07 08:00 | 16d 1h | 9675 | 0 | 0 | 0 | 0 | 9675 | 0 | 100% | Finished | 8550 | 8550 | 100 | 113.1579 | 100 | 100 | 113.1579 | 100
75 | test preparation | 2013-10-10 08:00 | 2013-10-14 15:00 | 2d 6h | Employee U | 1650 | 0 | 0 | 0 | 1650 |  | 0 | 0 | 1650 | 2d 6h | 0 | 0 | 0 | 1650 | 0% | Not Started | 0 | 1650 | 100 |  | 0 | 100 |  | 0
76 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee V | 1725 | 0 | 0 | 0 | 1725 | 2013-12-23 08:00 | 1d 6h | 1050 | 75 | 1h | 0 | 0 | 1050 | 75 | 54% | Started | 931.5 | 1725 | 100 | 60.8696 | 54 | 100 | 60.8696 | 54
77 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee W | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 1725 | 100 |  | 0 | 100 |  | 0
78 | bugfixing | 2013-12-02 08:00 | 2013-12-02 15:00 | 6h | Employee Q | 450 | 0 | 0 | 0 | 450 | 2014-01-06 08:00 | 4h | 300 | 300 | 4h | 0 | 0 | 300 | 300 | 75% | Started | 337.5 | 450 | 100 | 66.6667 | 75 | 100 | 66.6667 | 75
79 | bugfixing | 2013-12-02 08:00 | 2013-12-09 14:00 | 5d 5h | Employee N | 3375 | 0 | 0 | 0 | 3375 |  | 0 | 0 | 3375 | 5d 5h | 0 | 0 | 0 | 3375 | 0% | Not Started | 0 | 3375 | 100 |  | 0 | 100 |  | 0
80 | bugfixing | 2013-12-02 08:00 | 2014-01-06 12:00 | 25d 4h | Employee E | 15300 | 0 | 0 | 0 | 15300 | 2013-12-02 08:00 | 16d 1h | 9675 | 5400 | 9d | 0 | 0 | 9675 | 5400 | 64.18% | Started | 9819.403 | 15300 | 100 | 63.2353 | 64.1791 | 100 | 63.2353 | 64.1791
81 | bugfixing | 2013-12-02 08:00 | 2013-12-02 12:00 | 4h | Employee X | 300 | 0 | 0 | 0 | 300 | 2013-12-09 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
82 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee L | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 1725 | 100 |  | 0 | 100 |  | 0
98 | bugfixing | 2013-12-02 08:00 | 2013-12-17 17:00 | 12d | Employee P | 7200 | 0 | 0 | 0 | 7200 | 2013-12-02 08:00 | 9d 4h | 5700 | 0 | 0 | 0 | 0 | 5700 | 0 | 100% | Finished | 7200 | 7200 | 100 | 79.1667 | 100 | 100 | 79.1667 | 100
83 | ict test completed | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | ondersteuning | 2013-09-17 08:00 | 2013-10-17 10:00 | 22d 2h |  |  | 0 |  |  | 17400 |  | 81d 1h | [5 empty] | 10575 |  | 58.05% |  | 10101.2934 | 17400
84 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-17 09:00 | 1h | Employee J | 75 | 0 | 0 | 0 | 75 | 2013-09-16 08:00 | 4h | 300 | 225 | 3h | 0 | 0 | 300 | 225 | 51% | Started | 38.25 | 75 | 100 | 400 | 51 | 100 | 400 | 51
85 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-17 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 | 2013-11-05 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 600 | 600 | 100 | 112.5 | 100 | 100 | 112.5 | 100
86 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-24 14:00 | 5d 5h | Employee G | 3375 | 0 | 0 | 0 | 3375 | 2013-11-04 08:00 | 4d 6h | 2850 | 600 | 1d | 0 | 0 | 2850 | 600 | 82.61% | Started | 2788.0434 | 3375 | 100 | 84.4444 | 82.6087 | 100 | 84.4444 | 82.6087
87 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-10-17 10:00 | 22d 2h | Employee D | 13350 | 0 | 0 | 0 | 13350 | 2013-11-04 08:00 | 11d 2h | 6750 | 6750 | 11d 2h | 0 | 0 | 6750 | 6750 | 50% | Started | 6675 | 13350 | 100 | 50.5618 | 50 | 100 | 50.5618 | 50
100 | implementation | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | go live | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | post implementation | 2014-01-27 08:00 | 2014-02-05 12:00 | 7d 4h |  |  | 0 |  |  | 8400 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
88 | post implementation - post go live support | 2014-01-27 08:00 | 2014-02-05 12:00 | 7d 4h | Employee E | 4500 | 0 | 0 | 0 | 4500 |  | 0 | 0 | 4500 | 7d 4h | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-29 11:00 | 2d 3h | Employee R | 1425 | 0 | 0 | 0 | 1425 |  | 0 | 0 | 1425 | 2d 3h | 0 | 0 | 0 | 1425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-28 09:00 | 1d 1h | Employee T | 675 | 0 | 0 | 0 | 675 |  | 0 | 0 | 675 | 1d 1h | 0 | 0 | 0 | 675 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-27 10:00 | 2h | Employee L | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-29 15:00 | 2d 6h | Employee D | 1650 | 0 | 0 | 0 | 1650 |  | 0 | 0 | 1650 | 2d 6h | 0 | 0 | 0 | 1650 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2014-03-17 22:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Insurance Bundling System | 2013-04-19 08:00 | 2014-02-05 12:00 | 208d 4h |  |  | 0 |  |  | 281430 |  | 236d 1h | [5 empty] | 281070 |  | 100% |  | 281430 | 281430
31 | supporting tasks | 2013-07-16 08:00 | 2013-09-02 17:00 | 35d |  |  | 0 |  |  | 26190 |  | 35d 1h | [5 empty] | 26280 |  | 100% |  | 26190 | 26190
1 | project management | 2013-07-16 08:00 | 2013-09-02 17:00 | 35d | Employee A | 25200 | 0 | 0 | 0 | 25200 | 2013-07-15 08:00 | 35d 1h | 25290 | 0 | 0 | 0 | 0 | 25290 | 0 | 100% | Finished | 25200 | 25200 | 100 | 100.3571 | 100 | 100 | 100.3571 | 100
2 | project management | 2013-07-16 08:00 | 2013-07-17 11:00 | 1d 3h | Employee B | 990 | 0 | 0 | 0 | 990 | 2013-08-19 08:00 | 1d 3h | 990 | 0 | 0 | 0 | 0 | 990 | 0 | 100% | Finished | 990 | 990 | 100 | 100 | 100 | 100 | 100 | 100
30 | analysis | 2013-04-19 08:00 | 2013-09-27 17:00 | 116d |  |  | 0 |  |  | 38340 |  | 142d 7h | [5 empty] | 38490 |  | 100% |  | 38340 | 38340
3 | analysis - business analysis | 2013-07-01 08:00 | 2013-08-23 11:00 | 39d 3h | Employee D | 23625 | 0 | 0 | 0 | 23625 | 2013-07-01 08:00 | 39d 5h | 23775 | 0 | 0 | 0 | 0 | 23775 | 0 | 100% | Finished | 23625 | 23625 | 100 | 100.6349 | 100 | 100 | 100.6349 | 100
4 | analysis - datamodel | 2013-09-09 08:00 | 2013-09-13 11:00 | 4d 3h | Employee D | 2625 | 0 | 0 | 0 | 2625 | 2013-10-21 08:00 | 4d 3h | 2625 | 0 | 0 | 0 | 0 | 2625 | 0 | 100% | Finished | 2625 | 2625 | 100 | 100 | 100 | 100 | 100 | 100
5 | analysis - I/O services | 2013-09-23 08:00 | 2013-09-25 12:00 | 2d 4h | Employee D | 1500 | 0 | 0 | 0 | 1500 | 2013-10-28 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 100% | Finished | 1500 | 1500 | 100 | 110 | 100 | 100 | 110 | 100
6 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-22 10:00 | 1d 2h | Employee C | 750 | 0 | 0 | 0 | 750 | 2013-07-01 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
7 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-30 10:00 | 7d 2h | Employee E | 4350 | 0 | 0 | 0 | 4350 | 2013-04-22 08:00 | 7d 2h | 4350 | 0 | 0 | 0 | 0 | 4350 | 0 | 100% | Finished | 4350 | 4350 | 100 | 100 | 100 | 100 | 100 | 100
8 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-26 12:00 | 5d 4h | Employee F | 3300 | 0 | 0 | 0 | 3300 | 2013-04-19 08:00 | 5d 2h | 3150 | 0 | 0 | 0 | 0 | 3150 | 0 | 100% | Finished | 3300 | 3300 | 100 | 95.4545 | 100 | 100 | 95.4545 | 100
9 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 15:00 | 6h | Employee B | 540 | 0 | 0 | 0 | 540 | 2013-07-29 08:00 | 6h | 540 | 0 | 0 | 0 | 0 | 540 | 0 | 100% | Finished | 540 | 540 | 100 | 100 | 100 | 100 | 100 | 100
10 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2013-04-19 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 100 | 100
11 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 16:00 | 7h | Employee H | 525 | 0 | 0 | 0 | 525 | 2013-04-22 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
12 | analysis - solution concept | 2013-04-19 08:00 | 2013-04-19 16:00 | 7h | Employee I | 525 | 0 | 0 | 0 | 525 | 2013-07-29 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
13 | analysis validated | 2013-09-27 17:00 | 2013-09-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-11-05 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
29 | design | 2013-04-19 08:00 | 2013-11-15 17:00 | 151d |  |  | 0 |  |  | 18600 |  | 68d 7h | [5 empty] | 18900 |  | 100% |  | 18600 | 18600
14 | BPA | 2013-09-16 08:00 | 2013-09-17 10:00 | 1d 2h | Employee J | 750 | 0 | 0 | 0 | 750 | 2013-09-16 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
15 | CDM | 2013-10-14 08:00 | 2013-10-14 16:00 | 7h | Employee J | 525 | 0 | 0 | 0 | 525 | 2013-10-07 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
16 | classic | 2013-08-21 08:00 | 2013-08-23 14:00 | 2d 5h | Employee K | 1575 | 0 | 0 | 0 | 1575 | 2013-08-19 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 100% | Finished | 1575 | 1575 | 100 | 104.7619 | 100 | 100 | 104.7619 | 100
17 | classic | 2013-08-21 08:00 | 2013-08-26 10:00 | 3d 2h | Employee L | 1950 | 0 | 0 | 0 | 1950 | 2013-10-07 08:00 | 3d 3h | 2025 | 0 | 0 | 0 | 0 | 2025 | 0 | 100% | Finished | 1950 | 1950 | 100 | 103.8462 | 100 | 100 | 103.8462 | 100
18 | SAD/interface design | 2013-10-21 08:00 | 2013-10-25 11:00 | 4d 3h | Employee L | 2625 | 0 | 0 | 0 | 2625 | 2013-10-07 08:00 | 4d 4h | 2700 | 0 | 0 | 0 | 0 | 2700 | 0 | 100% | Finished | 2625 | 2625 | 100 | 102.8571 | 100 | 100 | 102.8571 | 100
19 | BPA | 2013-04-19 08:00 | 2013-04-19 09:00 | 1h | Employee J | 75 | 0 | 0 | 0 | 75 | 2013-09-30 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
20 | CDM | 2013-04-19 08:00 | 2013-04-19 11:00 | 3h | Employee J | 225 | 0 | 0 | 0 | 225 | 2013-09-30 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 225 | 225 | 100 | 100 | 100 | 100 | 100 | 100
21 | get NB | 2013-09-30 08:00 | 2013-10-03 16:00 | 3d 7h | Employee M | 2325 | 0 | 0 | 0 | 2325 | 2013-09-30 08:00 | 3d 7h | 2325 | 0 | 0 | 0 | 0 | 2325 | 0 | 100% | Finished | 2325 | 2325 | 100 | 100 | 100 | 100 | 100 | 100
22 | PO - BPA | 2013-09-18 08:00 | 2013-09-18 16:00 | 7h | Employee J | 525 | 0 | 0 | 0 | 525 | 2013-09-16 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
23 | PO - CDM | 2013-10-01 08:00 | 2013-10-01 14:00 | 5h | Employee J | 375 | 0 | 0 | 0 | 375 | 2013-09-30 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
24 | quote - BPA | 2013-10-03 08:00 | 2013-10-04 09:00 | 1d 1h | Employee J | 675 | 0 | 0 | 0 | 675 | 2013-09-30 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 675 | 675 | 100 | 100 | 100 | 100 | 100 | 100
25 | quote - CDM | 2013-10-14 08:00 | 2013-10-15 11:00 | 1d 3h | Employee J | 825 | 0 | 0 | 0 | 825 | 2013-10-07 08:00 | 1d 3h | 825 | 0 | 0 | 0 | 0 | 825 | 0 | 100% | Finished | 825 | 825 | 100 | 100 | 100 | 100 | 100 | 100
26 | quote - NB | 2013-10-07 08:00 | 2013-10-07 16:00 | 7h | Employee M | 525 | 0 | 0 | 0 | 525 | 2013-09-30 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 525 | 525 | 100 | 114.2857 | 100 | 100 | 114.2857 | 100
27 | web - user interface design | 2013-09-16 08:00 | 2013-09-25 09:00 | 7d 1h | Employee L | 4275 | 0 | 0 | 0 | 4275 | 2013-09-16 08:00 | 7d 1h | 4275 | 0 | 0 | 0 | 0 | 4275 | 0 | 100% | Finished | 4275 | 4275 | 100 | 100 | 100 | 100 | 100 | 100
96 | web - user interface integratie | 2013-11-12 08:00 | 2013-11-14 10:00 | 2d 2h | Employee L | 1350 | 0 | 0 | 0 | 1350 | 2013-11-18 08:00 | 2d 2h | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 100% | Finished | 1350 | 1350 | 100 | 100 | 100 | 100 | 100 | 100
28 | design validated | 2013-11-15 17:00 | 2013-11-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-11-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
66 | build | 2013-09-24 08:00 | 2013-12-16 17:00 | 60d |  |  | 0 |  |  | 81825 |  | 60d 7h | [5 empty] | 87675 |  | 100% |  | 81825 | 81825
32 | GP - classic | 2013-10-14 08:00 | 2013-10-29 10:00 | 11d 2h | Employee N | 6750 | 0 | 0 | 0 | 6750 | 2013-10-21 08:00 | 11d 2h | 6750 | 0 | 0 | 0 | 0 | 6750 | 0 | 100% | Finished | 6750 | 6750 | 100 | 100 | 100 | 100 | 100 | 100
33 | GP - classic | 2013-10-14 08:00 | 2013-10-14 16:00 | 7h | Employee E | 525 | 0 | 0 | 0 | 525 | 2013-10-21 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
34 | GP - ESB | 2013-11-04 08:00 | 2013-11-05 17:00 | 2d | Employee O | 1200 | 0 | 0 | 0 | 1200 | 2013-10-21 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1200 | 1200 | 100 | 100 | 100 | 100 | 100 | 100
35 | GP - technical assembly test | 2013-11-18 08:00 | 2013-11-18 11:00 | 3h | Employee O | 225 | 0 | 0 | 0 | 225 | 2013-11-04 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 225 | 225 | 100 | 100 | 100 | 100 | 100 | 100
36 | classic - arbeidsongeval | 2013-09-30 08:00 | 2013-09-30 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2013-10-14 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
37 | classic - arbeidsongeval | 2013-09-30 08:00 | 2013-10-10 14:00 | 8d 5h | Employee P | 5175 | 0 | 0 | 0 | 5175 | 2013-09-30 08:00 | 8d 5h | 5175 | 0 | 0 | 0 | 0 | 5175 | 0 | 100% | Finished | 5175 | 5175 | 100 | 100 | 100 | 100 | 100 | 100
38 | classic - auto | 2013-10-07 08:00 | 2013-10-09 10:00 | 2d 2h | Employee E | 1350 | 0 | 0 | 0 | 1350 | 2013-10-07 08:00 | 2d 2h | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 100% | Finished | 1350 | 1350 | 100 | 100 | 100 | 100 | 100 | 100
39 | classic - auto | 2013-10-07 08:00 | 2013-10-18 10:00 | 9d 2h | Employee P | 5550 | 0 | 0 | 0 | 5550 | 2013-10-07 08:00 | 9d 2h | 5550 | 0 | 0 | 0 | 0 | 5550 | 0 | 100% | Finished | 5550 | 5550 | 100 | 100 | 100 | 100 | 100 | 100
40 | classic - brand | 2013-10-28 08:00 | 2013-10-29 10:00 | 1d 2h | Employee E | 750 | 0 | 0 | 0 | 750 | 2013-10-07 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 750 | 750 | 100 | 100 | 100 | 100 | 100 | 100
41 | classic - brand | 2013-10-28 08:00 | 2013-10-28 16:00 | 7h | Employee P | 525 | 0 | 0 | 0 | 525 | 2013-10-28 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
42 | classic - cleansing data | 2013-11-04 08:00 | 2013-11-15 11:00 | 9d 3h | Employee N | 5625 | 0 | 0 | 0 | 5625 | 2013-09-30 08:00 | 3d 6h | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 5625 | 5625 | 100 | 40 | 100 | 100 | 40 | 100
43 | classic - cleansing | 2013-11-04 08:00 | 2013-11-15 12:00 | 9d 4h | Employee E | 5700 | 0 | 0 | 0 | 5700 | 2013-11-18 08:00 | 9d 4h | 5700 | 0 | 0 | 0 | 0 | 5700 | 0 | 100% | Finished | 5700 | 5700 | 100 | 100 | 100 | 100 | 100 | 100
44 | classic - cleansing voorbereiding | 2013-09-30 08:00 | 2013-10-02 16:00 | 2d 7h | Employee N | 1725 | 0 | 0 | 0 | 1725 | 2013-10-07 08:00 | 30d 7h | 18525 | 0 | 0 | 0 | 0 | 18525 | 0 | 100% | Finished | 1725 | 1725 | 100 | 1073.913 | 100 | 100 | 1073.913 | 100
45 | classic - cleansing voorbereiding | 2013-09-30 08:00 | 2013-10-04 14:00 | 4d 5h | Employee E | 2775 | 0 | 0 | 0 | 2775 | 2013-10-07 08:00 | 4d 5h | 2775 | 0 | 0 | 0 | 0 | 2775 | 0 | 100% | Finished | 2775 | 2775 | 100 | 100 | 100 | 100 | 100 | 100
46 | dashboard - BO | 2013-11-12 08:00 | 2013-11-12 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 | 2013-11-11 08:00 | 6h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 450 | 450 | 100 | 100 | 100 | 100 | 100 | 100
47 | dashboard - UI | 2013-11-25 08:00 | 2013-11-25 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2013-11-04 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
48 | dashboard - UI | 2013-11-25 08:00 | 2013-12-16 15:00 | 15d 6h | Employee P | 9450 | 0 | 0 | 0 | 9450 | 2013-11-04 08:00 | 15d 7h | 9525 | 0 | 0 | 0 | 0 | 9525 | 0 | 100% | Finished | 9450 | 9450 | 100 | 100.7937 | 100 | 100 | 100.7937 | 100
49 | classic - BO leeg gezin | 2013-09-26 08:00 | 2013-09-26 16:00 | 7h | Employee N | 525 | 0 | 0 | 0 | 525 | 2013-09-23 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
50 | classic - BO leeg gezin | 2013-09-26 08:00 | 2013-09-26 10:00 | 2h | Employee E | 150 | 0 | 0 | 0 | 150 | 2013-10-14 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
51 | classic - BO | 2013-10-21 08:00 | 2013-11-04 11:00 | 10d 3h | Employee E | 6225 | 0 | 0 | 0 | 6225 | 2013-11-11 08:00 | 4d 7h | 2925 | 0 | 0 | 0 | 0 | 2925 | 0 | 100% | Finished | 6225 | 6225 | 100 | 46.988 | 100 | 100 | 46.988 | 100
52 | classic - annuleren | 2013-11-25 08:00 | 2013-11-27 11:00 | 2d 3h | Employee E | 1425 | 0 | 0 | 0 | 1425 | 2013-11-04 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1425 | 1425 | 100 | 52.6316 | 100 | 100 | 52.6316 | 100
53 | classic - voltooien | 2013-11-18 08:00 | 2013-11-20 11:00 | 2d 3h | Employee E | 1425 | 0 | 0 | 0 | 1425 | 2013-11-04 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 1425 | 1425 | 100 | 47.3684 | 100 | 100 | 47.3684 | 100
54 | classic - UI detail | 2013-09-25 08:00 | 2013-09-25 15:00 | 6h | Employee E | 450 | 0 | 0 | 0 | 450 | 2013-09-23 08:00 | 6h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 450 | 450 | 100 | 100 | 100 | 100 | 100 | 100
55 | classic - UI | 2013-09-24 08:00 | 2013-09-26 09:00 | 2d 1h | Employee E | 1275 | 0 | 0 | 0 | 1275 | 2013-09-23 08:00 | 2d 1h | 1275 | 0 | 0 | 0 | 0 | 1275 | 0 | 100% | Finished | 1275 | 1275 | 100 | 100 | 100 | 100 | 100 | 100
56 | classic - inhoud | 2013-09-30 08:00 | 2013-10-08 15:00 | 6d 6h | Employee E | 4050 | 0 | 0 | 0 | 4050 | 2013-09-30 08:00 | 4d 5h | 2775 | 0 | 0 | 0 | 0 | 2775 | 0 | 100% | Finished | 4050 | 4050 | 100 | 68.5185 | 100 | 100 | 68.5185 | 100
57 | classic - leden | 2013-11-12 08:00 | 2013-11-12 17:00 | 1d | Employee P | 600 | 0 | 0 | 0 | 600 | 2013-11-04 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 100 | 100
58 | classic - varia | 2013-10-22 08:00 | 2013-10-22 14:00 | 5h | Employee E | 375 | 0 | 0 | 0 | 375 | 2013-10-14 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
59 | classic - varia | 2013-10-22 08:00 | 2013-10-29 14:00 | 5d 5h | Employee P | 3375 | 0 | 0 | 0 | 3375 | 2013-10-14 08:00 | 2d 3h | 1425 | 0 | 0 | 0 | 0 | 1425 | 0 | 100% | Finished | 3375 | 3375 | 100 | 42.2222 | 100 | 100 | 42.2222 | 100
61 | get NB - ESB | 2013-11-18 08:00 | 2013-11-20 17:00 | 3d | Employee V | 1800 | 0 | 0 | 0 | 1800 | 2013-11-18 08:00 | 3d | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 100% | Finished | 1800 | 1800 | 100 | 100 | 100 | 100 | 100 | 100
62 | PO - classic | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d | Employee E | 3000 | 0 | 0 | 0 | 3000 | 2013-11-18 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
63 | quote - ESB | 2013-11-18 08:00 | 2013-11-19 14:00 | 1d 5h | Employee O | 975 | 0 | 0 | 0 | 975 | 2013-11-04 08:00 | 1d 6h | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 100% | Finished | 975 | 975 | 100 | 107.6923 | 100 | 100 | 107.6923 | 100
64 | web | 2013-11-18 08:00 | 2013-11-19 17:00 | 2d | Employee H | 1200 | 0 | 0 | 0 | 1200 | 2013-11-18 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1200 | 1200 | 100 | 100 | 100 | 100 | 100 | 100
97 | web | 2013-11-18 08:00 | 2013-12-02 17:00 | 11d | Employee Q | 6600 | 0 | 0 | 0 | 6600 | 2013-11-11 08:00 | 11d 3h | 6825 | 0 | 0 | 0 | 0 | 6825 | 0 | 100% | Finished | 6600 | 6600 | 100 | 103.4091 | 100 | 100 | 103.4091 | 100
65 | build validated | 2013-12-16 17:00 | 2013-12-16 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-12-16 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
93 | test ict | 2013-10-10 08:00 | 2014-01-24 17:00 | 77d |  |  | 0 |  |  | 90675 |  | 115d 1h | [5 empty] | 88050 |  | 100% |  | 90675 | 90675
67 | test coordination | 2013-10-14 08:00 | 2013-10-25 09:00 | 9d 1h | Employee R | 5475 | 0 | 0 | 0 | 5475 | 2013-10-14 08:00 | 9d 1h | 5475 | 0 | 0 | 0 | 0 | 5475 | 0 | 100% | Finished | 5475 | 5475 | 100 | 100 | 100 | 100 | 100 | 100
68 | test execution | 2013-11-18 08:00 | 2013-12-13 12:00 | 19d 4h | Employee S | 11700 | 0 | 0 | 0 | 11700 | 2013-12-23 08:00 | 4d 4h | 2700 | 0 | 0 | 0 | 0 | 2700 | 0 | 100% | Finished | 11700 | 11700 | 100 | 23.0769 | 100 | 100 | 23.0769 | 100
69 | test execution | 2013-11-18 08:00 | 2013-12-18 16:00 | 22d 7h | Employee R | 13725 | 0 | 0 | 0 | 13725 | 2013-12-02 08:00 | 31d 5h | 18975 | 0 | 0 | 0 | 0 | 18975 | 0 | 100% | Finished | 13725 | 13725 | 100 | 138.2514 | 100 | 100 | 138.2514 | 100
70 | test execution | 2013-11-18 08:00 | 2013-12-16 09:00 | 20d 1h | Employee T | 12075 | 0 | 0 | 0 | 12075 | 2013-11-25 08:00 | 30d 7h | 18525 | 0 | 0 | 0 | 0 | 18525 | 0 | 100% | Finished | 12075 | 12075 | 100 | 153.4161 | 100 | 100 | 153.4161 | 100
71 | test execution | 2013-11-18 08:00 | 2013-11-18 16:00 | 7h | Employee L | 525 | 0 | 0 | 0 | 525 | 2014-01-13 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
72 | test preparation | 2013-10-10 08:00 | 2013-10-10 14:00 | 5h | Employee S | 375 | 0 | 0 | 0 | 375 | 2013-11-18 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
73 | test preparation | 2013-10-10 08:00 | 2013-10-21 17:00 | 8d | Employee R | 4800 | 0 | 0 | 0 | 4800 | 2013-11-11 08:00 | 9d 7h | 5925 | 0 | 0 | 0 | 0 | 5925 | 0 | 100% | Finished | 4800 | 4800 | 100 | 123.4375 | 100 | 100 | 123.4375 | 100
74 | test preparation | 2013-10-10 08:00 | 2013-10-30 10:00 | 14d 2h | Employee T | 8550 | 0 | 0 | 0 | 8550 | 2013-10-07 08:00 | 16d 1h | 9675 | 0 | 0 | 0 | 0 | 9675 | 0 | 100% | Finished | 8550 | 8550 | 100 | 113.1579 | 100 | 100 | 113.1579 | 100
75 | test preparation | 2013-10-10 08:00 | 2013-10-14 15:00 | 2d 6h | Employee U | 1650 | 0 | 0 | 0 | 1650 | 2014-01-13 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 100% | Finished | 1650 | 1650 | 100 | 100 | 100 | 100 | 100 | 100
76 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee V | 1725 | 0 | 0 | 0 | 1725 | 2013-12-23 08:00 | 3d 2h | 1950 | 0 | 0 | 0 | 0 | 1950 | 0 | 100% | Finished | 1725 | 1725 | 100 | 113.0435 | 100 | 100 | 113.0435 | 100
77 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee W | 1725 | 0 | 0 | 0 | 1725 | 2014-01-08 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1725 | 1725 | 100 | 4.3478 | 100 | 100 | 4.3478 | 100
78 | bugfixing | 2013-12-02 08:00 | 2013-12-02 15:00 | 6h | Employee Q | 450 | 0 | 0 | 0 | 450 | 2014-01-06 08:00 | 6h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 450 | 450 | 100 | 100 | 100 | 100 | 100 | 100
79 | bugfixing | 2013-12-02 08:00 | 2013-12-09 14:00 | 5d 5h | Employee N | 3375 | 0 | 0 | 0 | 3375 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 3375 | 3375 | 100 | 2.2222 | 100 | 100 | 2.2222 | 100
80 | bugfixing | 2013-12-02 08:00 | 2014-01-06 12:00 | 25d 4h | Employee E | 15300 | 0 | 0 | 0 | 15300 | 2013-12-02 08:00 | 25d 5h | 15375 | 0 | 0 | 0 | 0 | 15375 | 0 | 100% | Finished | 15300 | 15300 | 100 | 100.4902 | 100 | 100 | 100.4902 | 100
81 | bugfixing | 2013-12-02 08:00 | 2013-12-02 12:00 | 4h | Employee X | 300 | 0 | 0 | 0 | 300 | 2013-12-09 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 300 | 300 | 100 | 100 | 100 | 100 | 100 | 100
82 | bugfixing | 2013-12-02 08:00 | 2013-12-04 16:00 | 2d 7h | Employee L | 1725 | 0 | 0 | 0 | 1725 | 2014-01-27 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 1725 | 1725 | 100 | 17.3913 | 100 | 100 | 17.3913 | 100
98 | bugfixing | 2013-12-02 08:00 | 2013-12-17 17:00 | 12d | Employee P | 7200 | 0 | 0 | 0 | 7200 | 2013-12-02 08:00 | 9d 4h | 5700 | 0 | 0 | 0 | 0 | 5700 | 0 | 100% | Finished | 7200 | 7200 | 100 | 79.1667 | 100 | 100 | 79.1667 | 100
83 | ict test completed | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
94 | ondersteuning | 2013-09-17 08:00 | 2013-10-17 10:00 | 22d 2h |  |  | 0 |  |  | 17400 |  | 57d 2h | [5 empty] | 17700 |  | 100% |  | 17400 | 17400
84 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-17 09:00 | 1h | Employee J | 75 | 0 | 0 | 0 | 75 | 2013-09-16 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 75 | 75 | 100 | 400 | 100 | 100 | 400 | 100
85 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-17 17:00 | 1d | Employee C | 600 | 0 | 0 | 0 | 600 | 2013-11-05 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 600 | 600 | 100 | 112.5 | 100 | 100 | 112.5 | 100
86 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-09-24 14:00 | 5d 5h | Employee G | 3375 | 0 | 0 | 0 | 3375 | 2013-11-04 08:00 | 5d 5h | 3375 | 0 | 0 | 0 | 0 | 3375 | 0 | 100% | Finished | 3375 | 3375 | 100 | 100 | 100 | 100 | 100 | 100
87 | ondersteuning tijdens design/build/test | 2013-09-17 08:00 | 2013-10-17 10:00 | 22d 2h | Employee D | 13350 | 0 | 0 | 0 | 13350 | 2013-11-04 08:00 | 22d 2h | 13350 | 0 | 0 | 0 | 0 | 13350 | 0 | 100% | Finished | 13350 | 13350 | 100 | 100 | 100 | 100 | 100 | 100
100 | implementation | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | go live | 2014-01-24 17:00 | 2014-01-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
101 | post implementation | 2014-01-27 08:00 | 2014-02-05 12:00 | 7d 4h |  |  | 0 |  |  | 8400 |  | 12d 3h | [5 empty] | 3975 |  | 100% |  | 8400 | 8400
88 | post implementation - post go live support | 2014-01-27 08:00 | 2014-02-05 12:00 | 7d 4h | Employee E | 4500 | 0 | 0 | 0 | 4500 | 2014-01-27 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 4500 | 4500 | 100 | 1.6667 | 100 | 100 | 1.6667 | 100
89 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-29 11:00 | 2d 3h | Employee R | 1425 | 0 | 0 | 0 | 1425 | 2014-02-10 08:00 | 2d 3h | 1425 | 0 | 0 | 0 | 0 | 1425 | 0 | 100% | Finished | 1425 | 1425 | 100 | 100 | 100 | 100 | 100 | 100
90 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-28 09:00 | 1d 1h | Employee T | 675 | 0 | 0 | 0 | 675 | 2014-02-10 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 675 | 675 | 100 | 100 | 100 | 100 | 100 | 100
91 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-27 10:00 | 2h | Employee L | 150 | 0 | 0 | 0 | 150 | 2014-02-10 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
92 | post implementation - post go live support | 2014-01-27 08:00 | 2014-01-29 15:00 | 2d 6h | Employee D | 1650 | 0 | 0 | 0 | 1650 | 2014-02-03 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 100% | Finished | 1650 | 1650 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2013-04-19 08:00 | 2013-07-01 22:00 | 11490 | 2355 | 3150 | 2013-04-19 11:00 | -9135 | 20.5% | -795 | 74.76% | -51d 5h | 0.7212% | 47.27% | 2014-02-14 10:00 | 2017-03-14 10:00 | 2018-07-06 14:00 | 2014-04-03 16:00 | 2017-03-14 10:00 | 2018-06-13 09:00 | 2014-04-18 09:00 | 2124-02-14 17:00 | 2161-06-18 12:00 | 282225 | 376435.0345 | 1364751.602 | 38701550.0023 | 1824400.5633 | 51765341.4507 | 439827.3617 | 468633.7782 | 0.0072115 | 0.74762 | 0.20496 | 0.47266 | -51.625 | 0.74762 | 1 | 0.0072115 | 1
Tracking 2 | 2013-07-01 22:00 | 2013-09-02 22:00 | 64230 | 25152.0005 | 25110 | 2013-07-22 17:00 | -39077.9995 | 39.16% | 42.0005 | 100.2% | -30d | 69.07% | 83.54% | 2014-03-18 12:00 | 2015-05-05 12:00 | 2015-05-04 12:00 | 2014-04-29 12:00 | 2015-05-05 12:00 | 2015-05-04 15:00 | 2014-03-19 12:00 | 2014-06-16 16:00 | 2014-06-16 12:00 | 281387.9995 | 280960.049 | 679560.3642 | 396139.3425 | 678467.5183 | 395519.7724 | 316448.6634 | 297896.3591 | 0.69072 | 1.0017 | 0.39159 | 0.83541 | -30 | 1.0017 | 1 | 0.69072 | 1
Tracking 3 | 2013-09-02 22:00 | 2013-11-04 22:00 | 166680 | 108541.3398 | 107580 | 2013-10-08 11:00 | -58138.6602 | 65.12% | 961.3398 | 100.9% | -19d 5h | 86.18% | 65.97% | 2014-04-07 14:00 | 2014-07-11 09:00 | 2014-07-08 11:00 | 2014-04-15 17:00 | 2014-07-11 09:00 | 2014-07-09 14:00 | 2014-03-05 09:00 | 2014-03-24 16:00 | 2014-03-21 17:00 | 280468.6602 | 278937.4025 | 373074.0681 | 308194.4208 | 370722.6136 | 306417.5988 | 292016.5998 | 284085.6147 | 0.8618 | 1.0089 | 0.6512 | 0.65973 | -19.625 | 1.0089 | 1 | 0.8618 | 1
Tracking 4 | 2013-11-04 22:00 | 2014-01-07 09:00 | 273030 | 220359.4996 | 226785 | 2013-12-02 14:00 | -52670.5004 | 80.71% | -6425.5004 | 97.17% | -25d 4h | 86.37% | 88.09% | 2014-04-01 12:00 | 2014-04-16 11:00 | 2014-04-25 16:00 | 2014-03-27 14:00 | 2014-04-16 11:00 | 2014-04-18 11:00 | 2014-03-12 17:00 | 2014-03-24 11:00 | 2014-03-25 17:00 | 287855.5004 | 289636.2656 | 302452.6193 | 297490.7534 | 304659.0244 | 299552.4746 | 291840.0307 | 291064.386 | 0.86373 | 0.97167 | 0.80709 | 0.8809 | -25.5 | 0.97167 | 1 | 0.86373 | 1
Closure | 2014-01-07 09:00 | 2014-03-17 22:00 | 281430 | 281430 | 281070 | 2014-02-05 12:00 | 0 | 100% | 360 | 100.1% | -28d 4h | 87.97% | 100% | 2014-02-05 12:00 | 2014-02-05 12:00 | 2014-02-05 10:00 | 2014-03-17 17:00 | 2014-03-17 17:00 | 2014-03-17 17:00 | 2014-03-17 17:00 | 2014-03-17 17:00 | 2014-03-17 17:00 | 281070 | 281070 | 281070 | 281070 | 281070 | 281070 | 281070 | 281070 | 0.87975 | 1.0013 | 1 | 1 | -28.5 | 1.0013 | 1 | 0.87975 | 1