## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Receipt Numbering System | 1 |  |  | 2013-09-02 08:00 | 2014-05-13 16:00 | 181d 7h |  |  | 0 |  |  | 43800 | 253.3333
25 | supporting tasks | 1.1 |  |  | 2013-09-02 08:00 | 2013-11-29 17:00 | 65d |  |  | 0 |  |  | 11775 | 88.375
1 | project management | 1.1.1 |  | FS2;FS3;FS4;FS5 | 2013-09-02 08:00 | 2013-09-10 16:00 | 6d 7h | Employee I | 4950 | 0 | 0 | 0 | 4950 | 8.3333
2 | validation and support | 1.1.2 | 1FS |  | 2013-11-22 08:00 | 2013-11-25 16:00 | 1d 7h | Employee A | 1125 | 0 | 0 | 0 | 1125 | 3.3333
3 | validation and support | 1.1.3 | 1FS |  | 2013-11-22 08:00 | 2013-11-22 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 | 0.375
4 | validation and support | 1.1.4 | 1FS |  | 2013-11-22 08:00 | 2013-11-29 17:00 | 6d | Employee D | 3600 | 0 | 0 | 0 | 3600 | 7.375
5 | validation and support | 1.1.5 | 1FS | FS9;FS10;FS11;FS24 | 2013-11-22 08:00 | 2013-11-26 12:00 | 2d 4h | Employee L | 1500 | 0 | 0 | 0 | 1500 | 4.1667
26 | analysis | 1.2 |  |  | 2013-09-06 08:00 | 2013-12-31 17:00 | 83d |  |  | 0 |  |  | 750 | 116.375
6 | analysis - conceptual design | 1.2.1 |  | FS8 | 2013-09-06 08:00 | 2013-09-09 09:00 | 1d 1h | Employee A | 675 | 0 | 0 | 0 | 675 | 3.0417
7 | analysis - conceptual design | 1.2.2 |  | FS8;FS9;FS10;FS11 | 2013-09-06 08:00 | 2013-09-06 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 | 0.041667
8 | analysis validated | 1.2.3 | 6FS;7FS | FS24 | 2013-12-31 17:00 | 2013-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
27 | design | 1.3 |  |  | 2013-12-02 08:00 | 2014-02-18 17:00 | 57d |  |  | 0 |  |  | 9825 | 78.375
9 | design - MF | 1.3.1 | 5FS;7FS | FS13 | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h | Employee D | 150 | 0 | 0 | 0 | 150 | 0.083333
10 | design - MF | 1.3.2 | 5FS;7FS | FS13 | 2013-12-02 08:00 | 2013-12-03 15:00 | 1d 6h | Employee E | 1050 | 0 | 0 | 0 | 1050 | 1.2917
11 | design - MF | 1.3.3 | 5FS;7FS | FS13 | 2013-12-02 08:00 | 2013-12-20 10:00 | 14d 2h | Employee F | 8550 | 0 | 0 | 0 | 8550 | 18.0833
12 | design - DWH | 1.3.4 |  | FS13 | 2013-12-09 08:00 | 2013-12-09 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 0.041667
13 | design validated | 1.3.5 | 9FS;10FS;11FS;12FS | FS24 | 2014-02-18 17:00 | 2014-02-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
28 | development | 1.4 |  |  | 2013-11-19 08:00 | 2014-02-28 17:00 | 74d |  |  | 0 |  |  | 16875 | 101.375
14 | development - coding MF | 1.4.1 |  | FS20 | 2013-11-19 08:00 | 2013-12-13 17:00 | 19d | Employee G | 11400 | 0 | 0 | 0 | 11400 | 24.375
15 | development - coding MF | 1.4.2 |  | FS20 | 2013-11-19 08:00 | 2013-11-28 14:00 | 7d 5h | Employee H | 4575 | 0 | 0 | 0 | 4575 | 9.25
16 | development - coding MF | 1.4.3 |  | FS20 | 2013-11-19 08:00 | 2013-11-19 14:00 | 5h | Employee E | 375 | 0 | 0 | 0 | 375 | 0.25
17 | development - coding MF | 1.4.4 |  | FS20 | 2013-11-19 08:00 | 2013-11-19 16:00 | 7h | Employee F | 525 | 0 | 0 | 0 | 525 | 0.33333
20 | development completed | 1.4.5 | 14FS;15FS;16FS;17FS | FS24;FS32;FS31 | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
33 | development bugfixing | 1.5 |  |  | 2014-03-24 08:00 | 2014-03-26 11:00 | 2d 3h |  |  | 0 |  |  | 2250 | 2.125
32 | development - bugfixing | 1.5.1 | 20FS | FS24 | 2014-03-24 08:00 | 2014-03-26 11:00 | 2d 3h | Employee G | 1425 | 0 | 0 | 0 | 1425 | 2.125
31 | development - bugfixing | 1.5.2 | 20FS | FS24 | 2014-03-24 08:00 | 2014-03-25 11:00 | 1d 3h | Employee D | 825 | 0 | 0 | 0 | 825 | 1.125
29 | implementation | 1.6 |  |  | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0
24 | go live | 1.6.1 | 5FS;8FS;13FS;20FS;32FS;31FS | FS21;FS22;FS23 | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
30 | post implementation | 1.7 |  |  | 2014-05-12 08:00 | 2014-05-13 16:00 | 1d 7h |  |  | 0 |  |  | 2325 | 1.3333
21 | post implementation - post go live support | 1.7.1 | 24FS |  | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee A | 600 | 0 | 0 | 0 | 600 | 0.375
22 | post implementation - post go live support | 1.7.2 | 24FS |  | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 0.375
23 | post implementation - post go live support | 1.7.3 | 24FS |  | 2014-05-12 08:00 | 2014-05-13 16:00 | 1d 7h | Employee D | 1125 | 0 | 0 | 0 | 1125 | 1.3333

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee A | Renewable | 1 | 0 | 75 | 2;6;21; | 2400
2 | Employee B | Renewable | 1 | 0 | 75 | 7; | 75
3 | Employee C | Renewable | 1 | 0 | 75 | 12; | 75
4 | Employee D | Renewable | 1 | 0 | 75 | 4;9;31;23; | 5700
5 | Employee E | Renewable | 1 | 0 | 75 | 10;16; | 1425
6 | Employee F | Renewable | 1 | 0 | 75 | 11;17; | 9075
7 | Employee G | Renewable | 1 | 0 | 75 | 14;32;22; | 13425
8 | Employee H | Renewable | 1 | 0 | 75 | 15; | 4575
9 | Employee I | Renewable | 1 | 0 | 90 | 1; | 4950
10 | Employee J | Renewable | 1 | 0 | 75 |  | 0
11 | Employee K | Renewable | 1 | 0 | 75 | 3; | 600
12 | Employee L | Renewable | 1 | 0 | 75 | 5; | 1500

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Receipt Numbering System | 1455h |  |  |  |  | 99 | 100 | 101
25 | supporting tasks | 520h |  |  |  |  | 99 | 100 | 101
1 | project management | 55h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | validation and support | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | validation and support | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | validation and support | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | validation and support | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | analysis | 664h |  |  |  |  | 99 | 100 | 101
6 | analysis - conceptual design | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | analysis - conceptual design | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | analysis validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | design | 456h |  |  |  |  | 99 | 100 | 101
9 | design - MF | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | design - MF | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | design - MF | 114h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | design - DWH | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | design validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | development | 592h |  |  |  |  | 99 | 100 | 101
14 | development - coding MF | 152h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | development - coding MF | 61h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | development - coding MF | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | development - coding MF | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | development completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | development bugfixing | 19h |  |  |  |  | 99 | 100 | 101
32 | development - bugfixing | 19h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | development - bugfixing | 11h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | implementation | 0 |  |  |  |  | 99 | 100 | 101
24 | go live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | post implementation | 15h |  |  |  |  | 99 | 100 | 101
21 | post implementation - post go live support | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | post implementation - post go live support | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | post implementation - post go live support | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2013-11-18 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Receipt Numbering System | 2013-09-02 08:00 | 2014-05-13 16:00 | 181d 7h |  |  | 0 |  |  | 43800 |  | 56d | [5 empty] | 1035 |  | 3.003% |  | 1315.5 | 5700
25 | supporting tasks | 2013-09-02 08:00 | 2013-11-29 17:00 | 65d |  |  | 0 |  |  | 11775 |  | 56d | [5 empty] | 435 |  | 6.076% |  | 715.5 | 4950
1 | project management | 2013-09-02 08:00 | 2013-09-10 16:00 | 6d 7h | Employee I | 4950 | 0 | 0 | 0 | 4950 | 2013-09-02 08:00 | 4h | 360 | 2070 | 2d 7h | 0 | 0 | 360 | 2070 | 13% | Started | 643.5 | 4950 | 100 | 7.2727 | 13 | 100 | 7.2727 | 13
2 | validation and support | 2013-11-22 08:00 | 2013-11-25 16:00 | 1d 7h | Employee A | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | validation and support | 2013-11-22 08:00 | 2013-11-22 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | validation and support | 2013-11-22 08:00 | 2013-11-29 17:00 | 6d | Employee D | 3600 | 0 | 0 | 0 | 3600 | 2013-11-18 08:00 | 1h | 75 | 825 | 1d 3h | 0 | 0 | 75 | 825 | 2% | Started | 72 | 0 | 100 | 2.0833 | 2 | 100 | 2.0833 | 2
5 | validation and support | 2013-11-22 08:00 | 2013-11-26 12:00 | 2d 4h | Employee L | 1500 | 0 | 0 | 0 | 1500 |  | 0 | 0 | 1500 | 2d 4h | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | analysis | 2013-09-06 08:00 | 2013-12-31 17:00 | 83d |  |  | 0 |  |  | 750 |  | 52d | [5 empty] | 225 |  | 30% |  | 225 | 750
6 | analysis - conceptual design | 2013-09-06 08:00 | 2013-09-09 09:00 | 1d 1h | Employee A | 675 | 0 | 0 | 0 | 675 | 2013-09-06 08:00 | 3h | 225 | 450 | 6h | 0 | 0 | 225 | 450 | 33.33% | Started | 225 | 675 | 100 | 33.3333 | 33.3333 | 100 | 33.3333 | 33.3333
7 | analysis - conceptual design | 2013-09-06 08:00 | 2013-09-06 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 75 | 100 |  | 0 | 100 |  | 0
8 | analysis validated | 2013-12-31 17:00 | 2013-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | design | 2013-12-02 08:00 | 2014-02-18 17:00 | 57d |  |  | 0 |  |  | 9825 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | design - MF | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h | Employee D | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | design - MF | 2013-12-02 08:00 | 2013-12-03 15:00 | 1d 6h | Employee E | 1050 | 0 | 0 | 0 | 1050 |  | 0 | 0 | 1050 | 1d 6h | 0 | 0 | 0 | 1050 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | design - MF | 2013-12-02 08:00 | 2013-12-20 10:00 | 14d 2h | Employee F | 8550 | 0 | 0 | 0 | 8550 |  | 0 | 0 | 8550 | 14d 2h | 0 | 0 | 0 | 8550 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | design - DWH | 2013-12-09 08:00 | 2013-12-09 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 |  | 0 | 0 | 75 | 1h | 0 | 0 | 0 | 75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | design validated | 2014-02-18 17:00 | 2014-02-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | development | 2013-11-19 08:00 | 2014-02-28 17:00 | 74d |  |  | 0 |  |  | 16875 |  | 1d | [5 empty] | 375 |  | 2.222% |  | 375 | 0
14 | development - coding MF | 2013-11-19 08:00 | 2013-12-13 17:00 | 19d | Employee G | 11400 | 0 | 0 | 0 | 11400 |  | 0 | 0 | 11400 | 19d | 0 | 0 | 0 | 11400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | development - coding MF | 2013-11-19 08:00 | 2013-11-28 14:00 | 7d 5h | Employee H | 4575 | 0 | 0 | 0 | 4575 |  | 0 | 0 | 4575 | 7d 5h | 0 | 0 | 0 | 4575 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | development - coding MF | 2013-11-19 08:00 | 2013-11-19 14:00 | 5h | Employee E | 375 | 0 | 0 | 0 | 375 | 2013-11-18 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 0 | 100 | 100 | 100 | 100 | 100 | 100
17 | development - coding MF | 2013-11-19 08:00 | 2013-11-19 16:00 | 7h | Employee F | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | development completed | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | development bugfixing | 2014-03-24 08:00 | 2014-03-26 11:00 | 2d 3h |  |  | 0 |  |  | 2250 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | development - bugfixing | 2014-03-24 08:00 | 2014-03-26 11:00 | 2d 3h | Employee G | 1425 | 0 | 0 | 0 | 1425 |  | 0 | 0 | 1425 | 2d 3h | 0 | 0 | 0 | 1425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | development - bugfixing | 2014-03-24 08:00 | 2014-03-25 11:00 | 1d 3h | Employee D | 825 | 0 | 0 | 0 | 825 |  | 0 | 0 | 825 | 1d 3h | 0 | 0 | 0 | 825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | post implementation | 2014-05-12 08:00 | 2014-05-13 16:00 | 1d 7h |  |  | 0 |  |  | 2325 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee A | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 16:00 | 1d 7h | Employee D | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-01-13 22:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Receipt Numbering System | 2013-09-02 08:00 | 2014-05-13 16:00 | 181d 7h |  |  | 0 |  |  | 43800 |  | 96d | [5 empty] | 13275 |  | 33.27% |  | 14572.4998 | 39225
25 | supporting tasks | 2013-09-02 08:00 | 2013-11-29 17:00 | 65d |  |  | 0 |  |  | 11775 |  | 96d | [5 empty] | 3975 |  | 47.39% |  | 5579.9999 | 11775
1 | project management | 2013-09-02 08:00 | 2013-09-10 16:00 | 6d 7h | Employee I | 4950 | 0 | 0 | 0 | 4950 | 2013-09-02 08:00 | 1d 7h | 1350 | 1080 | 1d 4h | 0 | 0 | 1350 | 1080 | 48% | Started | 2375.9999 | 4950 | 100 | 27.2727 | 48 | 100 | 27.2727 | 48
2 | validation and support | 2013-11-22 08:00 | 2013-11-25 16:00 | 1d 7h | Employee A | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 1125 | 100 |  | 0 | 100 |  | 0
3 | validation and support | 2013-11-22 08:00 | 2013-11-22 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
4 | validation and support | 2013-11-22 08:00 | 2013-11-29 17:00 | 6d | Employee D | 3600 | 0 | 0 | 0 | 3600 | 2013-11-18 08:00 | 4d 3h | 2625 | 75 | 1h | 0 | 0 | 2625 | 75 | 89% | Started | 3203.9999 | 3600 | 100 | 72.9167 | 89 | 100 | 72.9167 | 89
5 | validation and support | 2013-11-22 08:00 | 2013-11-26 12:00 | 2d 4h | Employee L | 1500 | 0 | 0 | 0 | 1500 |  | 0 | 0 | 1500 | 2d 4h | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
26 | analysis | 2013-09-06 08:00 | 2013-12-31 17:00 | 83d |  |  | 0 |  |  | 750 |  | 92d | [5 empty] | 450 |  | 60% |  | 450 | 750
6 | analysis - conceptual design | 2013-09-06 08:00 | 2013-09-09 09:00 | 1d 1h | Employee A | 675 | 0 | 0 | 0 | 675 | 2013-09-06 08:00 | 5h | 375 | 300 | 4h | 0 | 0 | 375 | 300 | 55.56% | Started | 375 | 675 | 100 | 55.5556 | 55.5556 | 100 | 55.5556 | 55.5556
7 | analysis - conceptual design | 2013-09-06 08:00 | 2013-09-06 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 | 2013-12-16 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
8 | analysis validated | 2013-12-31 17:00 | 2013-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | design | 2013-12-02 08:00 | 2014-02-18 17:00 | 57d |  |  | 0 |  |  | 9825 |  | 31d | [5 empty] | 4725 |  | 46.92% |  | 4609.4999 | 9825
9 | design - MF | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h | Employee D | 150 | 0 | 0 | 0 | 150 | 2013-12-30 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
10 | design - MF | 2013-12-02 08:00 | 2013-12-03 15:00 | 1d 6h | Employee E | 1050 | 0 | 0 | 0 | 1050 | 2013-12-02 08:00 | 1d 6h | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 100% | Finished | 1050 | 1050 | 100 | 100 | 100 | 100 | 100 | 100
11 | design - MF | 2013-12-02 08:00 | 2013-12-20 10:00 | 14d 2h | Employee F | 8550 | 0 | 0 | 0 | 8550 | 2014-01-06 08:00 | 5d 6h | 3450 | 75 | 1h | 0 | 0 | 3450 | 75 | 39% | Started | 3334.4999 | 8550 | 100 | 40.3509 | 39 | 100 | 40.3509 | 39
12 | design - DWH | 2013-12-09 08:00 | 2013-12-09 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 2013-12-09 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
13 | design validated | 2014-02-18 17:00 | 2014-02-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | development | 2013-11-19 08:00 | 2014-02-28 17:00 | 74d |  |  | 0 |  |  | 16875 |  | 41d | [5 empty] | 4125 |  | 23.31% |  | 3933 | 16875
14 | development - coding MF | 2013-11-19 08:00 | 2013-12-13 17:00 | 19d | Employee G | 11400 | 0 | 0 | 0 | 11400 | 2014-01-06 08:00 | 5d 5h | 3375 | 1425 | 2d 3h | 0 | 0 | 3375 | 1425 | 28% | Started | 3192 | 11400 | 100 | 29.6053 | 28 | 100 | 29.6053 | 28
15 | development - coding MF | 2013-11-19 08:00 | 2013-11-28 14:00 | 7d 5h | Employee H | 4575 | 0 | 0 | 0 | 4575 | 2014-01-13 08:00 | 5h | 375 | 225 | 3h | 0 | 0 | 375 | 225 | 8% | Started | 366 | 4575 | 100 | 8.1967 | 8 | 100 | 8.1967 | 8
16 | development - coding MF | 2013-11-19 08:00 | 2013-11-19 14:00 | 5h | Employee E | 375 | 0 | 0 | 0 | 375 | 2013-11-18 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
17 | development - coding MF | 2013-11-19 08:00 | 2013-11-19 16:00 | 7h | Employee F | 525 | 0 | 0 | 0 | 525 |  | 0 | 0 | 525 | 7h | 0 | 0 | 0 | 525 | 0% | Not Started | 0 | 525 | 100 |  | 0 | 100 |  | 0
20 | development completed | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | development bugfixing | 2014-03-24 08:00 | 2014-03-26 11:00 | 2d 3h |  |  | 0 |  |  | 2250 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | development - bugfixing | 2014-03-24 08:00 | 2014-03-26 11:00 | 2d 3h | Employee G | 1425 | 0 | 0 | 0 | 1425 |  | 0 | 0 | 1425 | 2d 3h | 0 | 0 | 0 | 1425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | development - bugfixing | 2014-03-24 08:00 | 2014-03-25 11:00 | 1d 3h | Employee D | 825 | 0 | 0 | 0 | 825 |  | 0 | 0 | 825 | 1d 3h | 0 | 0 | 0 | 825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | post implementation | 2014-05-12 08:00 | 2014-05-13 16:00 | 1d 7h |  |  | 0 |  |  | 2325 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee A | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 16:00 | 1d 7h | Employee D | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-03-17 22:00 |  | TP Name | Tracking 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Receipt Numbering System | 2013-09-02 08:00 | 2014-05-13 16:00 | 181d 7h |  |  | 0 |  |  | 43800 |  | 141d | [5 empty] | 34470 |  | 84.45% |  | 36989.9999 | 39225
25 | supporting tasks | 2013-09-02 08:00 | 2013-11-29 17:00 | 65d |  |  | 0 |  |  | 11775 |  | 141d | [5 empty] | 6045 |  | 81.02% |  | 9539.9999 | 11775
1 | project management | 2013-09-02 08:00 | 2013-09-10 16:00 | 6d 7h | Employee I | 4950 | 0 | 0 | 0 | 4950 | 2013-09-02 08:00 | 3d 4h | 2520 | 90 | 1h | 0 | 0 | 2520 | 90 | 90% | Started | 4454.9999 | 4950 | 100 | 50.9091 | 90 | 100 | 50.9091 | 90
2 | validation and support | 2013-11-22 08:00 | 2013-11-25 16:00 | 1d 7h | Employee A | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 1125 | 100 |  | 0 | 100 |  | 0
3 | validation and support | 2013-11-22 08:00 | 2013-11-22 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
4 | validation and support | 2013-11-22 08:00 | 2013-11-29 17:00 | 6d | Employee D | 3600 | 0 | 0 | 0 | 3600 | 2013-11-18 08:00 | 4d 6h | 2850 | 0 | 0 | 0 | 0 | 2850 | 0 | 100% | Finished | 3600 | 3600 | 100 | 79.1667 | 100 | 100 | 79.1667 | 100
5 | validation and support | 2013-11-22 08:00 | 2013-11-26 12:00 | 2d 4h | Employee L | 1500 | 0 | 0 | 0 | 1500 | 2014-01-20 08:00 | 1d 1h | 675 | 225 | 3h | 0 | 0 | 675 | 225 | 99% | Started | 1485 | 1500 | 100 | 45 | 99 | 100 | 45 | 99
26 | analysis | 2013-09-06 08:00 | 2013-12-31 17:00 | 83d |  |  | 0 |  |  | 750 |  | 101d 7h | [5 empty] | 750 |  | 100% |  | 750 | 750
6 | analysis - conceptual design | 2013-09-06 08:00 | 2013-09-09 09:00 | 1d 1h | Employee A | 675 | 0 | 0 | 0 | 675 | 2013-09-06 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 675 | 675 | 100 | 100 | 100 | 100 | 100 | 100
7 | analysis - conceptual design | 2013-09-06 08:00 | 2013-09-06 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 | 2013-12-16 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
8 | analysis validated | 2013-12-31 17:00 | 2013-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-27 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
27 | design | 2013-12-02 08:00 | 2014-02-18 17:00 | 57d |  |  | 0 |  |  | 9825 |  | 55d 7h | [5 empty] | 10200 |  | 100% |  | 9825 | 9825
9 | design - MF | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h | Employee D | 150 | 0 | 0 | 0 | 150 | 2013-12-30 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
10 | design - MF | 2013-12-02 08:00 | 2013-12-03 15:00 | 1d 6h | Employee E | 1050 | 0 | 0 | 0 | 1050 | 2013-12-02 08:00 | 1d 6h | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 100% | Finished | 1050 | 1050 | 100 | 100 | 100 | 100 | 100 | 100
11 | design - MF | 2013-12-02 08:00 | 2013-12-20 10:00 | 14d 2h | Employee F | 8550 | 0 | 0 | 0 | 8550 | 2014-01-06 08:00 | 14d 7h | 8925 | 0 | 0 | 0 | 0 | 8925 | 0 | 100% | Finished | 8550 | 8550 | 100 | 104.386 | 100 | 100 | 104.386 | 100
12 | design - DWH | 2013-12-09 08:00 | 2013-12-09 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 2013-12-09 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
13 | design validated | 2014-02-18 17:00 | 2014-02-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-17 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
28 | development | 2013-11-19 08:00 | 2014-02-28 17:00 | 74d |  |  | 0 |  |  | 16875 |  | 56d 7h | [5 empty] | 17475 |  | 100% |  | 16875 | 16875
14 | development - coding MF | 2013-11-19 08:00 | 2013-12-13 17:00 | 19d | Employee G | 11400 | 0 | 0 | 0 | 11400 | 2014-01-06 08:00 | 20d | 12000 | 0 | 0 | 0 | 0 | 12000 | 0 | 100% | Finished | 11400 | 11400 | 100 | 105.2632 | 100 | 100 | 105.2632 | 100
15 | development - coding MF | 2013-11-19 08:00 | 2013-11-28 14:00 | 7d 5h | Employee H | 4575 | 0 | 0 | 0 | 4575 | 2014-01-13 08:00 | 7d 5h | 4575 | 0 | 0 | 0 | 0 | 4575 | 0 | 100% | Finished | 4575 | 4575 | 100 | 100 | 100 | 100 | 100 | 100
16 | development - coding MF | 2013-11-19 08:00 | 2013-11-19 14:00 | 5h | Employee E | 375 | 0 | 0 | 0 | 375 | 2013-11-18 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
17 | development - coding MF | 2013-11-19 08:00 | 2013-11-19 16:00 | 7h | Employee F | 525 | 0 | 0 | 0 | 525 | 2014-02-03 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
20 | development completed | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-04 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | development bugfixing | 2014-03-24 08:00 | 2014-03-26 11:00 | 2d 3h |  |  | 0 |  |  | 2250 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | development - bugfixing | 2014-03-24 08:00 | 2014-03-26 11:00 | 2d 3h | Employee G | 1425 | 0 | 0 | 0 | 1425 |  | 0 | 0 | 1425 | 2d 3h | 0 | 0 | 0 | 1425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | development - bugfixing | 2014-03-24 08:00 | 2014-03-25 11:00 | 1d 3h | Employee D | 825 | 0 | 0 | 0 | 825 |  | 0 | 0 | 825 | 1d 3h | 0 | 0 | 0 | 825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | post implementation | 2014-05-12 08:00 | 2014-05-13 16:00 | 1d 7h |  |  | 0 |  |  | 2325 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee A | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 16:00 | 1d 7h | Employee D | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2014-05-12 22:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Receipt Numbering System | 2013-09-02 08:00 | 2014-05-13 16:00 | 181d 7h |  |  | 0 |  |  | 43800 |  | 181d 7h | [5 empty] | 37530 |  | 96.06% |  | 42075 | 43275
25 | supporting tasks | 2013-09-02 08:00 | 2013-11-29 17:00 | 65d |  |  | 0 |  |  | 11775 |  | 181d | [5 empty] | 6480 |  | 85.35% |  | 10050 | 11775
1 | project management | 2013-09-02 08:00 | 2013-09-10 16:00 | 6d 7h | Employee I | 4950 | 0 | 0 | 0 | 4950 | 2013-09-02 08:00 | 4d | 2880 | 0 | 0 | 0 | 0 | 2880 | 0 | 100% | Finished | 4950 | 4950 | 100 | 58.1818 | 100 | 100 | 58.1818 | 100
2 | validation and support | 2013-11-22 08:00 | 2013-11-25 16:00 | 1d 7h | Employee A | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 1125 | 100 |  | 0 | 100 |  | 0
3 | validation and support | 2013-11-22 08:00 | 2013-11-22 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
4 | validation and support | 2013-11-22 08:00 | 2013-11-29 17:00 | 6d | Employee D | 3600 | 0 | 0 | 0 | 3600 | 2013-11-18 08:00 | 4d 6h | 2850 | 0 | 0 | 0 | 0 | 2850 | 0 | 100% | Finished | 3600 | 3600 | 100 | 79.1667 | 100 | 100 | 79.1667 | 100
5 | validation and support | 2013-11-22 08:00 | 2013-11-26 12:00 | 2d 4h | Employee L | 1500 | 0 | 0 | 0 | 1500 | 2014-01-20 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 1500 | 1500 | 100 | 50 | 100 | 100 | 50 | 100
26 | analysis | 2013-09-06 08:00 | 2013-12-31 17:00 | 83d |  |  | 0 |  |  | 750 |  | 101d 7h | [5 empty] | 750 |  | 100% |  | 750 | 750
6 | analysis - conceptual design | 2013-09-06 08:00 | 2013-09-09 09:00 | 1d 1h | Employee A | 675 | 0 | 0 | 0 | 675 | 2013-09-06 08:00 | 1d 1h | 675 | 0 | 0 | 0 | 0 | 675 | 0 | 100% | Finished | 675 | 675 | 100 | 100 | 100 | 100 | 100 | 100
7 | analysis - conceptual design | 2013-09-06 08:00 | 2013-09-06 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 | 2013-12-16 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
8 | analysis validated | 2013-12-31 17:00 | 2013-12-31 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-01-27 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
27 | design | 2013-12-02 08:00 | 2014-02-18 17:00 | 57d |  |  | 0 |  |  | 9825 |  | 55d 7h | [5 empty] | 10200 |  | 100% |  | 9825 | 9825
9 | design - MF | 2013-12-02 08:00 | 2013-12-02 10:00 | 2h | Employee D | 150 | 0 | 0 | 0 | 150 | 2013-12-30 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
10 | design - MF | 2013-12-02 08:00 | 2013-12-03 15:00 | 1d 6h | Employee E | 1050 | 0 | 0 | 0 | 1050 | 2013-12-02 08:00 | 1d 6h | 1050 | 0 | 0 | 0 | 0 | 1050 | 0 | 100% | Finished | 1050 | 1050 | 100 | 100 | 100 | 100 | 100 | 100
11 | design - MF | 2013-12-02 08:00 | 2013-12-20 10:00 | 14d 2h | Employee F | 8550 | 0 | 0 | 0 | 8550 | 2014-01-06 08:00 | 14d 7h | 8925 | 0 | 0 | 0 | 0 | 8925 | 0 | 100% | Finished | 8550 | 8550 | 100 | 104.386 | 100 | 100 | 104.386 | 100
12 | design - DWH | 2013-12-09 08:00 | 2013-12-09 09:00 | 1h | Employee C | 75 | 0 | 0 | 0 | 75 | 2013-12-09 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100 | 100 | 100 | 100 | 100 | 100
13 | design validated | 2014-02-18 17:00 | 2014-02-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-17 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
28 | development | 2013-11-19 08:00 | 2014-02-28 17:00 | 74d |  |  | 0 |  |  | 16875 |  | 56d 7h | [5 empty] | 17475 |  | 100% |  | 16875 | 16875
14 | development - coding MF | 2013-11-19 08:00 | 2013-12-13 17:00 | 19d | Employee G | 11400 | 0 | 0 | 0 | 11400 | 2014-01-06 08:00 | 20d | 12000 | 0 | 0 | 0 | 0 | 12000 | 0 | 100% | Finished | 11400 | 11400 | 100 | 105.2632 | 100 | 100 | 105.2632 | 100
15 | development - coding MF | 2013-11-19 08:00 | 2013-11-28 14:00 | 7d 5h | Employee H | 4575 | 0 | 0 | 0 | 4575 | 2014-01-13 08:00 | 7d 5h | 4575 | 0 | 0 | 0 | 0 | 4575 | 0 | 100% | Finished | 4575 | 4575 | 100 | 100 | 100 | 100 | 100 | 100
16 | development - coding MF | 2013-11-19 08:00 | 2013-11-19 14:00 | 5h | Employee E | 375 | 0 | 0 | 0 | 375 | 2013-11-18 08:00 | 5h | 375 | 0 | 0 | 0 | 0 | 375 | 0 | 100% | Finished | 375 | 375 | 100 | 100 | 100 | 100 | 100 | 100
17 | development - coding MF | 2013-11-19 08:00 | 2013-11-19 16:00 | 7h | Employee F | 525 | 0 | 0 | 0 | 525 | 2014-02-03 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
20 | development completed | 2014-02-28 17:00 | 2014-02-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-02-04 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
33 | development bugfixing | 2014-03-24 08:00 | 2014-03-26 11:00 | 2d 3h |  |  | 0 |  |  | 2250 |  | 6d 2h | [5 empty] | 825 |  | 100% |  | 2250 | 2250
32 | development - bugfixing | 2014-03-24 08:00 | 2014-03-26 11:00 | 2d 3h | Employee G | 1425 | 0 | 0 | 0 | 1425 | 2014-03-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1425 | 1425 | 100 | 5.2632 | 100 | 100 | 5.2632 | 100
31 | development - bugfixing | 2014-03-24 08:00 | 2014-03-25 11:00 | 1d 3h | Employee D | 825 | 0 | 0 | 0 | 825 | 2014-03-31 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 825 | 825 | 100 | 90.9091 | 100 | 100 | 90.9091 | 100
29 | implementation | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
24 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
30 | post implementation | 2014-05-12 08:00 | 2014-05-13 16:00 | 1d 7h |  |  | 0 |  |  | 2325 |  | 1d 7h | [5 empty] | 1800 |  | 100% |  | 2325 | 1800
21 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee A | 600 | 0 | 0 | 0 | 600 | 2014-05-12 08:00 | 1d | 600 | 0 | 0 | 0 | 0 | 600 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 100 | 100
22 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-12 17:00 | 1d | Employee G | 600 | 0 | 0 | 0 | 600 | 2014-05-12 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 600 | 600 | 100 | 12.5 | 100 | 100 | 12.5 | 100
23 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 16:00 | 1d 7h | Employee D | 1125 | 0 | 0 | 0 | 1125 | 2014-05-12 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 1125 | 600 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2013-09-02 08:00 | 2013-11-18 22:00 | 5700 | 1315.5 | 1035 | 2013-09-03 15:00 | -4384.5 | 23.08% | 280.5 | 127.1% | -54d 2h | 3.125% | 51.07% | 2014-06-09 09:00 | 2016-09-07 17:00 | 2016-01-15 17:00 | 2014-07-11 17:00 | 2016-09-07 17:00 | 2016-02-02 17:00 | 2014-07-29 09:00 | 2035-12-21 17:00 | 2031-04-07 17:00 | 43519.5 | 34460.6618 | 185118.355 | 1360539.0006 | 145866.8321 | 1070656.1786 | 41002.7517 | 42561.8258 | 0.03125 | 1.271 | 0.23079 | 0.51071 | -54.25 | 1.271 | 1 | 0.03125 | 1
Tracking 2 | 2013-11-18 22:00 | 2014-01-13 22:00 | 39225 | 14572.4998 | 13275 | 2013-11-25 10:00 | -24652.5002 | 37.15% | 1297.4998 | 109.8% | -35d 6h | 62.76% | 47.2% | 2014-10-03 10:00 | 2015-07-17 12:00 | 2015-05-18 17:00 | 2014-08-06 10:00 | 2015-07-17 12:00 | 2015-05-29 12:00 | 2014-07-02 14:00 | 2014-10-10 15:00 | 2014-09-17 12:00 | 42502.5002 | 39900.155 | 91947.068 | 59844.9588 | 84942.2992 | 55698.4834 | 43960.2271 | 42394.3825 | 0.6276 | 1.0977 | 0.37151 | 0.47196 | -35.75 | 1.0977 | 1 | 0.6276 | 1
Tracking 3 | 2014-01-13 22:00 | 2014-03-17 22:00 | 39225 | 36989.9999 | 34470 | 2013-12-16 12:00 | -2235.0001 | 94.3% | 2519.9999 | 107.3% | -65d 4h | 53.55% | 93.96% | 2014-05-27 09:00 | 2014-05-28 16:00 | 2014-05-09 15:00 | 2014-05-23 16:00 | 2014-05-28 16:00 | 2014-05-23 11:00 | 2014-08-13 11:00 | 2014-12-19 14:00 | 2014-12-02 09:00 | 41280.0001 | 40816.0585 | 41691.4721 | 47188.0134 | 41199.4984 | 46321.5795 | 40973.74 | 41522.7718 | 0.53546 | 1.0731 | 0.94302 | 0.93955 | -65.5 | 1.0731 | 1 | 0.53546 | 1
Closure | 2014-03-17 22:00 | 2014-05-12 22:00 | 43275 | 42075 | 37530 | 2014-05-12 10:00 | -1200 | 97.23% | 4545 | 112.1% | -6h | 99.59% | 95.89% | 2014-05-20 16:00 | 2014-05-20 17:00 | 2014-04-22 16:00 | 2014-05-20 16:00 | 2014-05-20 17:00 | 2014-05-20 11:00 | 2014-05-14 14:00 | 2014-05-14 14:00 | 2014-05-14 12:00 | 39255 | 39068.6631 | 39304.1979 | 39262.1775 | 39112.5465 | 39075.0653 | 39110.6306 | 39103.8279 | 0.99586 | 1.1211 | 0.97227 | 0.95886 | -0.75 | 1.1211 | 1 | 0.99586 | 1