## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Investment Product (2) | 1 |  |  | 2013-11-25 08:00 | 2014-05-13 12:00 | 121d 4h |  |  | 0 |  |  | 46920 | 169.1667
48 | supporting tasks | 1.1 |  |  | 2014-02-24 08:00 | 2014-03-18 10:00 | 16d 2h |  |  | 0 |  |  | 7095 | 22.0833
1 | project management | 1.1.1 |  | FS2;FS3;FS4;FS5;FS32;FS6 | 2014-02-24 08:00 | 2014-03-03 17:00 | 6d | Employee A | 4320 | 0 | 0 | 0 | 4320 | 7.375
2 | validation and support | 1.1.2 | 1FS |  | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee B | 600 | 0 | 0 | 0 | 600 | 0.375
3 | validation and support | 1.1.3 | 1FS |  | 2014-03-17 08:00 | 2014-03-18 10:00 | 1d 2h | Employee C | 750 | 0 | 0 | 0 | 750 | 1.0833
4 | validation and support | 1.1.4 | 1FS |  | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 0.16667
5 | validation and support | 1.1.5 | 1FS |  | 2014-03-17 08:00 | 2014-03-18 09:00 | 1d 1h | Employee F | 675 | 0 | 0 | 0 | 675 | 1.0417
32 | validation and support | 1.1.6 | 1FS |  | 2014-03-17 08:00 | 2014-03-17 15:00 | 6h | Employee D | 450 | 0 | 0 | 0 | 450 | 0.29167
49 | design | 1.2 |  |  | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  |  | 0 |  |  | 1125 | 11.375
6 | design - OMS | 1.2.1 | 1FS | FS7 | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 | 1.3333
7 | design validated | 1.2.2 | 6FS | FS41 | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
50 | begunstigingsclausules bank | 1.3 |  |  | 2013-11-25 08:00 | 2014-03-21 17:00 | 85d |  |  | 0 |  |  | 8100 | 116.375
8 | analyse | 1.3.1 |  | FS9;FS10 | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 | 0.375
9 | design front | 1.3.2 | 8FS | FS25;FS26;FS34 | 2014-02-18 08:00 | 2014-02-24 16:00 | 4d 7h | Employee F | 2925 | 0 | 0 | 0 | 2925 | 6.3333
10 | design mapping | 1.3.3 | 8FS | FS25;FS26;FS34 | 2014-02-18 08:00 | 2014-02-21 15:00 | 3d 6h | Employee C | 2250 | 0 | 0 | 0 | 2250 | 3.2917
25 | design extra velden | 1.3.4 | 9FS;10FS | FS27 | 2014-03-03 08:00 | 2014-03-03 14:00 | 5h | Employee C | 375 | 0 | 0 | 0 | 375 | 0.25
26 | uitbreiding extra velden | 1.3.5 | 9FS;10FS |  | 2014-03-03 08:00 | 2014-03-03 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 0.16667
27 | uitbreiding service extra velden | 1.3.6 | 25FS;34FS | FS28 | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee I | 150 | 0 | 0 | 0 | 150 | 0.083333
34 | uitbreiding extra velden | 1.3.7 | 9FS;10FS | FS27 | 2014-03-03 08:00 | 2014-03-05 12:00 | 2d 4h | Employee K | 1500 | 0 | 0 | 0 | 1500 | 2.1667
28 | uitbreiding rapportering completed | 1.3.8 | 27FS | FS41 | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
51 | elektronische handtekening | 1.4 |  |  | 2014-02-24 08:00 | 2014-04-30 17:00 | 48d |  |  | 0 |  |  | 10200 | 65.375
11 | build OMS | 1.4.1 |  | FS14;FS15 | 2014-02-26 08:00 | 2014-02-27 15:00 | 1d 6h | Employee G | 1050 | 0 | 0 | 0 | 1050 | 1.2917
12 | build progress | 1.4.2 |  | FS14;FS15 | 2014-02-24 08:00 | 2014-02-25 17:00 | 2d | Employee H | 1200 | 0 | 0 | 0 | 1200 | 1.375
13 | ICT test | 1.4.3 | 17FS | FS18 | 2014-04-07 08:00 | 2014-04-09 10:00 | 2d 2h | Employee I | 1350 | 0 | 0 | 0 | 1350 | 2.0833
14 | iPad: fixing blocking issues | 1.4.4 | 11FS;12FS | FS17 | 2014-03-05 08:00 | 2014-03-11 17:00 | 5d | Employee D | 3000 | 0 | 0 | 0 | 3000 | 6.375
15 | iPad: test iPad | 1.4.5 | 11FS;12FS | FS17 | 2014-03-10 08:00 | 2014-03-10 17:00 | 1d | Employee J | 600 | 0 | 0 | 0 | 600 | 0.375
17 | iPad: test ISP | 1.4.6 | 14FS;15FS | FS13 | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d | Employee I | 3000 | 0 | 0 | 0 | 3000 | 4.375
18 | Pod iPad completed | 1.4.7 | 13FS | FS41 | 2014-04-30 17:00 | 2014-04-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
52 | development | 1.5 |  |  | 2014-03-17 08:00 | 2014-03-28 17:00 | 10d |  |  | 0 |  |  | 8100 | 11.375
19 | build personal page | 1.5.1 |  | FS24 | 2014-03-17 08:00 | 2014-03-18 11:00 | 1d 3h | Employee B | 825 | 0 | 0 | 0 | 825 | 1.125
20 | build OMS | 1.5.2 |  | FS24 | 2014-03-17 08:00 | 2014-03-18 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 | 1.3333
21 | development - bugfixing | 1.5.3 |  | FS24 | 2014-03-17 08:00 | 2014-03-26 11:00 | 7d 3h | Employee B | 4425 | 0 | 0 | 0 | 4425 | 9.125
22 | development - bugfixing | 1.5.4 |  | FS24 | 2014-03-17 08:00 | 2014-03-19 14:00 | 2d 5h | Employee C | 1575 | 0 | 0 | 0 | 1575 | 2.25
33 | development - bugfixing | 1.5.5 |  | FS24 | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee E | 150 | 0 | 0 | 0 | 150 | 0.083333
24 | development completed | 1.5.6 | 19FS;20FS;21FS;22FS;33FS | FS41 | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
53 | test ict | 1.6 |  |  | 2013-11-25 08:00 | 2014-04-18 17:00 | 105d |  |  | 0 |  |  | 11400 | 144.375
29 | test ict - test coordination | 1.6.1 | 36FS | FS31 | 2014-02-27 08:00 | 2014-03-03 14:00 | 2d 5h | Employee M | 1575 | 0 | 0 | 0 | 1575 | 4.25
30 | test ict - test execution | 1.6.2 | 31FS | FS39 | 2014-03-31 08:00 | 2014-04-07 11:00 | 5d 3h | Employee N | 3225 | 0 | 0 | 0 | 3225 | 7.125
35 | test ict - test execution | 1.6.3 | 31FS | FS39 | 2014-03-31 08:00 | 2014-04-01 16:00 | 1d 7h | Employee O | 1125 | 0 | 0 | 0 | 1125 | 1.3333
31 | test ict - test preparation | 1.6.4 | 29FS | FS30;FS35 | 2014-03-10 08:00 | 2014-03-13 09:00 | 3d 1h | Employee N | 1875 | 0 | 0 | 0 | 1875 | 3.0417
36 | test ict - test support | 1.6.5 | 37FS;38FS | FS29 | 2014-02-21 08:00 | 2014-02-25 09:00 | 2d 1h | Employee F | 1275 | 0 | 0 | 0 | 1275 | 4.0417
37 | test ict - test uitvoering | 1.6.6 |  | FS36 | 2013-11-25 08:00 | 2013-11-27 17:00 | 3d | Employee O | 1800 | 0 | 0 | 0 | 1800 | 2.375
38 | test ict - test uitvoering | 1.6.7 |  | FS36 | 2013-11-25 08:00 | 2013-11-25 16:00 | 7h | Employee P | 525 | 0 | 0 | 0 | 525 | 0.33333
39 | test ict completed | 1.6.8 | 30FS;35FS | FS41 | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
54 | implementation | 1.7 |  |  | 2014-04-07 17:00 | 2014-05-09 17:00 | 24d |  |  | 0 |  |  | 0 | 32
40 | full handover | 1.7.1 |  | FS41 | 2014-04-07 17:00 | 2014-04-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
41 | go live | 1.7.2 | 7FS;28FS;18FS;24FS;39FS;40FS | FS47 | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
55 | post implementation | 1.8 |  |  | 2014-05-12 08:00 | 2014-05-13 12:00 | 1d 4h |  |  | 0 |  |  | 900 | 1.1667
47 | post implementation - post go live support | 1.8.1 | 41FS |  | 2014-05-12 08:00 | 2014-05-13 12:00 | 1d 4h | Employee G | 900 | 0 | 0 | 0 | 900 | 1.1667

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee A | Renewable | 1 | 0 | 90 | 1; | 4320
2 | Employee B | Renewable | 1 | 0 | 75 | 2;19;21; | 5850
3 | Employee C | Renewable | 1 | 0 | 75 | 3;10;25;22; | 4950
4 | Employee D | Renewable | 1 | 0 | 75 | 32;14; | 3450
5 | Employee E | Renewable | 1 | 0 | 75 | 4;8;33; | 1050
6 | Employee F | Renewable | 1 | 0 | 75 | 5;9;36; | 4875
7 | Employee G | Renewable | 1 | 0 | 75 | 6;11;20;47; | 4200
8 | Employee H | Renewable | 1 | 0 | 75 | 26;12; | 1500
9 | Employee I | Renewable | 1 | 0 | 75 | 27;13;17; | 4500
10 | Employee J | Renewable | 1 | 0 | 75 | 15; | 600
11 | Employee K | Renewable | 1 | 0 | 75 | 34; | 1500
12 | Employee L | Renewable | 1 | 0 | 75 |  | 0
13 | Employee M | Renewable | 1 | 0 | 75 | 29; | 1575
14 | Employee N | Renewable | 1 | 0 | 75 | 30;31; | 5100
15 | Employee O | Renewable | 1 | 0 | 75 | 35;37; | 2925
16 | Employee P | Renewable | 1 | 0 | 75 | 38; | 525

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Investment Product (2) | 972h |  |  |  |  | 99 | 100 | 101
48 | supporting tasks | 130h |  |  |  |  | 99 | 100 | 101
1 | project management | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | validation and support | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | validation and support | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | validation and support | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | validation and support | 9h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | validation and support | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | design | 80h |  |  |  |  | 99 | 100 | 101
6 | design - OMS | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | design validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | begunstigingsclausules bank | 680h |  |  |  |  | 99 | 100 | 101
8 | analyse | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | design front | 39h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | design mapping | 30h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | design extra velden | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | uitbreiding extra velden | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | uitbreiding service extra velden | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | uitbreiding extra velden | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | uitbreiding rapportering completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | elektronische handtekening | 384h |  |  |  |  | 99 | 100 | 101
11 | build OMS | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | build progress | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | ICT test | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | iPad: fixing blocking issues | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | iPad: test iPad | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | iPad: test ISP | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Pod iPad completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | development | 80h |  |  |  |  | 99 | 100 | 101
19 | build personal page | 11h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | build OMS | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | development - bugfixing | 59h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | development - bugfixing | 21h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | development - bugfixing | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | development completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | test ict | 840h |  |  |  |  | 99 | 100 | 101
29 | test ict - test coordination | 21h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | test ict - test execution | 43h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | test ict - test execution | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | test ict - test preparation | 25h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | test ict - test support | 17h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | test ict - test uitvoering | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | test ict - test uitvoering | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | test ict completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | implementation | 192h |  |  |  |  | 99 | 100 | 101
40 | full handover | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | go live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | post implementation | 12h |  |  |  |  | 99 | 100 | 101
47 | post implementation - post go live support | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2014-02-03 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Investment Product (2) | 2013-11-25 08:00 | 2014-05-13 12:00 | 121d 4h |  |  | 0 |  |  | 46920 |  | 51d | [5 empty] | 2325 |  | 4.955% |  | 2325 | 2925
48 | supporting tasks | 2014-02-24 08:00 | 2014-03-18 10:00 | 16d 2h |  |  | 0 |  |  | 7095 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
1 | project management | 2014-02-24 08:00 | 2014-03-03 17:00 | 6d | Employee A | 4320 | 0 | 0 | 0 | 4320 |  | 0 | 0 | 4320 | 6d | 0 | 0 | 0 | 4320 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | validation and support | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee B | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | validation and support | 2014-03-17 08:00 | 2014-03-18 10:00 | 1d 2h | Employee C | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | validation and support | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | validation and support | 2014-03-17 08:00 | 2014-03-18 09:00 | 1d 1h | Employee F | 675 | 0 | 0 | 0 | 675 |  | 0 | 0 | 675 | 1d 1h | 0 | 0 | 0 | 675 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | validation and support | 2014-03-17 08:00 | 2014-03-17 15:00 | 6h | Employee D | 450 | 0 | 0 | 0 | 450 |  | 0 | 0 | 450 | 6h | 0 | 0 | 0 | 450 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | design | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  |  | 0 |  |  | 1125 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
6 | design - OMS | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | design validated | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | begunstigingsclausules bank | 2013-11-25 08:00 | 2014-03-21 17:00 | 85d |  |  | 0 |  |  | 8100 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 600
8 | analyse | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
9 | design front | 2014-02-18 08:00 | 2014-02-24 16:00 | 4d 7h | Employee F | 2925 | 0 | 0 | 0 | 2925 |  | 0 | 0 | 2925 | 4d 7h | 0 | 0 | 0 | 2925 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | design mapping | 2014-02-18 08:00 | 2014-02-21 15:00 | 3d 6h | Employee C | 2250 | 0 | 0 | 0 | 2250 |  | 0 | 0 | 2250 | 3d 6h | 0 | 0 | 0 | 2250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | design extra velden | 2014-03-03 08:00 | 2014-03-03 14:00 | 5h | Employee C | 375 | 0 | 0 | 0 | 375 |  | 0 | 0 | 375 | 5h | 0 | 0 | 0 | 375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | uitbreiding extra velden | 2014-03-03 08:00 | 2014-03-03 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | uitbreiding service extra velden | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee I | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | uitbreiding extra velden | 2014-03-03 08:00 | 2014-03-05 12:00 | 2d 4h | Employee K | 1500 | 0 | 0 | 0 | 1500 |  | 0 | 0 | 1500 | 2d 4h | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | uitbreiding rapportering completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | elektronische handtekening | 2014-02-24 08:00 | 2014-04-30 17:00 | 48d |  |  | 0 |  |  | 10200 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
11 | build OMS | 2014-02-26 08:00 | 2014-02-27 15:00 | 1d 6h | Employee G | 1050 | 0 | 0 | 0 | 1050 |  | 0 | 0 | 1050 | 1d 6h | 0 | 0 | 0 | 1050 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | build progress | 2014-02-24 08:00 | 2014-02-25 17:00 | 2d | Employee H | 1200 | 0 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 2d | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | ICT test | 2014-04-07 08:00 | 2014-04-09 10:00 | 2d 2h | Employee I | 1350 | 0 | 0 | 0 | 1350 |  | 0 | 0 | 1350 | 2d 2h | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | iPad: fixing blocking issues | 2014-03-05 08:00 | 2014-03-11 17:00 | 5d | Employee D | 3000 | 0 | 0 | 0 | 3000 |  | 0 | 0 | 3000 | 5d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | iPad: test iPad | 2014-03-10 08:00 | 2014-03-10 17:00 | 1d | Employee J | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | iPad: test ISP | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d | Employee I | 3000 | 0 | 0 | 0 | 3000 |  | 0 | 0 | 3000 | 5d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Pod iPad completed | 2014-04-30 17:00 | 2014-04-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | development | 2014-03-17 08:00 | 2014-03-28 17:00 | 10d |  |  | 0 |  |  | 8100 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | build personal page | 2014-03-17 08:00 | 2014-03-18 11:00 | 1d 3h | Employee B | 825 | 0 | 0 | 0 | 825 |  | 0 | 0 | 825 | 1d 3h | 0 | 0 | 0 | 825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | build OMS | 2014-03-17 08:00 | 2014-03-18 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | development - bugfixing | 2014-03-17 08:00 | 2014-03-26 11:00 | 7d 3h | Employee B | 4425 | 0 | 0 | 0 | 4425 |  | 0 | 0 | 4425 | 7d 3h | 0 | 0 | 0 | 4425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | development - bugfixing | 2014-03-17 08:00 | 2014-03-19 14:00 | 2d 5h | Employee C | 1575 | 0 | 0 | 0 | 1575 |  | 0 | 0 | 1575 | 2d 5h | 0 | 0 | 0 | 1575 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | development - bugfixing | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee E | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | development completed | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | test ict | 2013-11-25 08:00 | 2014-04-18 17:00 | 105d |  |  | 0 |  |  | 11400 |  | 51d | [5 empty] | 2325 |  | 20.39% |  | 2325 | 2325
29 | test ict - test coordination | 2014-02-27 08:00 | 2014-03-03 14:00 | 2d 5h | Employee M | 1575 | 0 | 0 | 0 | 1575 |  | 0 | 0 | 1575 | 2d 5h | 0 | 0 | 0 | 1575 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | test ict - test execution | 2014-03-31 08:00 | 2014-04-07 11:00 | 5d 3h | Employee N | 3225 | 0 | 0 | 0 | 3225 |  | 0 | 0 | 3225 | 5d 3h | 0 | 0 | 0 | 3225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | test ict - test execution | 2014-03-31 08:00 | 2014-04-01 16:00 | 1d 7h | Employee O | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | test ict - test preparation | 2014-03-10 08:00 | 2014-03-13 09:00 | 3d 1h | Employee N | 1875 | 0 | 0 | 0 | 1875 |  | 0 | 0 | 1875 | 3d 1h | 0 | 0 | 0 | 1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | test ict - test support | 2014-02-21 08:00 | 2014-02-25 09:00 | 2d 1h | Employee F | 1275 | 0 | 0 | 0 | 1275 |  | 0 | 0 | 1275 | 2d 1h | 0 | 0 | 0 | 1275 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | test ict - test uitvoering | 2013-11-25 08:00 | 2013-11-27 17:00 | 3d | Employee O | 1800 | 0 | 0 | 0 | 1800 | 2014-01-27 08:00 | 3d | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 100% | Finished | 1800 | 1800 | 100 | 100 | 100 | 100 | 100 | 100
38 | test ict - test uitvoering | 2013-11-25 08:00 | 2013-11-25 16:00 | 7h | Employee P | 525 | 0 | 0 | 0 | 525 | 2013-11-25 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
39 | test ict completed | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | implementation | 2014-04-07 17:00 | 2014-05-09 17:00 | 24d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | full handover | 2014-04-07 17:00 | 2014-04-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | post implementation | 2014-05-12 08:00 | 2014-05-13 12:00 | 1d 4h |  |  | 0 |  |  | 900 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 12:00 | 1d 4h | Employee G | 900 | 0 | 0 | 0 | 900 |  | 0 | 0 | 900 | 1d 4h | 0 | 0 | 0 | 900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-03-10 22:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Investment Product (2) | 2013-11-25 08:00 | 2014-05-13 12:00 | 121d 4h |  |  | 0 |  |  | 46920 |  | 76d 4h | [5 empty] | 10845 |  | 34.9% |  | 16374.9 | 23895
48 | supporting tasks | 2014-02-24 08:00 | 2014-03-18 10:00 | 16d 2h |  |  | 0 |  |  | 7095 |  | 11d | [5 empty] | 720 |  | 7.307% |  | 518.4 | 4320
1 | project management | 2014-02-24 08:00 | 2014-03-03 17:00 | 6d | Employee A | 4320 | 0 | 0 | 0 | 4320 | 2014-02-24 08:00 | 1d | 720 | 3330 | 4d 5h | 0 | 0 | 720 | 3330 | 12% | Started | 518.4 | 4320 | 100 | 16.6667 | 12 | 100 | 16.6667 | 12
2 | validation and support | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee B | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | validation and support | 2014-03-17 08:00 | 2014-03-18 10:00 | 1d 2h | Employee C | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | validation and support | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 |  | 0 | 0 | 300 | 4h | 0 | 0 | 0 | 300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | validation and support | 2014-03-17 08:00 | 2014-03-18 09:00 | 1d 1h | Employee F | 675 | 0 | 0 | 0 | 675 |  | 0 | 0 | 675 | 1d 1h | 0 | 0 | 0 | 675 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | validation and support | 2014-03-17 08:00 | 2014-03-17 15:00 | 6h | Employee D | 450 | 0 | 0 | 0 | 450 |  | 0 | 0 | 450 | 6h | 0 | 0 | 0 | 450 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | design | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  |  | 0 |  |  | 1125 |  | 1d | [5 empty] | 525 |  | 100% |  | 1125 | 600
6 | design - OMS | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 | 2014-03-10 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 1125 | 600 | 100 | 46.6667 | 100 | 100 | 46.6667 | 100
7 | design validated | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | begunstigingsclausules bank | 2013-11-25 08:00 | 2014-03-21 17:00 | 85d |  |  | 0 |  |  | 8100 |  | 16d | [5 empty] | 3450 |  | 77.46% |  | 6274.5 | 7950
8 | analyse | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 | 2014-02-17 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 600 | 600 | 100 | 125 | 100 | 100 | 125 | 100
9 | design front | 2014-02-18 08:00 | 2014-02-24 16:00 | 4d 7h | Employee F | 2925 | 0 | 0 | 0 | 2925 | 2014-02-17 08:00 | 4d 1h | 2475 | 75 | 1h | 0 | 0 | 2475 | 75 | 94% | Started | 2749.5 | 2925 | 100 | 84.6154 | 94 | 100 | 84.6154 | 94
10 | design mapping | 2014-02-18 08:00 | 2014-02-21 15:00 | 3d 6h | Employee C | 2250 | 0 | 0 | 0 | 2250 | 2014-02-18 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 2250 | 2250 | 100 | 3.3333 | 100 | 100 | 3.3333 | 100
25 | design extra velden | 2014-03-03 08:00 | 2014-03-03 14:00 | 5h | Employee C | 375 | 0 | 0 | 0 | 375 | 2014-03-10 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 375 | 375 | 100 | 20 | 100 | 100 | 20 | 100
26 | uitbreiding extra velden | 2014-03-03 08:00 | 2014-03-03 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 2014-03-03 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 300 | 300 | 100 | 25 | 100 | 100 | 25 | 100
27 | uitbreiding service extra velden | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee I | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | uitbreiding extra velden | 2014-03-03 08:00 | 2014-03-05 12:00 | 2d 4h | Employee K | 1500 | 0 | 0 | 0 | 1500 |  | 0 | 0 | 1500 | 2d 4h | 0 | 0 | 0 | 1500 | 0% | Not Started | 0 | 1500 | 100 |  | 0 | 100 |  | 0
28 | uitbreiding rapportering completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | elektronische handtekening | 2014-02-24 08:00 | 2014-04-30 17:00 | 48d |  |  | 0 |  |  | 10200 |  | 11d | [5 empty] | 1800 |  | 28.76% |  | 2934 | 5250
11 | build OMS | 2014-02-26 08:00 | 2014-02-27 15:00 | 1d 6h | Employee G | 1050 | 0 | 0 | 0 | 1050 | 2014-02-24 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 1050 | 1050 | 100 | 21.4286 | 100 | 100 | 21.4286 | 100
12 | build progress | 2014-02-24 08:00 | 2014-02-25 17:00 | 2d | Employee H | 1200 | 0 | 0 | 0 | 1200 | 2014-02-24 08:00 | 1d 5h | 975 | 450 | 6h | 0 | 0 | 975 | 450 | 72% | Started | 864 | 1200 | 100 | 81.25 | 72 | 100 | 81.25 | 72
13 | ICT test | 2014-04-07 08:00 | 2014-04-09 10:00 | 2d 2h | Employee I | 1350 | 0 | 0 | 0 | 1350 |  | 0 | 0 | 1350 | 2d 2h | 0 | 0 | 0 | 1350 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | iPad: fixing blocking issues | 2014-03-05 08:00 | 2014-03-11 17:00 | 5d | Employee D | 3000 | 0 | 0 | 0 | 3000 | 2014-03-03 08:00 | 7h | 525 | 7875 | 13d 1h | 0 | 0 | 525 | 7875 | 14% | Started | 420 | 2400 | 100 | 17.5 | 14 | 100 | 17.5 | 14
15 | iPad: test iPad | 2014-03-10 08:00 | 2014-03-10 17:00 | 1d | Employee J | 600 | 0 | 0 | 0 | 600 | 2014-03-10 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 600 | 600 | 100 | 12.5 | 100 | 100 | 12.5 | 100
17 | iPad: test ISP | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d | Employee I | 3000 | 0 | 0 | 0 | 3000 |  | 0 | 0 | 3000 | 5d | 0 | 0 | 0 | 3000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Pod iPad completed | 2014-04-30 17:00 | 2014-04-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | development | 2014-03-17 08:00 | 2014-03-28 17:00 | 10d |  |  | 0 |  |  | 8100 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | build personal page | 2014-03-17 08:00 | 2014-03-18 11:00 | 1d 3h | Employee B | 825 | 0 | 0 | 0 | 825 |  | 0 | 0 | 825 | 1d 3h | 0 | 0 | 0 | 825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | build OMS | 2014-03-17 08:00 | 2014-03-18 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | development - bugfixing | 2014-03-17 08:00 | 2014-03-26 11:00 | 7d 3h | Employee B | 4425 | 0 | 0 | 0 | 4425 |  | 0 | 0 | 4425 | 7d 3h | 0 | 0 | 0 | 4425 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | development - bugfixing | 2014-03-17 08:00 | 2014-03-19 14:00 | 2d 5h | Employee C | 1575 | 0 | 0 | 0 | 1575 |  | 0 | 0 | 1575 | 2d 5h | 0 | 0 | 0 | 1575 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | development - bugfixing | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee E | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | development completed | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | test ict | 2013-11-25 08:00 | 2014-04-18 17:00 | 105d |  |  | 0 |  |  | 11400 |  | 76d | [5 empty] | 3450 |  | 40.55% |  | 4623 | 5775
29 | test ict - test coordination | 2014-02-27 08:00 | 2014-03-03 14:00 | 2d 5h | Employee M | 1575 | 0 | 0 | 0 | 1575 | 2014-02-24 08:00 | 5h | 375 | 1125 | 1d 7h | 0 | 0 | 375 | 1125 | 34% | Started | 535.5 | 1575 | 100 | 23.8095 | 34 | 100 | 23.8095 | 34
30 | test ict - test execution | 2014-03-31 08:00 | 2014-04-07 11:00 | 5d 3h | Employee N | 3225 | 0 | 0 | 0 | 3225 |  | 0 | 0 | 3225 | 5d 3h | 0 | 0 | 0 | 3225 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | test ict - test execution | 2014-03-31 08:00 | 2014-04-01 16:00 | 1d 7h | Employee O | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | test ict - test preparation | 2014-03-10 08:00 | 2014-03-13 09:00 | 3d 1h | Employee N | 1875 | 0 | 0 | 0 | 1875 | 2014-03-10 08:00 | 1d 1h | 675 | 1200 | 2d | 0 | 0 | 675 | 1200 | 26% | Started | 487.5 | 600 | 100 | 36 | 26 | 100 | 36 | 26
36 | test ict - test support | 2014-02-21 08:00 | 2014-02-25 09:00 | 2d 1h | Employee F | 1275 | 0 | 0 | 0 | 1275 | 2014-02-21 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1275 | 1275 | 100 | 5.8824 | 100 | 100 | 5.8824 | 100
37 | test ict - test uitvoering | 2013-11-25 08:00 | 2013-11-27 17:00 | 3d | Employee O | 1800 | 0 | 0 | 0 | 1800 | 2014-01-27 08:00 | 3d | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 100% | Finished | 1800 | 1800 | 100 | 100 | 100 | 100 | 100 | 100
38 | test ict - test uitvoering | 2013-11-25 08:00 | 2013-11-25 16:00 | 7h | Employee P | 525 | 0 | 0 | 0 | 525 | 2013-11-25 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
39 | test ict completed | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | implementation | 2014-04-07 17:00 | 2014-05-09 17:00 | 24d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | full handover | 2014-04-07 17:00 | 2014-04-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | post implementation | 2014-05-12 08:00 | 2014-05-13 12:00 | 1d 4h |  |  | 0 |  |  | 900 |  | 1d 4h | [5 empty] | 900 |  | 100% |  | 900 | 0
47 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 12:00 | 1d 4h | Employee G | 900 | 0 | 0 | 0 | 900 | 2014-03-10 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 900 | 0 | 100 | 100 | 100 | 100 | 100 | 100

## TP3
| TP Status Date | 2014-04-07 22:00 |  | TP Name | Tracking 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Investment Product (2) | 2013-11-25 08:00 | 2014-05-13 12:00 | 121d 4h |  |  | 0 |  |  | 46920 |  | 96d | [5 empty] | 27210 |  | 90.5% |  | 42464.2501 | 45270
48 | supporting tasks | 2014-02-24 08:00 | 2014-03-18 10:00 | 16d 2h |  |  | 0 |  |  | 7095 |  | 31d | [5 empty] | 4260 |  | 59.47% |  | 4219.5 | 7095
1 | project management | 2014-02-24 08:00 | 2014-03-03 17:00 | 6d | Employee A | 4320 | 0 | 0 | 0 | 4320 | 2014-02-24 08:00 | 4d 2h | 3060 | 990 | 1d 3h | 0 | 0 | 3060 | 990 | 55% | Started | 2376.0001 | 4320 | 100 | 70.8333 | 55 | 100 | 70.8333 | 55
2 | validation and support | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee B | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 600 | 600 | 100 | 12.5 | 100 | 100 | 12.5 | 100
3 | validation and support | 2014-03-17 08:00 | 2014-03-18 10:00 | 1d 2h | Employee C | 750 | 0 | 0 | 0 | 750 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 750 | 750 | 100 | 10 | 100 | 100 | 10 | 100
4 | validation and support | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2014-03-17 08:00 | 6h | 450 | 75 | 1h | 0 | 0 | 450 | 75 | 52% | Started | 156 | 300 | 100 | 150 | 52 | 100 | 150 | 52
5 | validation and support | 2014-03-17 08:00 | 2014-03-18 09:00 | 1d 1h | Employee F | 675 | 0 | 0 | 0 | 675 | 2014-03-24 08:00 | 1d | 600 | 3900 | 6d 4h | 0 | 0 | 600 | 3900 | 50% | Started | 337.5 | 675 | 100 | 88.8889 | 50 | 100 | 88.8889 | 50
32 | validation and support | 2014-03-17 08:00 | 2014-03-17 15:00 | 6h | Employee D | 450 | 0 | 0 | 0 | 450 |  | 0 | 0 | 450 | 6h | 0 | 0 | 0 | 450 | 0% | Not Started | 0 | 450 | 100 |  | 0 | 100 |  | 0
49 | design | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  |  | 0 |  |  | 1125 |  | 9d 7h | [5 empty] | 525 |  | 100% |  | 1125 | 1125
6 | design - OMS | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 | 2014-03-10 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 1125 | 1125 | 100 | 46.6667 | 100 | 100 | 46.6667 | 100
7 | design validated | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
50 | begunstigingsclausules bank | 2013-11-25 08:00 | 2014-03-21 17:00 | 85d |  |  | 0 |  |  | 8100 |  | 36d | [5 empty] | 4350 |  | 97.41% |  | 7890 | 8100
8 | analyse | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 | 2014-02-17 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 600 | 600 | 100 | 125 | 100 | 100 | 125 | 100
9 | design front | 2014-02-18 08:00 | 2014-02-24 16:00 | 4d 7h | Employee F | 2925 | 0 | 0 | 0 | 2925 | 2014-02-17 08:00 | 4d 3h | 2625 | 0 | 0 | 0 | 0 | 2625 | 0 | 100% | Finished | 2925 | 2925 | 100 | 89.7436 | 100 | 100 | 89.7436 | 100
10 | design mapping | 2014-02-18 08:00 | 2014-02-21 15:00 | 3d 6h | Employee C | 2250 | 0 | 0 | 0 | 2250 | 2014-02-18 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 2250 | 2250 | 100 | 3.3333 | 100 | 100 | 3.3333 | 100
25 | design extra velden | 2014-03-03 08:00 | 2014-03-03 14:00 | 5h | Employee C | 375 | 0 | 0 | 0 | 375 | 2014-03-10 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 375 | 375 | 100 | 20 | 100 | 100 | 20 | 100
26 | uitbreiding extra velden | 2014-03-03 08:00 | 2014-03-03 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 2014-03-03 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 300 | 300 | 100 | 25 | 100 | 100 | 25 | 100
27 | uitbreiding service extra velden | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee I | 150 | 0 | 0 | 0 | 150 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 150 | 150 | 100 | 50 | 100 | 100 | 50 | 100
34 | uitbreiding extra velden | 2014-03-03 08:00 | 2014-03-05 12:00 | 2d 4h | Employee K | 1500 | 0 | 0 | 0 | 1500 | 2014-03-17 08:00 | 1d 1h | 675 | 75 | 1h | 0 | 0 | 675 | 75 | 86% | Started | 1290 | 1500 | 100 | 45 | 86 | 100 | 45 | 86
28 | uitbreiding rapportering completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
51 | elektronische handtekening | 2014-02-24 08:00 | 2014-04-30 17:00 | 48d |  |  | 0 |  |  | 10200 |  | 31d | [5 empty] | 6300 |  | 89.12% |  | 9090 | 9450
11 | build OMS | 2014-02-26 08:00 | 2014-02-27 15:00 | 1d 6h | Employee G | 1050 | 0 | 0 | 0 | 1050 | 2014-02-24 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 1050 | 1050 | 100 | 21.4286 | 100 | 100 | 21.4286 | 100
12 | build progress | 2014-02-24 08:00 | 2014-02-25 17:00 | 2d | Employee H | 1200 | 0 | 0 | 0 | 1200 | 2014-02-24 08:00 | 2d 2h | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 100% | Finished | 1200 | 1200 | 100 | 112.5 | 100 | 100 | 112.5 | 100
13 | ICT test | 2014-04-07 08:00 | 2014-04-09 10:00 | 2d 2h | Employee I | 1350 | 0 | 0 | 0 | 1350 | 2014-04-07 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1350 | 600 | 100 | 5.5556 | 100 | 100 | 5.5556 | 100
14 | iPad: fixing blocking issues | 2014-03-05 08:00 | 2014-03-11 17:00 | 5d | Employee D | 3000 | 0 | 0 | 0 | 3000 | 2014-03-03 08:00 | 3d 7h | 2325 | 6075 | 10d 1h | 0 | 0 | 2325 | 6075 | 63% | Started | 1890 | 3000 | 100 | 77.5 | 63 | 100 | 77.5 | 63
15 | iPad: test iPad | 2014-03-10 08:00 | 2014-03-10 17:00 | 1d | Employee J | 600 | 0 | 0 | 0 | 600 | 2014-03-10 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 600 | 600 | 100 | 12.5 | 100 | 100 | 12.5 | 100
17 | iPad: test ISP | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d | Employee I | 3000 | 0 | 0 | 0 | 3000 | 2014-03-17 08:00 | 3d 6h | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 3000 | 3000 | 100 | 75 | 100 | 100 | 75 | 100
18 | Pod iPad completed | 2014-04-30 17:00 | 2014-04-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | development | 2014-03-17 08:00 | 2014-03-28 17:00 | 10d |  |  | 0 |  |  | 8100 |  | 16d | [5 empty] | 600 |  | 98.15% |  | 7950 | 8100
19 | build personal page | 2014-03-17 08:00 | 2014-03-18 11:00 | 1d 3h | Employee B | 825 | 0 | 0 | 0 | 825 | 2014-03-17 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 825 | 825 | 100 | 27.2727 | 100 | 100 | 27.2727 | 100
20 | build OMS | 2014-03-17 08:00 | 2014-03-18 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 | 2014-03-31 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 1125 | 1125 | 100 | 20 | 100 | 100 | 20 | 100
21 | development - bugfixing | 2014-03-17 08:00 | 2014-03-26 11:00 | 7d 3h | Employee B | 4425 | 0 | 0 | 0 | 4425 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 4425 | 4425 | 100 | 1.6949 | 100 | 100 | 1.6949 | 100
22 | development - bugfixing | 2014-03-17 08:00 | 2014-03-19 14:00 | 2d 5h | Employee C | 1575 | 0 | 0 | 0 | 1575 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1575 | 1575 | 100 | 4.7619 | 100 | 100 | 4.7619 | 100
33 | development - bugfixing | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee E | 150 | 0 | 0 | 0 | 150 |  | 0 | 0 | 150 | 2h | 0 | 0 | 0 | 150 | 0% | Not Started | 0 | 150 | 100 |  | 0 | 100 |  | 0
24 | development completed | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | test ict | 2013-11-25 08:00 | 2014-04-18 17:00 | 105d |  |  | 0 |  |  | 11400 |  | 96d | [5 empty] | 10275 |  | 99.03% |  | 11289.75 | 11400
29 | test ict - test coordination | 2014-02-27 08:00 | 2014-03-03 14:00 | 2d 5h | Employee M | 1575 | 0 | 0 | 0 | 1575 | 2014-02-24 08:00 | 1d 6h | 1050 | 450 | 6h | 0 | 0 | 1050 | 450 | 93% | Started | 1464.75 | 1575 | 100 | 66.6667 | 93 | 100 | 66.6667 | 93
30 | test ict - test execution | 2014-03-31 08:00 | 2014-04-07 11:00 | 5d 3h | Employee N | 3225 | 0 | 0 | 0 | 3225 | 2014-03-24 08:00 | 5d 1h | 3075 | 0 | 0 | 0 | 0 | 3075 | 0 | 100% | Finished | 3225 | 3225 | 100 | 95.3488 | 100 | 100 | 95.3488 | 100
35 | test ict - test execution | 2014-03-31 08:00 | 2014-04-01 16:00 | 1d 7h | Employee O | 1125 | 0 | 0 | 0 | 1125 | 2014-03-31 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 1125 | 1125 | 100 | 100 | 100 | 100 | 100 | 100
31 | test ict - test preparation | 2014-03-10 08:00 | 2014-03-13 09:00 | 3d 1h | Employee N | 1875 | 0 | 0 | 0 | 1875 | 2014-03-10 08:00 | 4d 3h | 2625 | 0 | 0 | 0 | 0 | 2625 | 0 | 100% | Finished | 1875 | 1875 | 100 | 140 | 100 | 100 | 140 | 100
36 | test ict - test support | 2014-02-21 08:00 | 2014-02-25 09:00 | 2d 1h | Employee F | 1275 | 0 | 0 | 0 | 1275 | 2014-02-21 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1275 | 1275 | 100 | 5.8824 | 100 | 100 | 5.8824 | 100
37 | test ict - test uitvoering | 2013-11-25 08:00 | 2013-11-27 17:00 | 3d | Employee O | 1800 | 0 | 0 | 0 | 1800 | 2014-01-27 08:00 | 3d | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 100% | Finished | 1800 | 1800 | 100 | 100 | 100 | 100 | 100 | 100
38 | test ict - test uitvoering | 2013-11-25 08:00 | 2013-11-25 16:00 | 7h | Employee P | 525 | 0 | 0 | 0 | 525 | 2013-11-25 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
39 | test ict completed | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | implementation | 2014-04-07 17:00 | 2014-05-09 17:00 | 24d |  |  | 0 |  |  | 0 |  | 1h | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | full handover | 2014-04-07 17:00 | 2014-04-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-07 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
41 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | post implementation | 2014-05-12 08:00 | 2014-05-13 12:00 | 1d 4h |  |  | 0 |  |  | 900 |  | 1d 4h | [5 empty] | 900 |  | 100% |  | 900 | 0
47 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 12:00 | 1d 4h | Employee G | 900 | 0 | 0 | 0 | 900 | 2014-03-10 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 900 | 0 | 100 | 100 | 100 | 100 | 100 | 100

## TP4
| TP Status Date | 2014-05-12 08:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Investment Product (2) | 2013-11-25 08:00 | 2014-05-13 12:00 | 121d 4h |  |  | 0 |  |  | 46920 |  | 119d 7h | [5 empty] | 32805 |  | 100% |  | 46920 | 46020
48 | supporting tasks | 2014-02-24 08:00 | 2014-03-18 10:00 | 16d 2h |  |  | 0 |  |  | 7095 |  | 35d 4h | [5 empty] | 8130 |  | 100% |  | 7095 | 7095
1 | project management | 2014-02-24 08:00 | 2014-03-03 17:00 | 6d | Employee A | 4320 | 0 | 0 | 0 | 4320 | 2014-02-24 08:00 | 7d 6h | 5580 | 0 | 0 | 0 | 0 | 5580 | 0 | 100% | Finished | 4320 | 4320 | 100 | 129.1667 | 100 | 100 | 129.1667 | 100
2 | validation and support | 2014-03-17 08:00 | 2014-03-17 17:00 | 1d | Employee B | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 600 | 600 | 100 | 12.5 | 100 | 100 | 12.5 | 100
3 | validation and support | 2014-03-17 08:00 | 2014-03-18 10:00 | 1d 2h | Employee C | 750 | 0 | 0 | 0 | 750 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 750 | 750 | 100 | 10 | 100 | 100 | 10 | 100
4 | validation and support | 2014-03-17 08:00 | 2014-03-17 12:00 | 4h | Employee E | 300 | 0 | 0 | 0 | 300 | 2014-03-17 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 300 | 300 | 100 | 300 | 100 | 100 | 300 | 100
5 | validation and support | 2014-03-17 08:00 | 2014-03-18 09:00 | 1d 1h | Employee F | 675 | 0 | 0 | 0 | 675 | 2014-03-24 08:00 | 2d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 675 | 675 | 100 | 177.7778 | 100 | 100 | 177.7778 | 100
32 | validation and support | 2014-03-17 08:00 | 2014-03-17 15:00 | 6h | Employee D | 450 | 0 | 0 | 0 | 450 | 2014-04-14 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 450 | 450 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
49 | design | 2014-03-10 08:00 | 2014-03-21 17:00 | 10d |  |  | 0 |  |  | 1125 |  | 9d 7h | [5 empty] | 525 |  | 100% |  | 1125 | 1125
6 | design - OMS | 2014-03-10 08:00 | 2014-03-11 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 | 2014-03-10 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 1125 | 1125 | 100 | 46.6667 | 100 | 100 | 46.6667 | 100
7 | design validated | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
50 | begunstigingsclausules bank | 2013-11-25 08:00 | 2014-03-21 17:00 | 85d |  |  | 0 |  |  | 8100 |  | 24d 7h | [5 empty] | 4500 |  | 100% |  | 8100 | 8100
8 | analyse | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d | Employee E | 600 | 0 | 0 | 0 | 600 | 2014-02-17 08:00 | 1d 2h | 750 | 0 | 0 | 0 | 0 | 750 | 0 | 100% | Finished | 600 | 600 | 100 | 125 | 100 | 100 | 125 | 100
9 | design front | 2014-02-18 08:00 | 2014-02-24 16:00 | 4d 7h | Employee F | 2925 | 0 | 0 | 0 | 2925 | 2014-02-17 08:00 | 4d 3h | 2625 | 0 | 0 | 0 | 0 | 2625 | 0 | 100% | Finished | 2925 | 2925 | 100 | 89.7436 | 100 | 100 | 89.7436 | 100
10 | design mapping | 2014-02-18 08:00 | 2014-02-21 15:00 | 3d 6h | Employee C | 2250 | 0 | 0 | 0 | 2250 | 2014-02-18 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 2250 | 2250 | 100 | 3.3333 | 100 | 100 | 3.3333 | 100
25 | design extra velden | 2014-03-03 08:00 | 2014-03-03 14:00 | 5h | Employee C | 375 | 0 | 0 | 0 | 375 | 2014-03-10 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 375 | 375 | 100 | 20 | 100 | 100 | 20 | 100
26 | uitbreiding extra velden | 2014-03-03 08:00 | 2014-03-03 12:00 | 4h | Employee H | 300 | 0 | 0 | 0 | 300 | 2014-03-03 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 300 | 300 | 100 | 25 | 100 | 100 | 25 | 100
27 | uitbreiding service extra velden | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee I | 150 | 0 | 0 | 0 | 150 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 150 | 150 | 100 | 50 | 100 | 100 | 50 | 100
34 | uitbreiding extra velden | 2014-03-03 08:00 | 2014-03-05 12:00 | 2d 4h | Employee K | 1500 | 0 | 0 | 0 | 1500 | 2014-03-17 08:00 | 1d 3h | 825 | 0 | 0 | 0 | 0 | 825 | 0 | 100% | Finished | 1500 | 1500 | 100 | 55 | 100 | 100 | 55 | 100
28 | uitbreiding rapportering completed | 2014-03-21 17:00 | 2014-03-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-03-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
51 | elektronische handtekening | 2014-02-24 08:00 | 2014-04-30 17:00 | 48d |  |  | 0 |  |  | 10200 |  | 47d 7h | [5 empty] | 7650 |  | 100% |  | 10200 | 10200
11 | build OMS | 2014-02-26 08:00 | 2014-02-27 15:00 | 1d 6h | Employee G | 1050 | 0 | 0 | 0 | 1050 | 2014-02-24 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 1050 | 1050 | 100 | 21.4286 | 100 | 100 | 21.4286 | 100
12 | build progress | 2014-02-24 08:00 | 2014-02-25 17:00 | 2d | Employee H | 1200 | 0 | 0 | 0 | 1200 | 2014-02-24 08:00 | 2d 2h | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 100% | Finished | 1200 | 1200 | 100 | 112.5 | 100 | 100 | 112.5 | 100
13 | ICT test | 2014-04-07 08:00 | 2014-04-09 10:00 | 2d 2h | Employee I | 1350 | 0 | 0 | 0 | 1350 | 2014-04-07 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1350 | 1350 | 100 | 5.5556 | 100 | 100 | 5.5556 | 100
14 | iPad: fixing blocking issues | 2014-03-05 08:00 | 2014-03-11 17:00 | 5d | Employee D | 3000 | 0 | 0 | 0 | 3000 | 2014-03-03 08:00 | 6d 1h | 3675 | 0 | 0 | 0 | 0 | 3675 | 0 | 100% | Finished | 3000 | 3000 | 100 | 122.5 | 100 | 100 | 122.5 | 100
15 | iPad: test iPad | 2014-03-10 08:00 | 2014-03-10 17:00 | 1d | Employee J | 600 | 0 | 0 | 0 | 600 | 2014-03-10 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 600 | 600 | 100 | 12.5 | 100 | 100 | 12.5 | 100
17 | iPad: test ISP | 2014-03-17 08:00 | 2014-03-21 17:00 | 5d | Employee I | 3000 | 0 | 0 | 0 | 3000 | 2014-03-17 08:00 | 3d 6h | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 3000 | 3000 | 100 | 75 | 100 | 100 | 75 | 100
18 | Pod iPad completed | 2014-04-30 17:00 | 2014-04-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-30 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | development | 2014-03-17 08:00 | 2014-03-28 17:00 | 10d |  |  | 0 |  |  | 8100 |  | 25d 7h | [5 empty] | 750 |  | 100% |  | 8100 | 8100
19 | build personal page | 2014-03-17 08:00 | 2014-03-18 11:00 | 1d 3h | Employee B | 825 | 0 | 0 | 0 | 825 | 2014-03-17 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 825 | 825 | 100 | 27.2727 | 100 | 100 | 27.2727 | 100
20 | build OMS | 2014-03-17 08:00 | 2014-03-18 16:00 | 1d 7h | Employee G | 1125 | 0 | 0 | 0 | 1125 | 2014-03-31 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 1125 | 1125 | 100 | 20 | 100 | 100 | 20 | 100
21 | development - bugfixing | 2014-03-17 08:00 | 2014-03-26 11:00 | 7d 3h | Employee B | 4425 | 0 | 0 | 0 | 4425 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 4425 | 4425 | 100 | 1.6949 | 100 | 100 | 1.6949 | 100
22 | development - bugfixing | 2014-03-17 08:00 | 2014-03-19 14:00 | 2d 5h | Employee C | 1575 | 0 | 0 | 0 | 1575 | 2014-03-17 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1575 | 1575 | 100 | 4.7619 | 100 | 100 | 4.7619 | 100
33 | development - bugfixing | 2014-03-17 08:00 | 2014-03-17 10:00 | 2h | Employee E | 150 | 0 | 0 | 0 | 150 | 2014-04-21 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100
24 | development completed | 2014-03-28 17:00 | 2014-03-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
53 | test ict | 2013-11-25 08:00 | 2014-04-18 17:00 | 105d |  |  | 0 |  |  | 11400 |  | 104d 7h | [5 empty] | 10350 |  | 100% |  | 11400 | 11400
29 | test ict - test coordination | 2014-02-27 08:00 | 2014-03-03 14:00 | 2d 5h | Employee M | 1575 | 0 | 0 | 0 | 1575 | 2014-02-24 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 1575 | 1575 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
30 | test ict - test execution | 2014-03-31 08:00 | 2014-04-07 11:00 | 5d 3h | Employee N | 3225 | 0 | 0 | 0 | 3225 | 2014-03-24 08:00 | 5d 1h | 3075 | 0 | 0 | 0 | 0 | 3075 | 0 | 100% | Finished | 3225 | 3225 | 100 | 95.3488 | 100 | 100 | 95.3488 | 100
35 | test ict - test execution | 2014-03-31 08:00 | 2014-04-01 16:00 | 1d 7h | Employee O | 1125 | 0 | 0 | 0 | 1125 | 2014-03-31 08:00 | 1d 7h | 1125 | 0 | 0 | 0 | 0 | 1125 | 0 | 100% | Finished | 1125 | 1125 | 100 | 100 | 100 | 100 | 100 | 100
31 | test ict - test preparation | 2014-03-10 08:00 | 2014-03-13 09:00 | 3d 1h | Employee N | 1875 | 0 | 0 | 0 | 1875 | 2014-03-10 08:00 | 4d 3h | 2625 | 0 | 0 | 0 | 0 | 2625 | 0 | 100% | Finished | 1875 | 1875 | 100 | 140 | 100 | 100 | 140 | 100
36 | test ict - test support | 2014-02-21 08:00 | 2014-02-25 09:00 | 2d 1h | Employee F | 1275 | 0 | 0 | 0 | 1275 | 2014-02-21 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1275 | 1275 | 100 | 5.8824 | 100 | 100 | 5.8824 | 100
37 | test ict - test uitvoering | 2013-11-25 08:00 | 2013-11-27 17:00 | 3d | Employee O | 1800 | 0 | 0 | 0 | 1800 | 2014-01-27 08:00 | 3d | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 100% | Finished | 1800 | 1800 | 100 | 100 | 100 | 100 | 100 | 100
38 | test ict - test uitvoering | 2013-11-25 08:00 | 2013-11-25 16:00 | 7h | Employee P | 525 | 0 | 0 | 0 | 525 | 2013-11-25 08:00 | 7h | 525 | 0 | 0 | 0 | 0 | 525 | 0 | 100% | Finished | 525 | 525 | 100 | 100 | 100 | 100 | 100 | 100
39 | test ict completed | 2014-04-18 17:00 | 2014-04-18 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-18 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
54 | implementation | 2014-04-07 17:00 | 2014-05-09 17:00 | 24d |  |  | 0 |  |  | 0 |  | 24d | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | full handover | 2014-04-07 17:00 | 2014-04-07 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-07 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
41 | go live | 2014-05-09 17:00 | 2014-05-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-09 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
55 | post implementation | 2014-05-12 08:00 | 2014-05-13 12:00 | 1d 4h |  |  | 0 |  |  | 900 |  | 1d 4h | [5 empty] | 900 |  | 100% |  | 900 | 0
47 | post implementation - post go live support | 2014-05-12 08:00 | 2014-05-13 12:00 | 1d 4h | Employee G | 900 | 0 | 0 | 0 | 900 | 2014-03-10 08:00 | 1d 4h | 900 | 0 | 0 | 0 | 0 | 900 | 0 | 100% | Finished | 900 | 0 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2013-11-25 08:00 | 2014-02-03 22:00 | 2925 | 2325 | 2325 | 2013-11-26 17:00 | -600 | 79.49% | 0 | 100% | -49d | 3.922% | 74.19% | 2014-05-14 17:00 | 2014-06-25 16:00 | 2014-06-25 16:00 | 2014-05-27 17:00 | 2014-06-25 16:00 | 2014-06-25 16:00 | 2014-07-21 12:00 | 2025-10-09 10:00 | 2025-10-09 10:00 | 46920 | 46920 | 58428.3871 | 1139497.5 | 58428.3871 | 1139497.5 | 48827.8075 | 57527.5485 | 0.039216 | 1 | 0.79487 | 0.74194 | -49 | 1 | 1 | 0.039216 | 1
Tracking 2 | 2014-02-03 22:00 | 2014-03-10 22:00 | 23895 | 16374.9 | 10845 | 2014-02-28 16:00 | -7520.1 | 68.53% | 5529.9 | 151% | -6d 1h | 91.94% | 74.83% | 2014-06-09 17:00 | 2014-07-30 10:00 | 2014-05-07 11:00 | 2014-06-16 11:00 | 2014-07-30 10:00 | 2014-06-12 09:00 | 2014-05-21 14:00 | 2014-05-28 09:00 | 2014-05-01 10:00 | 41390.1 | 31074.8401 | 55417.8013 | 44067.5775 | 40365.3042 | 32848.1177 | 33555.4548 | 32791.4072 | 0.91941 | 1.5099 | 0.68529 | 0.7483 | -6.125 | 1.5099 | 1 | 0.91941 | 1
Tracking 3 | 2014-03-10 22:00 | 2014-04-07 22:00 | 45270 | 42464.2501 | 27210 | 2014-04-01 15:00 | -2805.7499 | 93.8% | 15254.2501 | 156.1% | -4d 2h | 95.57% | 89.5% | 2014-05-22 15:00 | 2014-05-23 12:00 | 2014-03-19 17:00 | 2014-05-21 12:00 | 2014-05-23 12:00 | 2014-05-07 12:00 | 2014-05-19 15:00 | 2014-05-21 09:00 | 2014-05-05 17:00 | 31665.7499 | 30065.13 | 31960.1557 | 31872.1471 | 30253.7777 | 30197.384 | 30312.687 | 30305.0545 | 0.95573 | 1.5606 | 0.93802 | 0.89496 | -4.25 | 1.5606 | 1 | 0.95573 | 1
Closure | 2014-04-07 22:00 | 2014-05-12 08:00 | 46020 | 46920 | 32805 | 2014-05-13 12:00 | 900 | 102% | 14115 | 143% | 1d 4h | 101.2% | 100% | 2014-05-09 09:00 | 2014-05-09 09:00 | 2014-03-20 11:00 | 2014-05-09 09:00 | 2014-05-09 09:00 | 2014-05-09 11:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 2014-05-09 17:00 | 32805 | 32805 | 32805 | 32805 | 32805 | 32805 | 32805 | 32805 | 1.0125 | 1.4303 | 1.0196 | 1 | 1.5 | 1.4303 | 1 | 1.0125 | 1