## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Beer Tasting | 1 |  |  | 2014-04-07 08:00 | 2014-04-22 13:00 | 13d 5h |  |  | 200 |  |  | 1210 | 15.2083
21 | briefing | 1.1 |  |  | 2014-04-07 08:00 | 2014-04-07 10:00 | 2h |  |  | 0 |  |  | 110 | 0.083333
1 | briefing NL | 1.1.1 |  | FS3;FS4 | 2014-04-07 08:00 | 2014-04-07 09:00 | 1h | HR;Project Manager | 55 | 0 | 0 | 0 | 55 | 0.041667
2 | briefing FR | 1.1.2 |  | FS3;FS4 | 2014-04-07 09:00 | 2014-04-07 10:00 | 1h | HR;Project Manager | 55 | 0 | 0 | 0 | 55 | 0.041667
28 | voorbereiding | 1.2 |  |  | 2014-04-07 10:00 | 2014-04-09 20:00 | 2d 10h |  |  | 0 |  |  | 180 | 2.4167
3 | telechecks winkelpunt 1 | 1.2.1 | 2FS;1FS | FS19;FS9 | 2014-04-07 10:00 | 2014-04-07 13:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 0.125
4 | telechecks winkelpunt 2 | 1.2.2 | 2FS;1FS | FS19;FS9 | 2014-04-07 20:00 | 2014-04-08 10:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 0.58333
7 | levering degustatiemateriaal A | 1.2.3 |  | FS19;FS9 | 2014-04-08 20:00 | 2014-04-08 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0
8 | levering degustatiemateriaal B | 1.2.4 |  | FS19;FS9 | 2014-04-09 20:00 | 2014-04-09 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0
29 | degustatie vrijdag | 1.3 |  |  | 2014-04-11 09:00 | 2014-04-11 18:00 | 9h |  |  | 50 |  |  | 185 | 0.375
5 | VR aankomst + voorbereiding | 1.3.1 |  | FS19 | 2014-04-11 09:00 | 2014-04-11 10:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 0.041667
19 | VR degustatie | 1.3.2 | 5FS;3FS;4FS;7FS;8FS | FS6 | 2014-04-11 10:00 | 2014-04-11 17:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 | 0.29167
6 | VR opkuis + vertrek | 1.3.3 | 19FS | FS11;FS12 | 2014-04-11 17:00 | 2014-04-11 18:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 0.041667
30 | degustatie zaterdag | 1.4 |  |  | 2014-04-12 08:00 | 2014-04-12 17:00 | 9h |  |  | 50 |  |  | 185 | 0.375
20 | ZA aankomst + voorbereiding | 1.4.1 |  | FS9 | 2014-04-12 08:00 | 2014-04-12 09:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 0.041667
9 | ZA degustatie | 1.4.2 | 20FS;3FS;4FS;7FS;8FS | FS10 | 2014-04-12 09:00 | 2014-04-12 16:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 | 0.29167
10 | ZA opkuis + vertrek | 1.4.3 | 9FS | FS11;FS12 | 2014-04-12 16:00 | 2014-04-12 17:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 0.041667
34 | afsluiting | 1.5 |  |  | 2014-04-14 13:00 | 2014-04-15 13:00 | 1d |  |  | 0 |  |  | 0 | 1
11 | ophaling degustatiemateriaal A | 1.5.1 | 6FS;10FS |  | 2014-04-14 13:00 | 2014-04-14 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0
12 | ophaling degustatiemateriaal B | 1.5.2 | 6FS;10FS |  | 2014-04-15 13:00 | 2014-04-15 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0
31 | voorbereiding | 1.6 |  |  | 2014-04-12 20:00 | 2014-04-16 20:00 | 3d |  |  | 0 |  |  | 180 | 4
13 | telechecks winkelpunt 3 | 1.6.1 |  | FS18;FS24 | 2014-04-12 20:00 | 2014-04-14 10:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 1.5833
14 | telechecks winkelpunt 4 | 1.6.2 |  | FS18;FS24 | 2014-04-14 20:00 | 2014-04-15 10:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 0.58333
15 | levering degustatiemateriaal C | 1.6.3 |  | FS18;FS24 | 2014-04-15 20:00 | 2014-04-15 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0
16 | levering degustatiemateriaal D | 1.6.4 |  | FS18;FS24 | 2014-04-16 20:00 | 2014-04-16 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0
32 | degustatie vrijdag | 1.7 |  |  | 2014-04-18 09:00 | 2014-04-18 18:00 | 9h |  |  | 50 |  |  | 185 | 0.375
17 | VR aankomst + voorbereiding | 1.7.1 |  | FS18 | 2014-04-18 09:00 | 2014-04-18 10:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 0.041667
18 | VR degustatie | 1.7.2 | 13FS;14FS;15FS;16FS;17FS | FS22 | 2014-04-18 10:00 | 2014-04-18 17:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 | 0.29167
22 | VR opkuis + vertrek | 1.7.3 | 18FS | FS26;FS27 | 2014-04-18 17:00 | 2014-04-18 18:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 0.041667
33 | degustatie zaterdag | 1.8 |  |  | 2014-04-19 08:00 | 2014-04-19 17:00 | 9h |  |  | 50 |  |  | 185 | 0.375
23 | ZA aankomst + voorbereiding | 1.8.1 |  | FS24 | 2014-04-19 08:00 | 2014-04-19 09:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 0.041667
24 | ZA degustatie | 1.8.2 | 13FS;14FS;15FS;16FS;23FS | FS25 | 2014-04-19 09:00 | 2014-04-19 16:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 | 0.29167
25 | ZA opkuis + vertrek | 1.8.3 | 24FS | FS26;FS27 | 2014-04-19 16:00 | 2014-04-19 17:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 0.041667
35 | afsluiting | 1.9 |  |  | 2014-04-21 13:00 | 2014-04-22 13:00 | 1d |  |  | 0 |  |  | 0 | 1
26 | ophaling degustatiemateriaal C | 1.9.1 | 22FS;25FS |  | 2014-04-21 13:00 | 2014-04-21 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0
27 | ophaling degustatiemateriaal D | 1.9.2 | 22FS;25FS |  | 2014-04-22 13:00 | 2014-04-22 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Account Manager | Renewable | 1 | 0 | 25 |  | 0
2 | Project Manager | Renewable | 1 | 0 | 30 | 1;2;3;4;13;14; | 420
3 | Animator | Renewable | 1 | 0 | 15 | 5;19;6;20;9;10;17;18;22;23;24;25; | 540
4 | HR | Renewable | 1 | 0 | 25 | 1;2; | 50

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Beer Tasting | 174h |  |  |  |  | 99 | 100 | 101
21 | briefing | 2h |  |  |  |  | 99 | 100 | 101
1 | briefing NL | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | briefing FR | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | voorbereiding | 36h |  |  |  |  | 99 | 100 | 101
3 | telechecks winkelpunt 1 | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | telechecks winkelpunt 2 | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | levering degustatiemateriaal A | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | levering degustatiemateriaal B | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | degustatie vrijdag | 9h |  |  |  |  | 99 | 100 | 101
5 | VR aankomst + voorbereiding | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | VR degustatie | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | VR opkuis + vertrek | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | degustatie zaterdag | 9h |  |  |  |  | 99 | 100 | 101
20 | ZA aankomst + voorbereiding | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | ZA degustatie | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | ZA opkuis + vertrek | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | afsluiting | 13h |  |  |  |  | 99 | 100 | 101
11 | ophaling degustatiemateriaal A | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | ophaling degustatiemateriaal B | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | voorbereiding | 39h |  |  |  |  | 99 | 100 | 101
13 | telechecks winkelpunt 3 | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | telechecks winkelpunt 4 | 3h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | levering degustatiemateriaal C | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | levering degustatiemateriaal D | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | degustatie vrijdag | 9h |  |  |  |  | 99 | 100 | 101
17 | VR aankomst + voorbereiding | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | VR degustatie | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | VR opkuis + vertrek | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | degustatie zaterdag | 9h |  |  |  |  | 99 | 100 | 101
23 | ZA aankomst + voorbereiding | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | ZA degustatie | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | ZA opkuis + vertrek | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | afsluiting | 13h |  |  |  |  | 99 | 100 | 101
26 | ophaling degustatiemateriaal C | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | ophaling degustatiemateriaal D | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2014-04-11 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Beer Tasting | 2014-04-07 08:00 | 2014-04-22 13:00 | 13d 5h |  |  | 200 |  |  | 1210 |  | 5d | [5 empty] | 745 |  | 39.26% |  | 475 | 475
21 | briefing | 2014-04-07 08:00 | 2014-04-07 10:00 | 2h |  |  | 0 |  |  | 110 |  | 2h | [5 empty] | 110 |  | 100% |  | 110 | 110
1 | briefing NL | 2014-04-07 08:00 | 2014-04-07 09:00 | 1h | HR;Project Manager | 55 | 0 | 0 | 0 | 55 | 2014-04-07 08:00 | 1h | 55 | 0 | 0 | 0 | 0 | 55 | 0 | 100% | Finished | 55 | 55 | 100 | 100 | 100 | 100 | 100 | 100
2 | briefing FR | 2014-04-07 09:00 | 2014-04-07 10:00 | 1h | HR;Project Manager | 55 | 0 | 0 | 0 | 55 | 2014-04-07 09:00 | 1h | 55 | 0 | 0 | 0 | 0 | 55 | 0 | 100% | Finished | 55 | 55 | 100 | 100 | 100 | 100 | 100 | 100
28 | voorbereiding | 2014-04-07 10:00 | 2014-04-09 20:00 | 2d 10h |  |  | 0 |  |  | 180 |  | 2d 10h | [5 empty] | 480 |  | 100% |  | 180 | 180
3 | telechecks winkelpunt 1 | 2014-04-07 10:00 | 2014-04-07 13:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 2014-04-07 10:00 | 8h | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 90 | 90 | 100 | 266.6667 | 100 | 100 | 266.6667 | 100
4 | telechecks winkelpunt 2 | 2014-04-07 20:00 | 2014-04-08 10:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 2014-04-07 20:00 | 8h | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 90 | 90 | 100 | 266.6667 | 100 | 100 | 266.6667 | 100
7 | levering degustatiemateriaal A | 2014-04-08 20:00 | 2014-04-08 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-08 20:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | levering degustatiemateriaal B | 2014-04-09 20:00 | 2014-04-09 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-09 20:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
29 | degustatie vrijdag | 2014-04-11 09:00 | 2014-04-11 18:00 | 9h |  |  | 50 |  |  | 185 |  | 11h | [5 empty] | 155 |  | 100% |  | 185 | 185
5 | VR aankomst + voorbereiding | 2014-04-11 09:00 | 2014-04-11 10:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-11 09:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
19 | VR degustatie | 2014-04-11 10:00 | 2014-04-11 17:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 | 2014-04-11 15:00 | 5h | 125 | 0 | 0 | 0 | 0 | 125 | 0 | 100% | Finished | 155 | 155 | 100 | 71.4286 | 100 | 100 | 80.6452 | 100
6 | VR opkuis + vertrek | 2014-04-11 17:00 | 2014-04-11 18:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-11 17:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
30 | degustatie zaterdag | 2014-04-12 08:00 | 2014-04-12 17:00 | 9h |  |  | 50 |  |  | 185 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | ZA aankomst + voorbereiding | 2014-04-12 08:00 | 2014-04-12 09:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 |  | 0 | 0 | 15 | 1h | 0 | 0 | 0 | 15 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | ZA degustatie | 2014-04-12 09:00 | 2014-04-12 16:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 |  | 0 | 0 | 155 | 7h | 0 | 0 | 0 | 155 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | ZA opkuis + vertrek | 2014-04-12 16:00 | 2014-04-12 17:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 |  | 0 | 0 | 15 | 1h | 0 | 0 | 0 | 15 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | afsluiting | 2014-04-14 13:00 | 2014-04-15 13:00 | 1d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
11 | ophaling degustatiemateriaal A | 2014-04-14 13:00 | 2014-04-14 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | ophaling degustatiemateriaal B | 2014-04-15 13:00 | 2014-04-15 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | voorbereiding | 2014-04-12 20:00 | 2014-04-16 20:00 | 3d |  |  | 0 |  |  | 180 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
13 | telechecks winkelpunt 3 | 2014-04-12 20:00 | 2014-04-14 10:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 |  | 0 | 0 | 90 | 3h | 0 | 0 | 0 | 90 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | telechecks winkelpunt 4 | 2014-04-14 20:00 | 2014-04-15 10:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 |  | 0 | 0 | 90 | 3h | 0 | 0 | 0 | 90 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | levering degustatiemateriaal C | 2014-04-15 20:00 | 2014-04-15 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | levering degustatiemateriaal D | 2014-04-16 20:00 | 2014-04-16 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | degustatie vrijdag | 2014-04-18 09:00 | 2014-04-18 18:00 | 9h |  |  | 50 |  |  | 185 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | VR aankomst + voorbereiding | 2014-04-18 09:00 | 2014-04-18 10:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 |  | 0 | 0 | 15 | 1h | 0 | 0 | 0 | 15 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | VR degustatie | 2014-04-18 10:00 | 2014-04-18 17:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 |  | 0 | 0 | 155 | 7h | 0 | 0 | 0 | 155 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | VR opkuis + vertrek | 2014-04-18 17:00 | 2014-04-18 18:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 |  | 0 | 0 | 15 | 1h | 0 | 0 | 0 | 15 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | degustatie zaterdag | 2014-04-19 08:00 | 2014-04-19 17:00 | 9h |  |  | 50 |  |  | 185 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | ZA aankomst + voorbereiding | 2014-04-19 08:00 | 2014-04-19 09:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 |  | 0 | 0 | 15 | 1h | 0 | 0 | 0 | 15 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | ZA degustatie | 2014-04-19 09:00 | 2014-04-19 16:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 |  | 0 | 0 | 155 | 7h | 0 | 0 | 0 | 155 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | ZA opkuis + vertrek | 2014-04-19 16:00 | 2014-04-19 17:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 |  | 0 | 0 | 15 | 1h | 0 | 0 | 0 | 15 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | afsluiting | 2014-04-21 13:00 | 2014-04-22 13:00 | 1d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | ophaling degustatiemateriaal C | 2014-04-21 13:00 | 2014-04-21 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | ophaling degustatiemateriaal D | 2014-04-22 13:00 | 2014-04-22 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-04-18 22:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Beer Tasting | 2014-04-07 08:00 | 2014-04-22 13:00 | 13d 5h |  |  | 200 |  |  | 1210 |  | 11d | [5 empty] | 1595 |  | 84.71% |  | 1025 | 1025
21 | briefing | 2014-04-07 08:00 | 2014-04-07 10:00 | 2h |  |  | 0 |  |  | 110 |  | 2h | [5 empty] | 110 |  | 100% |  | 110 | 110
1 | briefing NL | 2014-04-07 08:00 | 2014-04-07 09:00 | 1h | HR;Project Manager | 55 | 0 | 0 | 0 | 55 | 2014-04-07 08:00 | 1h | 55 | 0 | 0 | 0 | 0 | 55 | 0 | 100% | Finished | 55 | 55 | 100 | 100 | 100 | 100 | 100 | 100
2 | briefing FR | 2014-04-07 09:00 | 2014-04-07 10:00 | 1h | HR;Project Manager | 55 | 0 | 0 | 0 | 55 | 2014-04-07 09:00 | 1h | 55 | 0 | 0 | 0 | 0 | 55 | 0 | 100% | Finished | 55 | 55 | 100 | 100 | 100 | 100 | 100 | 100
28 | voorbereiding | 2014-04-07 10:00 | 2014-04-09 20:00 | 2d 10h |  |  | 0 |  |  | 180 |  | 2d 10h | [5 empty] | 480 |  | 100% |  | 180 | 180
3 | telechecks winkelpunt 1 | 2014-04-07 10:00 | 2014-04-07 13:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 2014-04-07 10:00 | 8h | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 90 | 90 | 100 | 266.6667 | 100 | 100 | 266.6667 | 100
4 | telechecks winkelpunt 2 | 2014-04-07 20:00 | 2014-04-08 10:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 2014-04-07 20:00 | 8h | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 90 | 90 | 100 | 266.6667 | 100 | 100 | 266.6667 | 100
7 | levering degustatiemateriaal A | 2014-04-08 20:00 | 2014-04-08 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-08 20:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | levering degustatiemateriaal B | 2014-04-09 20:00 | 2014-04-09 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-09 20:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
29 | degustatie vrijdag | 2014-04-11 09:00 | 2014-04-11 18:00 | 9h |  |  | 50 |  |  | 185 |  | 11h | [5 empty] | 155 |  | 100% |  | 185 | 185
5 | VR aankomst + voorbereiding | 2014-04-11 09:00 | 2014-04-11 10:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-11 09:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
19 | VR degustatie | 2014-04-11 10:00 | 2014-04-11 17:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 | 2014-04-11 15:00 | 5h | 125 | 0 | 0 | 0 | 0 | 125 | 0 | 100% | Finished | 155 | 155 | 100 | 71.4286 | 100 | 100 | 80.6452 | 100
6 | VR opkuis + vertrek | 2014-04-11 17:00 | 2014-04-11 18:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-11 17:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
30 | degustatie zaterdag | 2014-04-12 08:00 | 2014-04-12 17:00 | 9h |  |  | 50 |  |  | 185 |  | 9h | [5 empty] | 185 |  | 100% |  | 185 | 185
20 | ZA aankomst + voorbereiding | 2014-04-12 08:00 | 2014-04-12 09:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-12 08:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
9 | ZA degustatie | 2014-04-12 09:00 | 2014-04-12 16:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 | 2014-04-12 09:00 | 7h | 155 | 0 | 0 | 0 | 0 | 155 | 0 | 100% | Finished | 155 | 155 | 100 | 100 | 100 | 100 | 100 | 100
10 | ZA opkuis + vertrek | 2014-04-12 16:00 | 2014-04-12 17:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-12 16:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
34 | afsluiting | 2014-04-14 13:00 | 2014-04-15 13:00 | 1d |  |  | 0 |  |  | 0 |  | 1d | [5 empty] | 0 |  | 0% |  | 0 | 0
11 | ophaling degustatiemateriaal A | 2014-04-14 13:00 | 2014-04-14 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-14 13:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
12 | ophaling degustatiemateriaal B | 2014-04-15 13:00 | 2014-04-15 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-15 13:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
31 | voorbereiding | 2014-04-12 20:00 | 2014-04-16 20:00 | 3d |  |  | 0 |  |  | 180 |  | 3d | [5 empty] | 480 |  | 100% |  | 180 | 180
13 | telechecks winkelpunt 3 | 2014-04-12 20:00 | 2014-04-14 10:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 2014-04-12 20:00 | 8h | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 90 | 90 | 100 | 266.6667 | 100 | 100 | 266.6667 | 100
14 | telechecks winkelpunt 4 | 2014-04-14 20:00 | 2014-04-15 10:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 2014-04-14 10:00 | 8h | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 90 | 90 | 100 | 266.6667 | 100 | 100 | 266.6667 | 100
15 | levering degustatiemateriaal C | 2014-04-15 20:00 | 2014-04-15 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-15 20:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
16 | levering degustatiemateriaal D | 2014-04-16 20:00 | 2014-04-16 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-16 20:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
32 | degustatie vrijdag | 2014-04-18 09:00 | 2014-04-18 18:00 | 9h |  |  | 50 |  |  | 185 |  | 11h | [5 empty] | 185 |  | 100% |  | 185 | 185
17 | VR aankomst + voorbereiding | 2014-04-18 09:00 | 2014-04-18 10:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-18 09:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
18 | VR degustatie | 2014-04-18 10:00 | 2014-04-18 17:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 | 2014-04-18 13:00 | 7h | 155 | 0 | 0 | 0 | 0 | 155 | 0 | 100% | Finished | 155 | 155 | 100 | 100 | 100 | 100 | 100 | 100
22 | VR opkuis + vertrek | 2014-04-18 17:00 | 2014-04-18 18:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-18 17:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
33 | degustatie zaterdag | 2014-04-19 08:00 | 2014-04-19 17:00 | 9h |  |  | 50 |  |  | 185 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | ZA aankomst + voorbereiding | 2014-04-19 08:00 | 2014-04-19 09:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 |  | 0 | 0 | 15 | 1h | 0 | 0 | 0 | 15 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | ZA degustatie | 2014-04-19 09:00 | 2014-04-19 16:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 |  | 0 | 0 | 155 | 7h | 0 | 0 | 0 | 155 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | ZA opkuis + vertrek | 2014-04-19 16:00 | 2014-04-19 17:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 |  | 0 | 0 | 15 | 1h | 0 | 0 | 0 | 15 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | afsluiting | 2014-04-21 13:00 | 2014-04-22 13:00 | 1d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | ophaling degustatiemateriaal C | 2014-04-21 13:00 | 2014-04-21 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | ophaling degustatiemateriaal D | 2014-04-22 13:00 | 2014-04-22 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-04-22 22:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Beer Tasting | 2014-04-07 08:00 | 2014-04-22 13:00 | 13d 5h |  |  | 200 |  |  | 1210 |  | 13d 5h | [5 empty] | 1780 |  | 100% |  | 1210 | 1210
21 | briefing | 2014-04-07 08:00 | 2014-04-07 10:00 | 2h |  |  | 0 |  |  | 110 |  | 2h | [5 empty] | 110 |  | 100% |  | 110 | 110
1 | briefing NL | 2014-04-07 08:00 | 2014-04-07 09:00 | 1h | HR;Project Manager | 55 | 0 | 0 | 0 | 55 | 2014-04-07 08:00 | 1h | 55 | 0 | 0 | 0 | 0 | 55 | 0 | 100% | Finished | 55 | 55 | 100 | 100 | 100 | 100 | 100 | 100
2 | briefing FR | 2014-04-07 09:00 | 2014-04-07 10:00 | 1h | HR;Project Manager | 55 | 0 | 0 | 0 | 55 | 2014-04-07 09:00 | 1h | 55 | 0 | 0 | 0 | 0 | 55 | 0 | 100% | Finished | 55 | 55 | 100 | 100 | 100 | 100 | 100 | 100
28 | voorbereiding | 2014-04-07 10:00 | 2014-04-09 20:00 | 2d 10h |  |  | 0 |  |  | 180 |  | 2d 10h | [5 empty] | 480 |  | 100% |  | 180 | 180
3 | telechecks winkelpunt 1 | 2014-04-07 10:00 | 2014-04-07 13:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 2014-04-07 10:00 | 8h | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 90 | 90 | 100 | 266.6667 | 100 | 100 | 266.6667 | 100
4 | telechecks winkelpunt 2 | 2014-04-07 20:00 | 2014-04-08 10:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 2014-04-07 20:00 | 8h | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 90 | 90 | 100 | 266.6667 | 100 | 100 | 266.6667 | 100
7 | levering degustatiemateriaal A | 2014-04-08 20:00 | 2014-04-08 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-08 20:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | levering degustatiemateriaal B | 2014-04-09 20:00 | 2014-04-09 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-09 20:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
29 | degustatie vrijdag | 2014-04-11 09:00 | 2014-04-11 18:00 | 9h |  |  | 50 |  |  | 185 |  | 11h | [5 empty] | 155 |  | 100% |  | 185 | 185
5 | VR aankomst + voorbereiding | 2014-04-11 09:00 | 2014-04-11 10:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-11 09:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
19 | VR degustatie | 2014-04-11 10:00 | 2014-04-11 17:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 | 2014-04-11 15:00 | 5h | 125 | 0 | 0 | 0 | 0 | 125 | 0 | 100% | Finished | 155 | 155 | 100 | 71.4286 | 100 | 100 | 80.6452 | 100
6 | VR opkuis + vertrek | 2014-04-11 17:00 | 2014-04-11 18:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-11 17:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
30 | degustatie zaterdag | 2014-04-12 08:00 | 2014-04-12 17:00 | 9h |  |  | 50 |  |  | 185 |  | 9h | [5 empty] | 185 |  | 100% |  | 185 | 185
20 | ZA aankomst + voorbereiding | 2014-04-12 08:00 | 2014-04-12 09:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-12 08:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
9 | ZA degustatie | 2014-04-12 09:00 | 2014-04-12 16:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 | 2014-04-12 09:00 | 7h | 155 | 0 | 0 | 0 | 0 | 155 | 0 | 100% | Finished | 155 | 155 | 100 | 100 | 100 | 100 | 100 | 100
10 | ZA opkuis + vertrek | 2014-04-12 16:00 | 2014-04-12 17:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-12 16:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
34 | afsluiting | 2014-04-14 13:00 | 2014-04-15 13:00 | 1d |  |  | 0 |  |  | 0 |  | 1d | [5 empty] | 0 |  | 0% |  | 0 | 0
11 | ophaling degustatiemateriaal A | 2014-04-14 13:00 | 2014-04-14 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-14 13:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
12 | ophaling degustatiemateriaal B | 2014-04-15 13:00 | 2014-04-15 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-15 13:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
31 | voorbereiding | 2014-04-12 20:00 | 2014-04-16 20:00 | 3d |  |  | 0 |  |  | 180 |  | 3d | [5 empty] | 480 |  | 100% |  | 180 | 180
13 | telechecks winkelpunt 3 | 2014-04-12 20:00 | 2014-04-14 10:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 2014-04-12 20:00 | 8h | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 90 | 90 | 100 | 266.6667 | 100 | 100 | 266.6667 | 100
14 | telechecks winkelpunt 4 | 2014-04-14 20:00 | 2014-04-15 10:00 | 3h | Project Manager | 90 | 0 | 0 | 0 | 90 | 2014-04-14 10:00 | 8h | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 90 | 90 | 100 | 266.6667 | 100 | 100 | 266.6667 | 100
15 | levering degustatiemateriaal C | 2014-04-15 20:00 | 2014-04-15 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-15 20:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
16 | levering degustatiemateriaal D | 2014-04-16 20:00 | 2014-04-16 20:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-16 20:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
32 | degustatie vrijdag | 2014-04-18 09:00 | 2014-04-18 18:00 | 9h |  |  | 50 |  |  | 185 |  | 11h | [5 empty] | 185 |  | 100% |  | 185 | 185
17 | VR aankomst + voorbereiding | 2014-04-18 09:00 | 2014-04-18 10:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-18 09:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
18 | VR degustatie | 2014-04-18 10:00 | 2014-04-18 17:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 | 2014-04-18 13:00 | 7h | 155 | 0 | 0 | 0 | 0 | 155 | 0 | 100% | Finished | 155 | 155 | 100 | 100 | 100 | 100 | 100 | 100
22 | VR opkuis + vertrek | 2014-04-18 17:00 | 2014-04-18 18:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-18 17:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
33 | degustatie zaterdag | 2014-04-19 08:00 | 2014-04-19 17:00 | 9h |  |  | 50 |  |  | 185 |  | 9h | [5 empty] | 185 |  | 100% |  | 185 | 185
23 | ZA aankomst + voorbereiding | 2014-04-19 08:00 | 2014-04-19 09:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-19 08:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
24 | ZA degustatie | 2014-04-19 09:00 | 2014-04-19 16:00 | 7h | Animator | 105 | 50 | 0 | 0 | 155 | 2014-04-19 09:00 | 7h | 155 | 0 | 0 | 0 | 0 | 155 | 0 | 100% | Finished | 155 | 155 | 100 | 100 | 100 | 100 | 100 | 100
25 | ZA opkuis + vertrek | 2014-04-19 16:00 | 2014-04-19 17:00 | 1h | Animator | 15 | 0 | 0 | 0 | 15 | 2014-04-19 16:00 | 1h | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 100% | Finished | 15 | 15 | 100 | 100 | 100 | 100 | 100 | 100
35 | afsluiting | 2014-04-21 13:00 | 2014-04-22 13:00 | 1d |  |  | 0 |  |  | 0 |  | 1d | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | ophaling degustatiemateriaal C | 2014-04-21 13:00 | 2014-04-21 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-21 13:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
27 | ophaling degustatiemateriaal D | 2014-04-22 13:00 | 2014-04-22 13:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-22 13:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | Yes
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | Yes
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | Yes
18:00 - 19:00 | Yes
19:00 - 20:00 | Yes
20:00 - 21:00 | Yes
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2014-04-07 08:00 | 2014-04-11 22:00 | 475 | 475 | 745 | 2014-04-11 21:00 | 0 | 100% | -270 | 63.76% | 0 | 100% | 100% | 2014-04-22 13:00 | 2014-04-22 13:00 | 2014-04-30 21:00 | 2014-04-22 13:00 | 2014-04-22 13:00 | 2014-04-28 10:00 | 2014-04-22 13:00 | 2014-04-22 13:00 | 2014-04-28 10:00 | 1480 | 1897.7895 | 1480 | 1480 | 1897.7895 | 1897.7895 | 1780.1134 | 1780.1134 | 1 | 0.63758 | 1 | 1 | 0 | 0.63758 | 1 | 1 | 1
Tracking 2 | 2014-04-11 22:00 | 2014-04-18 22:00 | 1025 | 1025 | 1595 | 2014-04-18 21:00 | 0 | 100% | -570 | 64.26% | 0 | 100% | 100% | 2014-04-22 13:00 | 2014-04-22 13:00 | 2014-04-30 19:00 | 2014-04-22 13:00 | 2014-04-22 13:00 | 2014-04-23 17:00 | 2014-04-22 13:00 | 2014-04-22 13:00 | 2014-04-23 17:00 | 1780 | 1882.878 | 1780 | 1780 | 1882.878 | 1882.878 | 1854.065 | 1854.065 | 1 | 0.64263 | 1 | 1 | 0 | 0.64263 | 1 | 1 | 1
Closure | 2014-04-18 22:00 | 2014-04-22 22:00 | 1210 | 1210 | 1780 | 2014-04-22 13:00 | 0 | 100% | -570 | 67.98% | -8h | 95.6% | 100% | 2014-04-22 13:00 | 2014-04-22 13:00 | 2014-04-29 17:00 | 2014-04-22 21:00 | 2014-04-22 21:00 | 2014-04-22 21:00 | 2014-04-22 21:00 | 2014-04-22 21:00 | 2014-04-22 21:00 | 1780 | 1780 | 1780 | 1780 | 1780 | 1780 | 1780 | 1780 | 0.95604 | 0.67978 | 1 | 1 | -0.61538 | 0.67978 | 1 | 0.95604 | 1