## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Data Loss Prevention System | 1 |  |  | 2013-04-10 08:00 | 2014-01-07 17:00 | 195d |  |  | 0 |  |  | 584951.7689 | 272.375
1 | MS Kick off meeting | 1.1 |  | FS3 | 2013-04-10 08:00 | 2013-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
2 | DLP workshop | 1.2 |  | FS3;FS9;FS23;FS37;FS52;FS66;FS84 | 2013-04-15 08:00 | 2013-04-15 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 0.375
3 | study existing documentation | 1.3 | 2FS;1FS | FS9 | 2013-04-16 08:00 | 2013-04-22 17:00 | 5d |  | 0 | 0 | 408.6 | 16344.0002 | 16344.0002 | 6.375
120 | Milestones | 1.4 |  |  | 2013-05-03 17:00 | 2013-12-30 17:00 | 171d |  |  | 0 |  |  | 0 | 241
4 | MS Start specific design | 1.4.1 |  |  | 2013-05-03 17:00 | 2013-05-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
5 | MS testing start | 1.4.2 |  |  | 2013-07-05 17:00 | 2013-07-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
6 | MS testing end | 1.4.3 |  |  | 2013-09-13 17:00 | 2013-09-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
7 | MS Deployment start | 1.4.4 |  |  | 2013-09-30 17:00 | 2013-09-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
8 | MS Deployment end | 1.4.5 |  |  | 2013-12-30 17:00 | 2013-12-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
121 | A. DLP Strategy | 1.5 |  |  | 2013-05-10 08:00 | 2013-07-24 17:00 | 54d |  |  | 0 |  |  | 67010.401 | 75.375
9 | Define DLP Strategy output | 1.5.1 | 2FS;3FS | FS10 | 2013-05-10 08:00 | 2013-05-10 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 0.375
10 | Initial DLP Strategy workshop | 1.5.2 | 9FS | FS11 | 2013-05-16 08:00 | 2013-05-20 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 4.375
129 | DLP Strategy Document writing | 1.5.3 |  |  | 2013-05-21 08:00 | 2013-06-18 17:00 | 21d |  |  | 0 |  |  | 31053.6005 | 28.375
11 | A.1 Technical and Organizational inputs | 1.5.3.1 | 10FS | FS12 | 2013-05-21 08:00 | 2013-05-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
12 | A.2 Data loss/leakage prevention Strategy | 1.5.3.2 | 11FS | FS13 | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
15 | Follow-up DLP Strategy workshop | 1.5.3.3 | 14FS | FS16;FS17;FS18;FS19 | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 4.375
13 | A.3 Proposed optimization of the need of information sharing and portability | 1.5.3.4 | 12FS | FS14 | 2013-06-10 08:00 | 2013-06-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
14 | A.4 Overarching technical policies | 1.5.3.5 | 13FS | FS15 | 2013-06-12 08:00 | 2013-06-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
130 | DLP Strategy Document writing | 1.5.4 |  |  | 2013-06-21 08:00 | 2013-06-26 17:00 | 4d |  |  | 0 |  |  | 13075.2002 | 5.375
16 | A.1 Technical and Organizational inputs | 1.5.4.1 | 15FS |  | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 3.375
17 | A.2 Data loss/leakage prevention Strategy | 1.5.4.2 | 15FS |  | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 3.375
18 | A.3 Proposed optimization of the need of information sharing and portability | 1.5.4.3 | 15FS |  | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
19 | A.4 Overarching technical policies | 1.5.4.4 | 15FS | FS20 | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
20 | DLP Strategy Document review | 1.5.5 | 19FS | FS21 | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 6.375
21 | DLP Strategy Fix document | 1.5.6 | 20FS | FS22 | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 6.375
22 | DLP Strategy approval | 1.5.7 | 21FS |  | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 13.375
122 | B. High level implementation plan | 1.6 |  |  | 2013-05-09 08:00 | 2013-07-24 17:00 | 55d |  |  | 0 |  |  | 67010.401 | 76.375
23 | Define HL Implementation plan output | 1.6.1 | 2FS | FS24 | 2013-05-09 08:00 | 2013-05-09 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 0.375
24 | Initial HL Implementation plan workshop | 1.6.2 | 23FS | FS25 | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2.375
131 | HL Implementation plan Document writing | 1.6.3 |  |  | 2013-05-23 08:00 | 2013-06-03 17:00 | 8d |  |  | 0 |  |  | 26150.4004 | 11.375
25 | B.1 Roadmap towards a full DLP implementation | 1.6.3.1 | 24FS | FS26 | 2013-05-23 08:00 | 2013-05-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
26 | B.2 Communication plan to stakeholders | 1.6.3.2 | 25FS | FS27 | 2013-05-27 08:00 | 2013-05-28 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
27 | B.3 integration in exisiting architecture | 1.6.3.3 | 26FS | FS28 | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
28 | B.4 Security controls for the enforcement of the policy | 1.6.3.4 | 27FS | FS29 | 2013-05-31 08:00 | 2013-06-03 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 3.375
29 | Follow-up HL Implementation plan workshop | 1.6.4 | 28FS | FS30;FS31;FS32;FS33 | 2013-06-12 08:00 | 2013-06-14 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2.375
132 | HL Implementation plan Document writing | 1.6.5 |  |  | 2013-06-17 08:00 | 2013-06-20 17:00 | 4d |  |  | 0 |  |  | 13075.2002 | 3.375
30 | B.1 Roadmap towards a full DLP implementation | 1.6.5.1 | 29FS |  | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
31 | B.2 Communication plan to stakeholders | 1.6.5.2 | 29FS |  | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
32 | B.3 integration in existing architecture | 1.6.5.3 | 29FS |  | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
33 | B.4 Security controls for the enforcement of the policy | 1.6.5.4 | 29FS | FS34 | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
34 | HL Implementation plan Document review | 1.6.6 | 33FS | FS35 | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 6.375
35 | HL Implementation plan Fix document | 1.6.7 | 34FS | FS36 | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 6.375
36 | HL Implementation plan approval | 1.6.8 | 35FS |  | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 13.375
123 | D. Technical directives | 1.7 |  |  | 2013-06-27 08:00 | 2013-09-10 17:00 | 54d |  |  | 0 |  |  | 67010.401 | 75.375
37 | Define Technical directives output | 1.7.1 | 2FS | FS38 | 2013-06-27 08:00 | 2013-06-27 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 0.375
38 | Initial Technical directives workshop | 1.7.2 | 37FS | FS39;FS40;FS41;FS42 | 2013-06-28 08:00 | 2013-07-02 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 4.375
133 | Technical directives Document writing | 1.7.3 |  |  | 2013-07-03 08:00 | 2013-07-18 17:00 | 12d |  |  | 0 |  |  | 22881.6003 | 15.375
39 | D.1 Device/Port control rules | 1.7.3.1 | 38FS | FS44 | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 0.375
40 | D.2 DLP rules | 1.7.3.2 | 38FS | FS44 | 2013-07-09 08:00 | 2013-07-10 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
41 | D.3 Encryption rules | 1.7.3.3 | 38FS | FS44 | 2013-07-17 08:00 | 2013-07-18 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
42 | D.4 Use-cases Device Control & DLP Encryption | 1.7.3.4 | 38FS | FS44 | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
43 | Rule set v1 | 1.7.4 |  |  | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 0.375
44 | Follow-up Technical directives workshop | 1.7.5 | 39FS;40FS;41FS;42FS | FS45;FS46;FS48;FS47 | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 4.375
134 | Technical directives Document writing | 1.7.6 |  |  | 2013-07-24 08:00 | 2013-07-26 17:00 | 3d |  |  | 0 |  |  | 13075.2002 | 2.375
45 | D.1 Device /Port control rules | 1.7.6.1 | 44FS | FS49 | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
46 | D.2 DLP rules | 1.7.6.2 | 44FS | FS49 | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
47 | D.3 Encryption rules | 1.7.6.3 | 44FS | FS49 | 2013-07-25 08:00 | 2013-07-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
48 | D.4 Use-cases Device Control & DLP Encryption | 1.7.6.4 | 44FS | FS49 | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
49 | Technical directives Document review | 1.7.7 | 45FS;46FS;47FS;48FS | FS50 | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 4.375
50 | Technical directives Fix document | 1.7.8 | 49FS | FS51 | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 4.375
51 | Technical directives approval | 1.7.9 | 50FS |  | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 13.375
124 | C. High Level Solution Design for Data Tagging and Information Classification | 1.8 |  |  | 2013-05-03 08:00 | 2013-09-10 17:00 | 93d |  |  | 0 |  |  | 67010.401 | 130.375
52 | Define Data tagging HL Solution output | 1.8.1 | 2FS |  | 2013-07-04 08:00 | 2013-07-04 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 0.375
53 | Initial Data tagging HL Solution workshop | 1.8.2 |  | FS54;FS55;FS56;FS57 | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 4.375
135 | DLP Data tagging HL Solution Document writing | 1.8.3 |  |  | 2013-07-26 08:00 | 2013-08-06 17:00 | 8d |  |  | 0 |  |  | 26150.4004 | 11.375
54 | C.1 High-level solution design | 1.8.3.1 | 53FS | FS58 | 2013-07-26 08:00 | 2013-07-29 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 3.375
55 | C.2 Organization & Roles | 1.8.3.2 | 53FS | FS58 | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
56 | C.3 Discovery of Classified Information | 1.8.3.3 | 53FS | FS61 | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
57 | C.4 Control for tagging and classification | 1.8.3.4 | 53FS | FS58 | 2013-08-05 08:00 | 2013-08-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
58 | Follow-up Data tagging HL Solution workshop | 1.8.4 | 54FS;55FS;57FS | FS59;FS62 | 2013-08-07 08:00 | 2013-08-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2.375
136 | DLP Data tagging HL Solution Document writing | 1.8.5 |  |  | 2013-05-03 08:00 | 2013-08-13 17:00 | 73d |  |  | 0 |  |  | 13075.2002 | 102.375
59 | C.1 High-level solution design | 1.8.5.1 | 58FS | FS63 | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
60 | C.2 Organization & Roles | 1.8.5.2 |  | FS63 | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 3.375
61 | C.3 Discovery of Classified Information | 1.8.5.3 | 56FS | FS63 | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
62 | C.4 Control for tagging and classification | 1.8.5.4 | 58FS | FS63 | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
63 | DLP Data tagging HL Solution Document review | 1.8.6 | 59FS;60FS;61FS;62FS | FS64 | 2013-08-14 08:00 | 2013-08-20 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 6.375
64 | DLP Data tagging HL Solution Fix document | 1.8.7 | 63FS | FS65 | 2013-08-21 08:00 | 2013-08-27 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 6.375
65 | DLP Data tagging HL Solution approval | 1.8.8 | 64FS |  | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 13.375
125 | H. Migration Strategy and a high level Implementation Package | 1.9 |  |  | 2013-05-03 08:00 | 2013-11-12 17:00 | 138d |  |  | 0 |  |  | 97737.1215 | 193.375
66 | Define Migration Strategy output | 1.9.1 | 2FS | FS67 | 2013-08-20 08:00 | 2013-08-20 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 0.375
67 | Initial Migration Strategy workshop | 1.9.2 | 66FS |  | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2.375
137 | Migration Strategy Document writing | 1.9.3 |  |  | 2013-05-03 08:00 | 2013-09-23 17:00 | 102d |  |  | 0 |  |  | 39225.6006 | 143.375
68 | H.1 Preparation guide | 1.9.3.1 |  | FS74 | 2013-09-10 08:00 | 2013-09-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
69 | H.2 Installation guide | 1.9.3.2 |  |  | 2013-09-12 08:00 | 2013-09-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
70 | H.5 Uninstallation guide | 1.9.3.3 |  |  | 2013-09-16 08:00 | 2013-09-17 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
71 | H.6 Training Needs Analysis | 1.9.3.4 |  | FS74 | 2013-09-18 08:00 | 2013-09-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
72 | H.7 Dashboards | 1.9.3.5 |  | FS74 | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 3.375
73 | H.8 Measurement Methods | 1.9.3.6 |  | FS74 | 2013-09-20 08:00 | 2013-09-23 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 3.375
74 | Follow-up Migration Strategy workshop | 1.9.4 | 68FS;71FS;72FS;73FS | FS75;FS76;FS77;FS78;FS80 | 2013-09-30 08:00 | 2013-10-02 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2.375
138 | Migration Strategy Document writing | 1.9.5 |  |  | 2013-05-07 08:00 | 2013-10-08 17:00 | 111d |  |  | 0 |  |  | 17651.5203 | 154.375
75 | H.1 Preparation guide | 1.9.5.1 | 74FS | FS81 | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
76 | H.2 Installation guide | 1.9.5.2 | 74FS | FS81 | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
77 | H.3 Configuration guide | 1.9.5.3 | 74FS | FS81 | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
78 | H.4 Migration guide | 1.9.5.4 | 74FS | FS81 | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
79 | H.5 Uninstallation guide | 1.9.5.5 |  |  | 2013-05-07 08:00 | 2013-05-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
80 | H.6 Training Needs Analysis | 1.9.5.6 | 74FS | FS81 | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 81.72 | 1307.52 | 1307.52 | 1.375
81 | Migration Strategy Document review | 1.9.6 | 75FS;76FS;77FS;78FS;80FS | FS82 | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 6.375
82 | Migration Strategy Fix document | 1.9.7 | 81FS | FS83 | 2013-10-16 08:00 | 2013-10-22 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 6.375
83 | Migration Strategy approval | 1.9.8 | 82FS |  | 2013-10-30 08:00 | 2013-11-12 17:00 | 10d |  | 0 | 0 | 204.3 | 16344.0002 | 16344.0002 | 13.375
126 | E. DLP Control and Enforcement | 1.10 |  |  | 2013-08-14 08:00 | 2013-10-25 17:00 | 53d |  |  | 0 |  |  | 81393.1213 | 72.375
84 | Define DLP Control and Enforcement output | 1.10.1 | 2FS | FS85 | 2013-08-14 08:00 | 2013-08-14 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 0.375
85 | Initial DLP Control and Enforcement workshop | 1.10.2 | 84FS | FS86 | 2013-08-15 08:00 | 2013-08-19 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 4.375
86 | DLP Control and Enforcement Document writing | 1.10.3 | 85FS | FS88 | 2013-08-21 08:00 | 2013-08-30 17:00 | 8d |  | 0 | 0 | 408.6 | 26150.4004 | 26150.4004 | 9.375
87 | E.1 Comparion systems | 1.10.4 |  |  | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
88 | Follow-up DLP Control and Enforcement workshop | 1.10.5 | 86FS | FS89 | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 4.375
89 | DLP Control and Enforcement Document writing | 1.10.6 | 88FS | FS91 | 2013-09-24 08:00 | 2013-09-27 17:00 | 4d |  | 0 | 0 | 408.6 | 13075.2002 | 13075.2002 | 3.375
90 | E.1 Comparion systems | 1.10.7 |  |  | 2013-09-24 08:00 | 2013-09-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
91 | DLP Control and Enforcement Document review | 1.10.8 | 89FS | FS92 | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 4.375
92 | DLP Control and Enforcement Fix document | 1.10.9 | 91FS | FS93 | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 4.375
93 | DLP Control and Enforcement approval | 1.10.10 | 92FS |  | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 98.064 | 7845.1202 | 7845.1202 | 11.375
127 | F. Centralized Management and Monitoring Architecture for DLP | 1.11 |  |  | 2013-04-12 08:00 | 2013-11-22 17:00 | 161d |  |  | 0 |  |  | 81720.0012 | 224.375
94 | Define Mgt & Monitoring Architecture output | 1.11.1 |  | FS95 | 2013-04-12 08:00 | 2013-04-12 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 0.375
95 | Initial Mgt & Monitoring Architecture workshop | 1.11.2 | 94FS | FS97 | 2013-04-15 08:00 | 2013-04-17 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2.375
139 | Mgt & Monitoring Architecture Document writing | 1.11.3 |  |  | 2013-04-18 08:00 | 2013-10-14 17:00 | 128d |  |  | 0 |  |  | 32688.0005 | 179.375
96 | F.1 Definition of organisation & roles | 1.11.3.1 |  | FS102 | 2013-04-23 08:00 | 2013-04-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
97 | F.2 log specs & formats | 1.11.3.2 | 95FS | FS101 | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
98 | F.3 Central management design | 1.11.3.3 |  | FS104 | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
99 | F.4 Log collection design | 1.11.3.4 |  | FS105 | 2013-10-11 08:00 | 2013-10-14 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 3.375
100 | F.5 Integration | 1.11.3.5 |  | FS101 | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
101 | Follow-up Mgt & Monitoring Architecture workshop | 1.11.4 | 97FS;100FS | FS103 | 2013-04-22 08:00 | 2013-04-24 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2.375
140 | Mgt & Monitoring Architecture Document writing | 1.11.5 |  |  | 2013-04-25 08:00 | 2013-11-01 17:00 | 137d |  |  | 0 |  |  | 16344.0002 | 190.375
102 | F.1 Definition of organisation & roles | 1.11.5.1 | 96FS |  | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
103 | F.2 log specs & formats | 1.11.5.2 | 101FS | FS108 | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
104 | F.3 Central management design | 1.11.5.3 | 98FS |  | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
105 | F.4 Log collection design | 1.11.5.4 | 99FS |  | 2013-10-29 08:00 | 2013-10-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
106 | F.5 Integration | 1.11.5.5 |  | FS108 | 2013-10-31 08:00 | 2013-11-01 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
107 | Mgt & Monitoring Architecture Document review | 1.11.6 |  | FS108 | 2013-10-22 08:00 | 2013-10-28 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 6.375
108 | Mgt & Monitoring Architecture Fix document | 1.11.7 | 103FS;106FS;107FS | FS109 | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 204.3 | 8172.0001 | 8172.0001 | 4.375
109 | Mgt & Monitoring Architecture approval | 1.11.8 | 108FS |  | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 11.375
128 | G. High Level Solution for Network based DLP | 1.12 |  |  | 2013-11-25 08:00 | 2014-01-07 17:00 | 32d |  |  | 0 |  |  | 36447.1205 | 43.375
110 | Define HL Solution for NW based DLP output | 1.12.1 |  | FS111 | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 0.375
111 | Initial HL Solution for NW based DLP workshop | 1.12.2 | 110FS | FS112;FS113 | 2013-11-26 08:00 | 2013-11-28 17:00 | 3d |  | 0 | 0 | 20.43 | 490.32 | 490.32 | 2.375
141 | HL Solution for NW based DLP Document writing | 1.12.3 |  |  | 2013-11-29 08:00 | 2013-12-04 17:00 | 4d |  |  | 0 |  |  | 13075.2002 | 5.375
112 | G.1 Solution Design | 1.12.3.1 | 111FS | FS114 | 2013-11-29 08:00 | 2013-12-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 3.375
113 | G.2 Gap analysis | 1.12.3.2 | 111FS | FS114 | 2013-12-03 08:00 | 2013-12-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 1.375
114 | Follow-up HL Solution for NW based DLP workshop | 1.12.4 | 112FS;113FS | FS115;FS116 | 2013-12-05 08:00 | 2013-12-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
142 | HL Solution for NW based DLP Document writing | 1.12.5 |  |  | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  |  | 0 |  |  | 6537.6001 | 1.375
115 | G.1 Solution Design | 1.12.5.1 | 114FS | FS117 | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
116 | G.2 Gap analysis | 1.12.5.2 | 114FS | FS117 | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 1.375
117 | HL Solution for NW based DLP Document review | 1.12.6 | 115FS;116FS | FS118 | 2013-12-11 08:00 | 2013-12-17 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 6.375
118 | HL Solution for NW based DLP Fix document | 1.12.7 | 117FS | FS119 | 2013-12-18 08:00 | 2013-12-24 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 6.375
119 | HL Solution for NW based DLP approval | 1.12.8 | 118FS |  | 2013-12-25 08:00 | 2014-01-07 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 13.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Data Loss Prevention System | 1560h |  |  |  |  | 99 | 100 | 101
1 | MS Kick off meeting | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | DLP workshop | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | study existing documentation | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
120 | Milestones | 1368h |  |  |  |  | 99 | 100 | 101
4 | MS Start specific design | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | MS testing start | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | MS testing end | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | MS Deployment start | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | MS Deployment end | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
121 | A. DLP Strategy | 432h |  |  |  |  | 99 | 100 | 101
9 | Define DLP Strategy output | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Initial DLP Strategy workshop | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
129 | DLP Strategy Document writing | 168h |  |  |  |  | 99 | 100 | 101
11 | A.1 Technical and Organizational inputs | 16h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
12 | A.2 Data loss/leakage prevention Strategy | 16h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
15 | Follow-up DLP Strategy workshop | 24h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
13 | A.3 Proposed optimization of the need of information sharing and portability | 16h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
14 | A.4 Overarching technical policies | 16h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
130 | DLP Strategy Document writing | 32h |  |  |  |  | 99 | 100 | 101
16 | A.1 Technical and Organizational inputs | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
17 | A.2 Data loss/leakage prevention Strategy | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
18 | A.3 Proposed optimization of the need of information sharing and portability | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
19 | A.4 Overarching technical policies | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
20 | DLP Strategy Document review | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | DLP Strategy Fix document | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | DLP Strategy approval | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
122 | B. High level implementation plan | 440h |  |  |  |  | 99 | 100 | 101
23 | Define HL Implementation plan output | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Initial HL Implementation plan workshop | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
131 | HL Implementation plan Document writing | 64h |  |  |  |  | 99 | 100 | 101
25 | B.1 Roadmap towards a full DLP implementation | 16h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
26 | B.2 Communication plan to stakeholders | 16h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
27 | B.3 integration in exisiting architecture | 16h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
28 | B.4 Security controls for the enforcement of the policy | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
29 | Follow-up HL Implementation plan workshop | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
132 | HL Implementation plan Document writing | 32h |  |  |  |  | 99 | 100 | 101
30 | B.1 Roadmap towards a full DLP implementation | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
31 | B.2 Communication plan to stakeholders | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
32 | B.3 integration in existing architecture | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
33 | B.4 Security controls for the enforcement of the policy | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
34 | HL Implementation plan Document review | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | HL Implementation plan Fix document | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | HL Implementation plan approval | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
123 | D. Technical directives | 432h |  |  |  |  | 99 | 100 | 101
37 | Define Technical directives output | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Initial Technical directives workshop | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
133 | Technical directives Document writing | 96h |  |  |  |  | 99 | 100 | 101
39 | D.1 Device/Port control rules | 8h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
40 | D.2 DLP rules | 16h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
41 | D.3 Encryption rules | 16h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
42 | D.4 Use-cases Device Control & DLP Encryption | 16h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
43 | Rule set v1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | Follow-up Technical directives workshop | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
134 | Technical directives Document writing | 24h |  |  |  |  | 99 | 100 | 101
45 | D.1 Device /Port control rules | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
46 | D.2 DLP rules | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
47 | D.3 Encryption rules | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
48 | D.4 Use-cases Device Control & DLP Encryption | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
49 | Technical directives Document review | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Technical directives Fix document | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | Technical directives approval | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
124 | C. High Level Solution Design for Data Tagging and Information Classification | 744h |  |  |  |  | 99 | 100 | 101
52 | Define Data tagging HL Solution output | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Initial Data tagging HL Solution workshop | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
135 | DLP Data tagging HL Solution Document writing | 64h |  |  |  |  | 99 | 100 | 101
54 | C.1 High-level solution design | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
55 | C.2 Organization & Roles | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
56 | C.3 Discovery of Classified Information | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
57 | C.4 Control for tagging and classification | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
58 | Follow-up Data tagging HL Solution workshop | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
136 | DLP Data tagging HL Solution Document writing | 584h |  |  |  |  | 99 | 100 | 101
59 | C.1 High-level solution design | 16h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
60 | C.2 Organization & Roles | 16h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
61 | C.3 Discovery of Classified Information | 16h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
62 | C.4 Control for tagging and classification | 16h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
63 | DLP Data tagging HL Solution Document review | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | DLP Data tagging HL Solution Fix document | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | DLP Data tagging HL Solution approval | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
125 | H. Migration Strategy and a high level Implementation Package | 1104h |  |  |  |  | 99 | 100 | 101
66 | Define Migration Strategy output | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
67 | Initial Migration Strategy workshop | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
137 | Migration Strategy Document writing | 816h |  |  |  |  | 99 | 100 | 101
68 | H.1 Preparation guide | 16h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
69 | H.2 Installation guide | 16h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
70 | H.5 Uninstallation guide | 16h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
71 | H.6 Training Needs Analysis | 16h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
72 | H.7 Dashboards | 16h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
73 | H.8 Measurement Methods | 16h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
74 | Follow-up Migration Strategy workshop | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
138 | Migration Strategy Document writing | 888h |  |  |  |  | 99 | 100 | 101
75 | H.1 Preparation guide | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
76 | H.2 Installation guide | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
77 | H.3 Configuration guide | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
78 | H.4 Migration guide | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
79 | H.5 Uninstallation guide | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
80 | H.6 Training Needs Analysis | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
81 | Migration Strategy Document review | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
82 | Migration Strategy Fix document | 40h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
83 | Migration Strategy approval | 80h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
126 | E. DLP Control and Enforcement | 424h |  |  |  |  | 99 | 100 | 101
84 | Define DLP Control and Enforcement output | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
85 | Initial DLP Control and Enforcement workshop | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | DLP Control and Enforcement Document writing | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
87 | E.1 Comparion systems | 16h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
88 | Follow-up DLP Control and Enforcement workshop | 24h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
89 | DLP Control and Enforcement Document writing | 32h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
90 | E.1 Comparion systems | 16h | manual - relative | 99 | 100 | 101 | 99 | 100 | 101
91 | DLP Control and Enforcement Document review | 40h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
92 | DLP Control and Enforcement Fix document | 40h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
93 | DLP Control and Enforcement approval | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
127 | F. Centralized Management and Monitoring Architecture for DLP | 1288h |  |  |  |  | 99 | 100 | 101
94 | Define Mgt & Monitoring Architecture output | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
95 | Initial Mgt & Monitoring Architecture workshop | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
139 | Mgt & Monitoring Architecture Document writing | 1024h |  |  |  |  | 99 | 100 | 101
96 | F.1 Definition of organisation & roles | 16h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
97 | F.2 log specs & formats | 16h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
98 | F.3 Central management design | 16h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
99 | F.4 Log collection design | 16h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
100 | F.5 Integration | 16h | manual - relative | 80 | 100 | 150 | 80 | 100 | 150
101 | Follow-up Mgt & Monitoring Architecture workshop | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
140 | Mgt & Monitoring Architecture Document writing | 1096h |  |  |  |  | 99 | 100 | 101
102 | F.1 Definition of organisation & roles | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
103 | F.2 log specs & formats | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
104 | F.3 Central management design | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
105 | F.4 Log collection design | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
106 | F.5 Integration | 16h | manual - relative | 40 | 100 | 120 | 40 | 100 | 120
107 | Mgt & Monitoring Architecture Document review | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
108 | Mgt & Monitoring Architecture Fix document | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
109 | Mgt & Monitoring Architecture approval | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
128 | G. High Level Solution for Network based DLP | 256h |  |  |  |  | 99 | 100 | 101
110 | Define HL Solution for NW based DLP output | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
111 | Initial HL Solution for NW based DLP workshop | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
141 | HL Solution for NW based DLP Document writing | 32h |  |  |  |  | 99 | 100 | 101
112 | G.1 Solution Design | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
113 | G.2 Gap analysis | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
114 | Follow-up HL Solution for NW based DLP workshop | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
142 | HL Solution for NW based DLP Document writing | 16h |  |  |  |  | 99 | 100 | 101
115 | G.1 Solution Design | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
116 | G.2 Gap analysis | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
117 | HL Solution for NW based DLP Document review | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
118 | HL Solution for NW based DLP Fix document | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
119 | HL Solution for NW based DLP approval | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2013-05-06 08:00 |  | TP Name | T1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Data Loss Prevention System | 2013-04-10 08:00 | 2014-01-07 17:00 | 195d |  |  | 0 |  |  | 584951.7689 |  | 18d | [5 empty] | 42494.4006 |  | 6.892% |  | 40315.2007 | 78451.2012
1 | MS Kick off meeting | 2013-04-10 08:00 | 2013-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-04-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | DLP workshop | 2013-04-15 08:00 | 2013-04-15 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-04-15 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | study existing documentation | 2013-04-16 08:00 | 2013-04-22 17:00 | 5d |  | 0 | 0 | 408.6 | 16344.0002 | 16344.0002 | 2013-04-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 16344.0002 | 16344.0002 | 100 | 100 | 100 | 100 | 100 | 100
120 | Milestones | 2013-05-03 17:00 | 2013-12-30 17:00 | 171d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | MS Start specific design | 2013-05-03 17:00 | 2013-05-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | MS testing start | 2013-07-05 17:00 | 2013-07-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | MS testing end | 2013-09-13 17:00 | 2013-09-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | MS Deployment start | 2013-09-30 17:00 | 2013-09-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | MS Deployment end | 2013-12-30 17:00 | 2013-12-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | A. DLP Strategy | 2013-05-10 08:00 | 2013-07-24 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
9 | Define DLP Strategy output | 2013-05-10 08:00 | 2013-05-10 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Initial DLP Strategy workshop | 2013-05-16 08:00 | 2013-05-20 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 |  | 0 | 0 | 9806.4001 | 3d | 0 | 0 | 0 | 9806.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | DLP Strategy Document writing | 2013-05-21 08:00 | 2013-06-18 17:00 | 21d |  |  | 0 |  |  | 31053.6005 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
11 | A.1 Technical and Organizational inputs | 2013-05-21 08:00 | 2013-05-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | A.2 Data loss/leakage prevention Strategy | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Follow-up DLP Strategy workshop | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-10 08:00 | 2013-06-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | A.4 Overarching technical policies | 2013-06-12 08:00 | 2013-06-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | DLP Strategy Document writing | 2013-06-21 08:00 | 2013-06-26 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | A.1 Technical and Organizational inputs | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | A.2 Data loss/leakage prevention Strategy | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | A.4 Overarching technical policies | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | DLP Strategy Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | DLP Strategy Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | DLP Strategy approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | B. High level implementation plan | 2013-05-09 08:00 | 2013-07-24 17:00 | 55d |  |  | 0 |  |  | 67010.401 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | Define HL Implementation plan output | 2013-05-09 08:00 | 2013-05-09 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Initial HL Implementation plan workshop | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 |  | 0 | 0 | 9806.4001 | 3d | 0 | 0 | 0 | 9806.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | HL Implementation plan Document writing | 2013-05-23 08:00 | 2013-06-03 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | B.1 Roadmap towards a full DLP implementation | 2013-05-23 08:00 | 2013-05-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | B.2 Communication plan to stakeholders | 2013-05-27 08:00 | 2013-05-28 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | B.3 integration in exisiting architecture | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | B.4 Security controls for the enforcement of the policy | 2013-05-31 08:00 | 2013-06-03 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Follow-up HL Implementation plan workshop | 2013-06-12 08:00 | 2013-06-14 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | HL Implementation plan Document writing | 2013-06-17 08:00 | 2013-06-20 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
30 | B.1 Roadmap towards a full DLP implementation | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | B.2 Communication plan to stakeholders | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | B.3 integration in existing architecture | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | B.4 Security controls for the enforcement of the policy | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | HL Implementation plan Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | HL Implementation plan Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | HL Implementation plan approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | D. Technical directives | 2013-06-27 08:00 | 2013-09-10 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
37 | Define Technical directives output | 2013-06-27 08:00 | 2013-06-27 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Initial Technical directives workshop | 2013-06-28 08:00 | 2013-07-02 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 |  | 0 | 0 | 9806.4001 | 3d | 0 | 0 | 0 | 9806.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Technical directives Document writing | 2013-07-03 08:00 | 2013-07-18 17:00 | 12d |  |  | 0 |  |  | 22881.6003 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | D.1 Device/Port control rules | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | D.2 DLP rules | 2013-07-09 08:00 | 2013-07-10 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | D.3 Encryption rules | 2013-07-17 08:00 | 2013-07-18 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Rule set v1 | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Follow-up Technical directives workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Technical directives Document writing | 2013-07-24 08:00 | 2013-07-26 17:00 | 3d |  |  | 0 |  |  | 13075.2002 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
45 | D.1 Device /Port control rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | D.2 DLP rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | D.3 Encryption rules | 2013-07-25 08:00 | 2013-07-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Technical directives Document review | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Technical directives Fix document | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Technical directives approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | C. High Level Solution Design for Data Tagging and Information Classification | 2013-05-03 08:00 | 2013-09-10 17:00 | 93d |  |  | 0 |  |  | 67010.401 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1634.4
52 | Define Data tagging HL Solution output | 2013-07-04 08:00 | 2013-07-04 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Initial Data tagging HL Solution workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 |  | 0 | 0 | 9806.4001 | 3d | 0 | 0 | 0 | 9806.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | DLP Data tagging HL Solution Document writing | 2013-07-26 08:00 | 2013-08-06 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
54 | C.1 High-level solution design | 2013-07-26 08:00 | 2013-07-29 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | C.2 Organization & Roles | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | C.3 Discovery of Classified Information | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | C.4 Control for tagging and classification | 2013-08-05 08:00 | 2013-08-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Follow-up Data tagging HL Solution workshop | 2013-08-07 08:00 | 2013-08-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | DLP Data tagging HL Solution Document writing | 2013-05-03 08:00 | 2013-08-13 17:00 | 73d |  |  | 0 |  |  | 13075.2002 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1634.4
59 | C.1 High-level solution design | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | C.2 Organization & Roles | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 1634.4 | 100 |  | 0 | 100 |  | 0
61 | C.3 Discovery of Classified Information | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | C.4 Control for tagging and classification | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | DLP Data tagging HL Solution Document review | 2013-08-14 08:00 | 2013-08-20 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | DLP Data tagging HL Solution Fix document | 2013-08-21 08:00 | 2013-08-27 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | DLP Data tagging HL Solution approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | H. Migration Strategy and a high level Implementation Package | 2013-05-03 08:00 | 2013-11-12 17:00 | 138d |  |  | 0 |  |  | 97737.1215 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3268.8
66 | Define Migration Strategy output | 2013-08-20 08:00 | 2013-08-20 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Initial Migration Strategy workshop | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 |  | 0 | 0 | 9806.4001 | 3d | 0 | 0 | 0 | 9806.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Migration Strategy Document writing | 2013-05-03 08:00 | 2013-09-23 17:00 | 102d |  |  | 0 |  |  | 39225.6006 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3268.8
68 | H.1 Preparation guide | 2013-09-10 08:00 | 2013-09-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | H.2 Installation guide | 2013-09-12 08:00 | 2013-09-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | H.5 Uninstallation guide | 2013-09-16 08:00 | 2013-09-17 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | H.6 Training Needs Analysis | 2013-09-18 08:00 | 2013-09-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | H.7 Dashboards | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 3268.8 | 100 |  | 0 | 100 |  | 0
73 | H.8 Measurement Methods | 2013-09-20 08:00 | 2013-09-23 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Follow-up Migration Strategy workshop | 2013-09-30 08:00 | 2013-10-02 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Migration Strategy Document writing | 2013-05-07 08:00 | 2013-10-08 17:00 | 111d |  |  | 0 |  |  | 17651.5203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
75 | H.1 Preparation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | H.2 Installation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | H.3 Configuration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | H.4 Migration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | H.5 Uninstallation guide | 2013-05-07 08:00 | 2013-05-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | H.6 Training Needs Analysis | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 81.72 | 1307.52 | 1307.52 |  | 0 | 0 | 1307.52 | 2d | 0 | 0 | 0 | 1307.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Migration Strategy Document review | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Migration Strategy Fix document | 2013-10-16 08:00 | 2013-10-22 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Migration Strategy approval | 2013-10-30 08:00 | 2013-11-12 17:00 | 10d |  | 0 | 0 | 204.3 | 16344.0002 | 16344.0002 |  | 0 | 0 | 16344.0002 | 10d | 0 | 0 | 0 | 16344.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | E. DLP Control and Enforcement | 2013-08-14 08:00 | 2013-10-25 17:00 | 53d |  |  | 0 |  |  | 81393.1213 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
84 | Define DLP Control and Enforcement output | 2013-08-14 08:00 | 2013-08-14 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Initial DLP Control and Enforcement workshop | 2013-08-15 08:00 | 2013-08-19 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 |  | 0 | 0 | 9806.4001 | 3d | 0 | 0 | 0 | 9806.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | DLP Control and Enforcement Document writing | 2013-08-21 08:00 | 2013-08-30 17:00 | 8d |  | 0 | 0 | 408.6 | 26150.4004 | 26150.4004 |  | 0 | 0 | 26150.4004 | 8d | 0 | 0 | 0 | 26150.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | E.1 Comparion systems | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Follow-up DLP Control and Enforcement workshop | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | DLP Control and Enforcement Document writing | 2013-09-24 08:00 | 2013-09-27 17:00 | 4d |  | 0 | 0 | 408.6 | 13075.2002 | 13075.2002 |  | 0 | 0 | 13075.2002 | 4d | 0 | 0 | 0 | 13075.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | E.1 Comparion systems | 2013-09-24 08:00 | 2013-09-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | DLP Control and Enforcement Document review | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | DLP Control and Enforcement Fix document | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | DLP Control and Enforcement approval | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 98.064 | 7845.1202 | 7845.1202 |  | 0 | 0 | 7845.1202 | 10d | 0 | 0 | 0 | 7845.1202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | F. Centralized Management and Monitoring Architecture for DLP | 2013-04-12 08:00 | 2013-11-22 17:00 | 161d |  |  | 0 |  |  | 81720.0012 |  | 9d | [5 empty] | 22881.6003 |  | 25.33% |  | 20702.4004 | 53935.2008
94 | Define Mgt & Monitoring Architecture output | 2013-04-12 08:00 | 2013-04-12 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 3268.8 | 100 |  | 0 | 100 |  | 0
95 | Initial Mgt & Monitoring Architecture workshop | 2013-04-15 08:00 | 2013-04-17 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 |  | 0 | 0 | 9806.4001 | 3d | 0 | 0 | 0 | 9806.4001 | 0% | Not Started | 0 | 9806.4001 | 100 |  | 0 | 100 |  | 0
139 | Mgt & Monitoring Architecture Document writing | 2013-04-18 08:00 | 2013-10-14 17:00 | 128d |  |  | 0 |  |  | 32688.0005 |  | 9d | [5 empty] | 13075.2002 |  | 33.33% |  | 10896.0003 | 26150.4004
96 | F.1 Definition of organisation & roles | 2013-04-23 08:00 | 2013-04-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
97 | F.2 log specs & formats | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 6537.6001 | 100 |  | 0 | 100 |  | 0
98 | F.3 Central management design | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 1d | 3268.8 | 6537.6001 | 2d | 0 | 0 | 3268.8 | 6537.6001 | 33.33% | Started | 2179.2001 | 6537.6001 | 100 | 50 | 33.3333 | 100 | 50 | 33.3333
99 | F.4 Log collection design | 2013-10-11 08:00 | 2013-10-14 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-25 08:00 | 1d | 3268.8 | 6537.6001 | 2d | 0 | 0 | 3268.8 | 6537.6001 | 33.33% | Started | 2179.2001 | 0 | 100 | 50 | 33.3333 | 100 | 50 | 33.3333
100 | F.5 Integration | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 6537.6001 | 100 |  | 0 | 100 |  | 0
101 | Follow-up Mgt & Monitoring Architecture workshop | 2013-04-22 08:00 | 2013-04-24 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 4903.2001 | 100 |  | 0 | 100 |  | 0
140 | Mgt & Monitoring Architecture Document writing | 2013-04-25 08:00 | 2013-11-01 17:00 | 137d |  |  | 0 |  |  | 16344.0002 |  | 7d | [5 empty] | 9806.4001 |  | 60% |  | 9806.4001 | 9806.4001
102 | F.1 Definition of organisation & roles | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
103 | F.2 log specs & formats | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 3268.8 | 100 |  | 0 | 100 |  | 0
104 | F.3 Central management design | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
105 | F.4 Log collection design | 2013-10-29 08:00 | 2013-10-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-29 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
106 | F.5 Integration | 2013-10-31 08:00 | 2013-11-01 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Mgt & Monitoring Architecture Document review | 2013-10-22 08:00 | 2013-10-28 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Mgt & Monitoring Architecture Fix document | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 204.3 | 8172.0001 | 8172.0001 |  | 0 | 0 | 8172.0001 | 5d | 0 | 0 | 0 | 8172.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Mgt & Monitoring Architecture approval | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | G. High Level Solution for Network based DLP | 2013-11-25 08:00 | 2014-01-07 17:00 | 32d |  |  | 0 |  |  | 36447.1205 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Define HL Solution for NW based DLP output | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Initial HL Solution for NW based DLP workshop | 2013-11-26 08:00 | 2013-11-28 17:00 | 3d |  | 0 | 0 | 20.43 | 490.32 | 490.32 |  | 0 | 0 | 490.32 | 3d | 0 | 0 | 0 | 490.32 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HL Solution for NW based DLP Document writing | 2013-11-29 08:00 | 2013-12-04 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
112 | G.1 Solution Design | 2013-11-29 08:00 | 2013-12-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | G.2 Gap analysis | 2013-12-03 08:00 | 2013-12-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Follow-up HL Solution for NW based DLP workshop | 2013-12-05 08:00 | 2013-12-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | HL Solution for NW based DLP Document writing | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  |  | 0 |  |  | 6537.6001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | G.1 Solution Design | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | G.2 Gap analysis | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | HL Solution for NW based DLP Document review | 2013-12-11 08:00 | 2013-12-17 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | HL Solution for NW based DLP Fix document | 2013-12-18 08:00 | 2013-12-24 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | HL Solution for NW based DLP approval | 2013-12-25 08:00 | 2014-01-07 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2013-06-03 08:00 |  | TP Name | T2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Data Loss Prevention System | 2013-04-10 08:00 | 2014-01-07 17:00 | 195d |  |  | 0 |  |  | 584951.7689 |  | 38d | [5 empty] | 326880.0049 |  | 26.55% |  | 155283.7839 | 148730.4022
1 | MS Kick off meeting | 2013-04-10 08:00 | 2013-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-04-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | DLP workshop | 2013-04-15 08:00 | 2013-04-15 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-04-15 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | study existing documentation | 2013-04-16 08:00 | 2013-04-22 17:00 | 5d |  | 0 | 0 | 408.6 | 16344.0002 | 16344.0002 | 2013-04-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 16344.0002 | 16344.0002 | 100 | 100 | 100 | 100 | 100 | 100
120 | Milestones | 2013-05-03 17:00 | 2013-12-30 17:00 | 171d |  |  | 0 |  |  | 0 |  | 20d | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | MS Start specific design | 2013-05-03 17:00 | 2013-05-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-05-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
5 | MS testing start | 2013-07-05 17:00 | 2013-07-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | MS testing end | 2013-09-13 17:00 | 2013-09-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | MS Deployment start | 2013-09-30 17:00 | 2013-09-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | MS Deployment end | 2013-12-30 17:00 | 2013-12-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | A. DLP Strategy | 2013-05-10 08:00 | 2013-07-24 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 16d | [5 empty] | 44128.8007 |  | 65.85% |  | 44128.8007 | 26150.4004
9 | Define DLP Strategy output | 2013-05-10 08:00 | 2013-05-10 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-10 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
10 | Initial DLP Strategy workshop | 2013-05-16 08:00 | 2013-05-20 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-16 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
129 | DLP Strategy Document writing | 2013-05-21 08:00 | 2013-06-18 17:00 | 21d |  |  | 0 |  |  | 31053.6005 |  | 5d | [5 empty] | 31053.6005 |  | 100% |  | 31053.6005 | 13075.2002
11 | A.1 Technical and Organizational inputs | 2013-05-21 08:00 | 2013-05-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
12 | A.2 Data loss/leakage prevention Strategy | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
15 | Follow-up DLP Strategy workshop | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-05-21 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 0 | 100 | 100 | 100 | 100 | 100 | 100
13 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-10 08:00 | 2013-06-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 100 | 100 | 100 | 100 | 100
14 | A.4 Overarching technical policies | 2013-06-12 08:00 | 2013-06-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-24 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 100 | 100 | 100 | 100 | 100
130 | DLP Strategy Document writing | 2013-06-21 08:00 | 2013-06-26 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
16 | A.1 Technical and Organizational inputs | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | A.2 Data loss/leakage prevention Strategy | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | A.4 Overarching technical policies | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | DLP Strategy Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | DLP Strategy Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | DLP Strategy approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | B. High level implementation plan | 2013-05-09 08:00 | 2013-07-24 17:00 | 55d |  |  | 0 |  |  | 67010.401 |  | 17d | [5 empty] | 29419.2004 |  | 34.15% |  | 22881.6005 | 35956.8005
23 | Define HL Implementation plan output | 2013-05-09 08:00 | 2013-05-09 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-09 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
24 | Initial HL Implementation plan workshop | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-13 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
131 | HL Implementation plan Document writing | 2013-05-23 08:00 | 2013-06-03 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 7d | [5 empty] | 16344.0002 |  | 37.5% |  | 9806.4003 | 22881.6003
25 | B.1 Roadmap towards a full DLP implementation | 2013-05-23 08:00 | 2013-05-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-23 08:00 | 2d | 6537.6001 | 6537.6001 | 2d | 0 | 0 | 6537.6001 | 6537.6001 | 50% | Started | 3268.8 | 6537.6001 | 100 | 100 | 50 | 100 | 100 | 50
26 | B.2 Communication plan to stakeholders | 2013-05-27 08:00 | 2013-05-28 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 6537.6001 | 2d | 0 | 0 | 3268.8 | 6537.6001 | 33.33% | Started | 2179.2001 | 6537.6001 | 100 | 50 | 33.3333 | 100 | 50 | 33.3333
27 | B.3 integration in exisiting architecture | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-29 08:00 | 1d | 3268.8 | 6537.6001 | 2d | 0 | 0 | 3268.8 | 6537.6001 | 33.33% | Started | 2179.2001 | 6537.6001 | 100 | 50 | 33.3333 | 100 | 50 | 33.3333
28 | B.4 Security controls for the enforcement of the policy | 2013-05-31 08:00 | 2013-06-03 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-31 08:00 | 1d | 3268.8 | 6537.6001 | 2d | 0 | 0 | 3268.8 | 6537.6001 | 33.33% | Started | 2179.2001 | 3268.8 | 100 | 50 | 33.3333 | 100 | 50 | 33.3333
29 | Follow-up HL Implementation plan workshop | 2013-06-12 08:00 | 2013-06-14 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | HL Implementation plan Document writing | 2013-06-17 08:00 | 2013-06-20 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
30 | B.1 Roadmap towards a full DLP implementation | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | B.2 Communication plan to stakeholders | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | B.3 integration in existing architecture | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | B.4 Security controls for the enforcement of the policy | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | HL Implementation plan Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | HL Implementation plan Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | HL Implementation plan approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | D. Technical directives | 2013-06-27 08:00 | 2013-09-10 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 12d | [5 empty] | 22881.6003 |  | 11.16% |  | 7479.326 | 0
37 | Define Technical directives output | 2013-06-27 08:00 | 2013-06-27 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Initial Technical directives workshop | 2013-06-28 08:00 | 2013-07-02 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 |  | 0 | 0 | 9806.4001 | 3d | 0 | 0 | 0 | 9806.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Technical directives Document writing | 2013-07-03 08:00 | 2013-07-18 17:00 | 12d |  |  | 0 |  |  | 22881.6003 |  | 12d | [5 empty] | 22881.6003 |  | 32.69% |  | 7479.326 | 0
39 | D.1 Device/Port control rules | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-16 08:00 | 1d | 3268.8 | 9806.4001 | 3d | 0 | 0 | 3268.8 | 9806.4001 | 25% | Started | 817.2 | 0 | 100 | 100 | 25 | 100 | 100 | 25
40 | D.2 DLP rules | 2013-07-09 08:00 | 2013-07-10 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 2d | 6537.6001 | 9806.4001 | 3d | 0 | 0 | 6537.6001 | 9806.4001 | 40% | Started | 2615.0401 | 0 | 100 | 100 | 40 | 100 | 100 | 40
41 | D.3 Encryption rules | 2013-07-17 08:00 | 2013-07-18 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 2d | 6537.6001 | 13075.2002 | 4d | 0 | 0 | 6537.6001 | 13075.2002 | 33.33% | Started | 2179.2001 | 0 | 100 | 100 | 33.3333 | 100 | 100 | 33.3333
42 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 2d | 6537.6001 | 16344.0002 | 5d | 0 | 0 | 6537.6001 | 16344.0002 | 28.57% | Started | 1867.8858 | 0 | 100 | 100 | 28.5714 | 100 | 100 | 28.5714
43 | Rule set v1 | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Follow-up Technical directives workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Technical directives Document writing | 2013-07-24 08:00 | 2013-07-26 17:00 | 3d |  |  | 0 |  |  | 13075.2002 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
45 | D.1 Device /Port control rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | D.2 DLP rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | D.3 Encryption rules | 2013-07-25 08:00 | 2013-07-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Technical directives Document review | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Technical directives Fix document | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Technical directives approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | C. High Level Solution Design for Data Tagging and Information Classification | 2013-05-03 08:00 | 2013-09-10 17:00 | 93d |  |  | 0 |  |  | 67010.401 |  | 8d | [5 empty] | 13075.2002 |  | 39.02% |  | 26150.4004 | 3268.8
52 | Define Data tagging HL Solution output | 2013-07-04 08:00 | 2013-07-04 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Initial Data tagging HL Solution workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 |  | 0 | 0 | 9806.4001 | 3d | 0 | 0 | 0 | 9806.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | DLP Data tagging HL Solution Document writing | 2013-07-26 08:00 | 2013-08-06 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 5d | [5 empty] | 13075.2002 |  | 100% |  | 26150.4004 | 0
54 | C.1 High-level solution design | 2013-07-26 08:00 | 2013-07-29 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-22 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 50 | 100 | 100 | 50 | 100
55 | C.2 Organization & Roles | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 50 | 100 | 100 | 50 | 100
56 | C.3 Discovery of Classified Information | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 50 | 100 | 100 | 50 | 100
57 | C.4 Control for tagging and classification | 2013-08-05 08:00 | 2013-08-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-28 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 50 | 100 | 100 | 50 | 100
58 | Follow-up Data tagging HL Solution workshop | 2013-08-07 08:00 | 2013-08-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | DLP Data tagging HL Solution Document writing | 2013-05-03 08:00 | 2013-08-13 17:00 | 73d |  |  | 0 |  |  | 13075.2002 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3268.8
59 | C.1 High-level solution design | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | C.2 Organization & Roles | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 3268.8 | 100 |  | 0 | 100 |  | 0
61 | C.3 Discovery of Classified Information | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | C.4 Control for tagging and classification | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | DLP Data tagging HL Solution Document review | 2013-08-14 08:00 | 2013-08-20 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | DLP Data tagging HL Solution Fix document | 2013-08-21 08:00 | 2013-08-27 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | DLP Data tagging HL Solution approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | H. Migration Strategy and a high level Implementation Package | 2013-05-03 08:00 | 2013-11-12 17:00 | 138d |  |  | 0 |  |  | 97737.1215 |  | 19d | [5 empty] | 171612.0026 |  | 11.32% |  | 11059.6555 | 9806.4001
66 | Define Migration Strategy output | 2013-08-20 08:00 | 2013-08-20 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Initial Migration Strategy workshop | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 |  | 0 | 0 | 9806.4001 | 3d | 0 | 0 | 0 | 9806.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Migration Strategy Document writing | 2013-05-03 08:00 | 2013-09-23 17:00 | 102d |  |  | 0 |  |  | 39225.6006 |  | 13d | [5 empty] | 169977.6025 |  | 24.03% |  | 9425.2555 | 6537.6001
68 | H.1 Preparation guide | 2013-09-10 08:00 | 2013-09-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 13d | 42494.4006 | 107870.4016 | 33d | 0 | 0 | 42494.4006 | 107870.4016 | 28.26% | Started | 1847.5826 | 0 | 100 | 650 | 28.2609 | 100 | 650 | 28.2609
69 | H.2 Installation guide | 2013-09-12 08:00 | 2013-09-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 13d | 42494.4006 | 127483.2019 | 39d | 0 | 0 | 42494.4006 | 127483.2019 | 25% | Started | 1634.4 | 0 | 100 | 650 | 25 | 100 | 650 | 25
70 | H.5 Uninstallation guide | 2013-09-16 08:00 | 2013-09-17 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 13d | 42494.4006 | 127483.2019 | 39d | 0 | 0 | 42494.4006 | 127483.2019 | 25% | Started | 1634.4 | 0 | 100 | 650 | 25 | 100 | 650 | 25
71 | H.6 Training Needs Analysis | 2013-09-18 08:00 | 2013-09-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 2d | 6537.6001 | 29419.2004 | 9d | 0 | 0 | 6537.6001 | 29419.2004 | 18.18% | Started | 1188.6546 | 0 | 100 | 100 | 18.1818 | 100 | 100 | 18.1818
72 | H.7 Dashboards | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 5d | 16344.0002 | 55569.6008 | 17d | 0 | 0 | 16344.0002 | 55569.6008 | 22.73% | Started | 1485.8182 | 6537.6001 | 100 | 250 | 22.7273 | 100 | 250 | 22.7273
73 | H.8 Measurement Methods | 2013-09-20 08:00 | 2013-09-23 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 6d | 19612.8003 | 58838.4009 | 18d | 0 | 0 | 19612.8003 | 58838.4009 | 25% | Started | 1634.4 | 0 | 100 | 300 | 25 | 100 | 300 | 25
74 | Follow-up Migration Strategy workshop | 2013-09-30 08:00 | 2013-10-02 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Migration Strategy Document writing | 2013-05-07 08:00 | 2013-10-08 17:00 | 111d |  |  | 0 |  |  | 17651.5203 |  | 19d | [5 empty] | 1634.4 |  | 9.259% |  | 1634.4 | 3268.8
75 | H.1 Preparation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | H.2 Installation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | H.3 Configuration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | H.4 Migration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | H.5 Uninstallation guide | 2013-05-07 08:00 | 2013-05-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 1d | 1634.4 | 1634.4 | 1d | 0 | 0 | 1634.4 | 1634.4 | 50% | Started | 1634.4 | 3268.8 | 100 | 50 | 50 | 100 | 50 | 50
80 | H.6 Training Needs Analysis | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 81.72 | 1307.52 | 1307.52 |  | 0 | 0 | 1307.52 | 2d | 0 | 0 | 0 | 1307.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Migration Strategy Document review | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Migration Strategy Fix document | 2013-10-16 08:00 | 2013-10-22 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Migration Strategy approval | 2013-10-30 08:00 | 2013-11-12 17:00 | 10d |  | 0 | 0 | 204.3 | 16344.0002 | 16344.0002 |  | 0 | 0 | 16344.0002 | 10d | 0 | 0 | 0 | 16344.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | E. DLP Control and Enforcement | 2013-08-14 08:00 | 2013-10-25 17:00 | 53d |  |  | 0 |  |  | 81393.1213 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
84 | Define DLP Control and Enforcement output | 2013-08-14 08:00 | 2013-08-14 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Initial DLP Control and Enforcement workshop | 2013-08-15 08:00 | 2013-08-19 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 |  | 0 | 0 | 9806.4001 | 3d | 0 | 0 | 0 | 9806.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | DLP Control and Enforcement Document writing | 2013-08-21 08:00 | 2013-08-30 17:00 | 8d |  | 0 | 0 | 408.6 | 26150.4004 | 26150.4004 |  | 0 | 0 | 26150.4004 | 8d | 0 | 0 | 0 | 26150.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | E.1 Comparion systems | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Follow-up DLP Control and Enforcement workshop | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | DLP Control and Enforcement Document writing | 2013-09-24 08:00 | 2013-09-27 17:00 | 4d |  | 0 | 0 | 408.6 | 13075.2002 | 13075.2002 |  | 0 | 0 | 13075.2002 | 4d | 0 | 0 | 0 | 13075.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | E.1 Comparion systems | 2013-09-24 08:00 | 2013-09-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | DLP Control and Enforcement Document review | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | DLP Control and Enforcement Fix document | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | DLP Control and Enforcement approval | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 98.064 | 7845.1202 | 7845.1202 |  | 0 | 0 | 7845.1202 | 10d | 0 | 0 | 0 | 7845.1202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | F. Centralized Management and Monitoring Architecture for DLP | 2013-04-12 08:00 | 2013-11-22 17:00 | 161d |  |  | 0 |  |  | 81720.0012 |  | 29d | [5 empty] | 26150.4004 |  | 29.33% |  | 23971.2005 | 53935.2008
94 | Define Mgt & Monitoring Architecture output | 2013-04-12 08:00 | 2013-04-12 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
95 | Initial Mgt & Monitoring Architecture workshop | 2013-04-15 08:00 | 2013-04-17 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 |  | 0 | 0 | 9806.4001 | 3d | 0 | 0 | 0 | 9806.4001 | 0% | Not Started | 0 | 9806.4001 | 100 |  | 0 | 100 |  | 0
139 | Mgt & Monitoring Architecture Document writing | 2013-04-18 08:00 | 2013-10-14 17:00 | 128d |  |  | 0 |  |  | 32688.0005 |  | 29d | [5 empty] | 13075.2002 |  | 33.33% |  | 10896.0003 | 26150.4004
96 | F.1 Definition of organisation & roles | 2013-04-23 08:00 | 2013-04-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
97 | F.2 log specs & formats | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 6537.6001 | 100 |  | 0 | 100 |  | 0
98 | F.3 Central management design | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 1d | 3268.8 | 6537.6001 | 2d | 0 | 0 | 3268.8 | 6537.6001 | 33.33% | Started | 2179.2001 | 6537.6001 | 100 | 50 | 33.3333 | 100 | 50 | 33.3333
99 | F.4 Log collection design | 2013-10-11 08:00 | 2013-10-14 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-25 08:00 | 1d | 3268.8 | 6537.6001 | 2d | 0 | 0 | 3268.8 | 6537.6001 | 33.33% | Started | 2179.2001 | 0 | 100 | 50 | 33.3333 | 100 | 50 | 33.3333
100 | F.5 Integration | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 6537.6001 | 100 |  | 0 | 100 |  | 0
101 | Follow-up Mgt & Monitoring Architecture workshop | 2013-04-22 08:00 | 2013-04-24 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 4903.2001 | 100 |  | 0 | 100 |  | 0
140 | Mgt & Monitoring Architecture Document writing | 2013-04-25 08:00 | 2013-11-01 17:00 | 137d |  |  | 0 |  |  | 16344.0002 |  | 27d | [5 empty] | 9806.4001 |  | 60% |  | 9806.4001 | 9806.4001
102 | F.1 Definition of organisation & roles | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
103 | F.2 log specs & formats | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 3268.8 | 100 |  | 0 | 100 |  | 0
104 | F.3 Central management design | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
105 | F.4 Log collection design | 2013-10-29 08:00 | 2013-10-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-29 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
106 | F.5 Integration | 2013-10-31 08:00 | 2013-11-01 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Mgt & Monitoring Architecture Document review | 2013-10-22 08:00 | 2013-10-28 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Mgt & Monitoring Architecture Fix document | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 204.3 | 8172.0001 | 8172.0001 |  | 0 | 0 | 8172.0001 | 5d | 0 | 0 | 0 | 8172.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Mgt & Monitoring Architecture approval | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | G. High Level Solution for Network based DLP | 2013-11-25 08:00 | 2014-01-07 17:00 | 32d |  |  | 0 |  |  | 36447.1205 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Define HL Solution for NW based DLP output | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Initial HL Solution for NW based DLP workshop | 2013-11-26 08:00 | 2013-11-28 17:00 | 3d |  | 0 | 0 | 20.43 | 490.32 | 490.32 |  | 0 | 0 | 490.32 | 3d | 0 | 0 | 0 | 490.32 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HL Solution for NW based DLP Document writing | 2013-11-29 08:00 | 2013-12-04 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
112 | G.1 Solution Design | 2013-11-29 08:00 | 2013-12-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | G.2 Gap analysis | 2013-12-03 08:00 | 2013-12-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Follow-up HL Solution for NW based DLP workshop | 2013-12-05 08:00 | 2013-12-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | HL Solution for NW based DLP Document writing | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  |  | 0 |  |  | 6537.6001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | G.1 Solution Design | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | G.2 Gap analysis | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | HL Solution for NW based DLP Document review | 2013-12-11 08:00 | 2013-12-17 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | HL Solution for NW based DLP Fix document | 2013-12-18 08:00 | 2013-12-24 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | HL Solution for NW based DLP approval | 2013-12-25 08:00 | 2014-01-07 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2013-07-01 08:00 |  | TP Name | T3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Data Loss Prevention System | 2013-04-10 08:00 | 2014-01-07 17:00 | 195d |  |  | 0 |  |  | 584951.7689 |  | 58d | [5 empty] | 728370.3709 |  | 46.68% |  | 273070.3117 | 210183.8431
1 | MS Kick off meeting | 2013-04-10 08:00 | 2013-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-04-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | DLP workshop | 2013-04-15 08:00 | 2013-04-15 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-04-15 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | study existing documentation | 2013-04-16 08:00 | 2013-04-22 17:00 | 5d |  | 0 | 0 | 408.6 | 16344.0002 | 16344.0002 | 2013-04-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 16344.0002 | 16344.0002 | 100 | 100 | 100 | 100 | 100 | 100
120 | Milestones | 2013-05-03 17:00 | 2013-12-30 17:00 | 171d |  |  | 0 |  |  | 0 |  | 40d | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | MS Start specific design | 2013-05-03 17:00 | 2013-05-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-05-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
5 | MS testing start | 2013-07-05 17:00 | 2013-07-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | MS testing end | 2013-09-13 17:00 | 2013-09-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | MS Deployment start | 2013-09-30 17:00 | 2013-09-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | MS Deployment end | 2013-12-30 17:00 | 2013-12-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | A. DLP Strategy | 2013-05-10 08:00 | 2013-07-24 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 36d | [5 empty] | 60472.8009 |  | 89.43% |  | 59928.0008 | 58511.5209
9 | Define DLP Strategy output | 2013-05-10 08:00 | 2013-05-10 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-10 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
10 | Initial DLP Strategy workshop | 2013-05-16 08:00 | 2013-05-20 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-16 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
129 | DLP Strategy Document writing | 2013-05-21 08:00 | 2013-06-18 17:00 | 21d |  |  | 0 |  |  | 31053.6005 |  | 5d | [5 empty] | 31053.6005 |  | 100% |  | 31053.6005 | 31053.6005
11 | A.1 Technical and Organizational inputs | 2013-05-21 08:00 | 2013-05-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
12 | A.2 Data loss/leakage prevention Strategy | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
15 | Follow-up DLP Strategy workshop | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-05-21 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
13 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-10 08:00 | 2013-06-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
14 | A.4 Overarching technical policies | 2013-06-12 08:00 | 2013-06-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-24 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
130 | DLP Strategy Document writing | 2013-06-21 08:00 | 2013-06-26 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 2d | [5 empty] | 13075.2002 |  | 100% |  | 13075.2002 | 13075.2002
16 | A.1 Technical and Organizational inputs | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
17 | A.2 Data loss/leakage prevention Strategy | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
18 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
19 | A.4 Overarching technical policies | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
20 | DLP Strategy Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-06-25 08:00 | 5d | 3268.8 | 653.76 | 1d | 0 | 0 | 3268.8 | 653.76 | 83.33% | Started | 2724 | 1307.52 | 100 | 100 | 83.3333 | 100 | 100 | 83.3333
21 | DLP Strategy Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | DLP Strategy approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | B. High level implementation plan | 2013-05-09 08:00 | 2013-07-24 17:00 | 55d |  |  | 0 |  |  | 67010.401 |  | 37d | [5 empty] | 68644.801 |  | 85.37% |  | 57204.0009 | 58511.5209
23 | Define HL Implementation plan output | 2013-05-09 08:00 | 2013-05-09 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-09 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
24 | Initial HL Implementation plan workshop | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-13 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
131 | HL Implementation plan Document writing | 2013-05-23 08:00 | 2013-06-03 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 8d | [5 empty] | 39225.6006 |  | 100% |  | 26150.4004 | 26150.4004
25 | B.1 Roadmap towards a full DLP implementation | 2013-05-23 08:00 | 2013-05-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-23 08:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 200 | 100 | 100 | 200 | 100
26 | B.2 Communication plan to stakeholders | 2013-05-27 08:00 | 2013-05-28 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
27 | B.3 integration in exisiting architecture | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-29 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
28 | B.4 Security controls for the enforcement of the policy | 2013-05-31 08:00 | 2013-06-03 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-31 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
29 | Follow-up HL Implementation plan workshop | 2013-06-12 08:00 | 2013-06-14 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-06-11 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
132 | HL Implementation plan Document writing | 2013-06-17 08:00 | 2013-06-20 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 3d | [5 empty] | 11440.8002 |  | 100% |  | 13075.2002 | 13075.2002
30 | B.1 Roadmap towards a full DLP implementation | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-14 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
31 | B.2 Communication plan to stakeholders | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-14 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
32 | B.3 integration in existing architecture | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
33 | B.4 Security controls for the enforcement of the policy | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 1d | 1634.4 | 0 | 0 | 0 | 0 | 1634.4 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 50 | 100 | 100 | 50 | 100
34 | HL Implementation plan Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 1307.52 | 100 |  | 0 | 100 |  | 0
35 | HL Implementation plan Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | HL Implementation plan approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | D. Technical directives | 2013-06-27 08:00 | 2013-09-10 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 32d | [5 empty] | 62515.8009 |  | 45.61% |  | 30563.2805 | 6537.6001
37 | Define Technical directives output | 2013-06-27 08:00 | 2013-06-27 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 3268.8 | 100 |  | 0 | 100 |  | 0
38 | Initial Technical directives workshop | 2013-06-28 08:00 | 2013-07-02 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-13 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
133 | Technical directives Document writing | 2013-07-03 08:00 | 2013-07-18 17:00 | 12d |  |  | 0 |  |  | 22881.6003 |  | 32d | [5 empty] | 52300.8008 |  | 76.43% |  | 17488.0803 | 0
39 | D.1 Device/Port control rules | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-16 08:00 | 3d | 9806.4001 | 3268.8 | 1d | 0 | 0 | 9806.4001 | 3268.8 | 75% | Started | 2451.6 | 0 | 100 | 300 | 75 | 100 | 300 | 75
40 | D.2 DLP rules | 2013-07-09 08:00 | 2013-07-10 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 4d | 13075.2002 | 3268.8 | 1d | 0 | 0 | 13075.2002 | 3268.8 | 80% | Started | 5230.0802 | 0 | 100 | 200 | 80 | 100 | 200 | 80
41 | D.3 Encryption rules | 2013-07-17 08:00 | 2013-07-18 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 4d | 13075.2002 | 6537.6001 | 2d | 0 | 0 | 13075.2002 | 6537.6001 | 66.67% | Started | 4358.4002 | 0 | 100 | 200 | 66.6667 | 100 | 200 | 66.6667
42 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 5d | 16344.0002 | 3268.8 | 1d | 0 | 0 | 16344.0002 | 3268.8 | 83.33% | Started | 5448 | 0 | 100 | 250 | 83.3333 | 100 | 250 | 83.3333
43 | Rule set v1 | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 1h | 408.6 | 0 | 0 | 0 | 0 | 408.6 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 12.5 | 100 | 100 | 12.5 | 100
44 | Follow-up Technical directives workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Technical directives Document writing | 2013-07-24 08:00 | 2013-07-26 17:00 | 3d |  |  | 0 |  |  | 13075.2002 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
45 | D.1 Device /Port control rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | D.2 DLP rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | D.3 Encryption rules | 2013-07-25 08:00 | 2013-07-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Technical directives Document review | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Technical directives Fix document | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Technical directives approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | C. High Level Solution Design for Data Tagging and Information Classification | 2013-05-03 08:00 | 2013-09-10 17:00 | 93d |  |  | 0 |  |  | 67010.401 |  | 28d | [5 empty] | 29419.2004 |  | 58.54% |  | 39225.6006 | 3268.8
52 | Define Data tagging HL Solution output | 2013-07-04 08:00 | 2013-07-04 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-06-19 09:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 200 | 100 | 100 | 200 | 100
53 | Initial Data tagging HL Solution workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-17 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 0 | 100 | 100 | 100 | 100 | 100 | 100
135 | DLP Data tagging HL Solution Document writing | 2013-07-26 08:00 | 2013-08-06 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 5d | [5 empty] | 13075.2002 |  | 100% |  | 26150.4004 | 0
54 | C.1 High-level solution design | 2013-07-26 08:00 | 2013-07-29 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-22 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 50 | 100 | 100 | 50 | 100
55 | C.2 Organization & Roles | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 50 | 100 | 100 | 50 | 100
56 | C.3 Discovery of Classified Information | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 50 | 100 | 100 | 50 | 100
57 | C.4 Control for tagging and classification | 2013-08-05 08:00 | 2013-08-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-28 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 50 | 100 | 100 | 50 | 100
58 | Follow-up Data tagging HL Solution workshop | 2013-08-07 08:00 | 2013-08-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | DLP Data tagging HL Solution Document writing | 2013-05-03 08:00 | 2013-08-13 17:00 | 73d |  |  | 0 |  |  | 13075.2002 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3268.8
59 | C.1 High-level solution design | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | C.2 Organization & Roles | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 3268.8 | 100 |  | 0 | 100 |  | 0
61 | C.3 Discovery of Classified Information | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | C.4 Control for tagging and classification | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | DLP Data tagging HL Solution Document review | 2013-08-14 08:00 | 2013-08-20 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | DLP Data tagging HL Solution Fix document | 2013-08-21 08:00 | 2013-08-27 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | DLP Data tagging HL Solution approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | H. Migration Strategy and a high level Implementation Package | 2013-05-03 08:00 | 2013-11-12 17:00 | 138d |  |  | 0 |  |  | 97737.1215 |  | 39d | [5 empty] | 441941.7666 |  | 32.4% |  | 31669.4276 | 9806.4001
66 | Define Migration Strategy output | 2013-08-20 08:00 | 2013-08-20 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Initial Migration Strategy workshop | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 |  | 0 | 0 | 9806.4001 | 3d | 0 | 0 | 0 | 9806.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Migration Strategy Document writing | 2013-05-03 08:00 | 2013-09-23 17:00 | 102d |  |  | 0 |  |  | 39225.6006 |  | 33d | [5 empty] | 434750.4065 |  | 62.4% |  | 24478.0674 | 6537.6001
68 | H.1 Preparation guide | 2013-09-10 08:00 | 2013-09-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 33d | 107870.4016 | 42494.4006 | 13d | 0 | 0 | 107870.4016 | 42494.4006 | 71.74% | Started | 4690.0175 | 0 | 100 | 1650 | 71.7391 | 100 | 1650 | 71.7391
69 | H.2 Installation guide | 2013-09-12 08:00 | 2013-09-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 33d | 107870.4016 | 62107.2009 | 19d | 0 | 0 | 107870.4016 | 62107.2009 | 63.46% | Started | 4148.8615 | 0 | 100 | 1650 | 63.4615 | 100 | 1650 | 63.4615
70 | H.5 Uninstallation guide | 2013-09-16 08:00 | 2013-09-17 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 33d | 107870.4016 | 62107.2009 | 19d | 0 | 0 | 107870.4016 | 62107.2009 | 63.46% | Started | 4148.8615 | 0 | 100 | 1650 | 63.4615 | 100 | 1650 | 63.4615
71 | H.6 Training Needs Analysis | 2013-09-18 08:00 | 2013-09-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 7d | 22881.6003 | 16344.0002 | 5d | 0 | 0 | 22881.6003 | 16344.0002 | 58.33% | Started | 3813.5999 | 0 | 100 | 350 | 58.3333 | 100 | 350 | 58.3333
72 | H.7 Dashboards | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 13d | 42494.4006 | 29419.2004 | 9d | 0 | 0 | 42494.4006 | 29419.2004 | 59.09% | Started | 3863.1272 | 6537.6001 | 100 | 650 | 59.0909 | 100 | 650 | 59.0909
73 | H.8 Measurement Methods | 2013-09-20 08:00 | 2013-09-23 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 14d | 45763.2007 | 32688.0005 | 10d | 0 | 0 | 45763.2007 | 32688.0005 | 58.33% | Started | 3813.5999 | 0 | 100 | 700 | 58.3333 | 100 | 700 | 58.3333
74 | Follow-up Migration Strategy workshop | 2013-09-30 08:00 | 2013-10-02 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-06-25 08:00 | 1d | 1634.4 | 3268.8 | 2d | 0 | 0 | 1634.4 | 3268.8 | 33.33% | Started | 1634.4001 | 0 | 100 | 33.3333 | 33.3333 | 100 | 33.3333 | 33.3333
138 | Migration Strategy Document writing | 2013-05-07 08:00 | 2013-10-08 17:00 | 111d |  |  | 0 |  |  | 17651.5203 |  | 39d | [5 empty] | 5556.9601 |  | 31.48% |  | 5556.9601 | 3268.8
75 | H.1 Preparation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-28 08:00 | 1d | 1634.4 | 1634.4 | 1d | 0 | 0 | 1634.4 | 1634.4 | 50% | Started | 1634.4 | 0 | 100 | 50 | 50 | 100 | 50 | 50
76 | H.2 Installation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-28 08:00 | 1d | 1634.4 | 1634.4 | 1d | 0 | 0 | 1634.4 | 1634.4 | 50% | Started | 1634.4 | 0 | 100 | 50 | 50 | 100 | 50 | 50
77 | H.3 Configuration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | H.4 Migration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | H.5 Uninstallation guide | 2013-05-07 08:00 | 2013-05-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 1d | 1634.4 | 1634.4 | 1d | 0 | 0 | 1634.4 | 1634.4 | 50% | Started | 1634.4 | 3268.8 | 100 | 50 | 50 | 100 | 50 | 50
80 | H.6 Training Needs Analysis | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 81.72 | 1307.52 | 1307.52 | 2013-06-28 08:00 | 1d | 653.76 | 653.76 | 1d | 0 | 0 | 653.76 | 653.76 | 50% | Started | 653.76 | 0 | 100 | 50 | 50 | 100 | 50 | 50
81 | Migration Strategy Document review | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Migration Strategy Fix document | 2013-10-16 08:00 | 2013-10-22 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Migration Strategy approval | 2013-10-30 08:00 | 2013-11-12 17:00 | 10d |  | 0 | 0 | 204.3 | 16344.0002 | 16344.0002 |  | 0 | 0 | 16344.0002 | 10d | 0 | 0 | 0 | 16344.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | E. DLP Control and Enforcement | 2013-08-14 08:00 | 2013-10-25 17:00 | 53d |  |  | 0 |  |  | 81393.1213 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
84 | Define DLP Control and Enforcement output | 2013-08-14 08:00 | 2013-08-14 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Initial DLP Control and Enforcement workshop | 2013-08-15 08:00 | 2013-08-19 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 |  | 0 | 0 | 9806.4001 | 3d | 0 | 0 | 0 | 9806.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | DLP Control and Enforcement Document writing | 2013-08-21 08:00 | 2013-08-30 17:00 | 8d |  | 0 | 0 | 408.6 | 26150.4004 | 26150.4004 |  | 0 | 0 | 26150.4004 | 8d | 0 | 0 | 0 | 26150.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | E.1 Comparion systems | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Follow-up DLP Control and Enforcement workshop | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | DLP Control and Enforcement Document writing | 2013-09-24 08:00 | 2013-09-27 17:00 | 4d |  | 0 | 0 | 408.6 | 13075.2002 | 13075.2002 |  | 0 | 0 | 13075.2002 | 4d | 0 | 0 | 0 | 13075.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | E.1 Comparion systems | 2013-09-24 08:00 | 2013-09-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | DLP Control and Enforcement Document review | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | DLP Control and Enforcement Fix document | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | DLP Control and Enforcement approval | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 98.064 | 7845.1202 | 7845.1202 |  | 0 | 0 | 7845.1202 | 10d | 0 | 0 | 0 | 7845.1202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | F. Centralized Management and Monitoring Architecture for DLP | 2013-04-12 08:00 | 2013-11-22 17:00 | 161d |  |  | 0 |  |  | 81720.0012 |  | 49d | [5 empty] | 45763.2007 |  | 42.67% |  | 34867.201 | 53935.2008
94 | Define Mgt & Monitoring Architecture output | 2013-04-12 08:00 | 2013-04-12 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
95 | Initial Mgt & Monitoring Architecture workshop | 2013-04-15 08:00 | 2013-04-17 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-24 08:00 | 4d | 13075.2002 | 6537.6001 | 2d | 0 | 0 | 13075.2002 | 6537.6001 | 66.67% | Started | 6537.6003 | 9806.4001 | 100 | 133.3333 | 66.6667 | 100 | 133.3333 | 66.6667
139 | Mgt & Monitoring Architecture Document writing | 2013-04-18 08:00 | 2013-10-14 17:00 | 128d |  |  | 0 |  |  | 32688.0005 |  | 49d | [5 empty] | 19612.8003 |  | 46.67% |  | 15254.4005 | 26150.4004
96 | F.1 Definition of organisation & roles | 2013-04-23 08:00 | 2013-04-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
97 | F.2 log specs & formats | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 6537.6001 | 100 |  | 0 | 100 |  | 0
98 | F.3 Central management design | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 2d | 6537.6001 | 3268.8 | 1d | 0 | 0 | 6537.6001 | 3268.8 | 66.67% | Started | 4358.4002 | 6537.6001 | 100 | 100 | 66.6667 | 100 | 100 | 66.6667
99 | F.4 Log collection design | 2013-10-11 08:00 | 2013-10-14 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-25 08:00 | 2d | 6537.6001 | 3268.8 | 1d | 0 | 0 | 6537.6001 | 3268.8 | 66.67% | Started | 4358.4002 | 0 | 100 | 100 | 66.6667 | 100 | 100 | 66.6667
100 | F.5 Integration | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 6537.6001 | 100 |  | 0 | 100 |  | 0
101 | Follow-up Mgt & Monitoring Architecture workshop | 2013-04-22 08:00 | 2013-04-24 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 4903.2001 | 100 |  | 0 | 100 |  | 0
140 | Mgt & Monitoring Architecture Document writing | 2013-04-25 08:00 | 2013-11-01 17:00 | 137d |  |  | 0 |  |  | 16344.0002 |  | 47d | [5 empty] | 9806.4001 |  | 60% |  | 9806.4001 | 9806.4001
102 | F.1 Definition of organisation & roles | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
103 | F.2 log specs & formats | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 3268.8 | 100 |  | 0 | 100 |  | 0
104 | F.3 Central management design | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
105 | F.4 Log collection design | 2013-10-29 08:00 | 2013-10-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-29 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
106 | F.5 Integration | 2013-10-31 08:00 | 2013-11-01 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Mgt & Monitoring Architecture Document review | 2013-10-22 08:00 | 2013-10-28 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Mgt & Monitoring Architecture Fix document | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 204.3 | 8172.0001 | 8172.0001 |  | 0 | 0 | 8172.0001 | 5d | 0 | 0 | 0 | 8172.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Mgt & Monitoring Architecture approval | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | G. High Level Solution for Network based DLP | 2013-11-25 08:00 | 2014-01-07 17:00 | 32d |  |  | 0 |  |  | 36447.1205 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Define HL Solution for NW based DLP output | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Initial HL Solution for NW based DLP workshop | 2013-11-26 08:00 | 2013-11-28 17:00 | 3d |  | 0 | 0 | 20.43 | 490.32 | 490.32 |  | 0 | 0 | 490.32 | 3d | 0 | 0 | 0 | 490.32 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HL Solution for NW based DLP Document writing | 2013-11-29 08:00 | 2013-12-04 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
112 | G.1 Solution Design | 2013-11-29 08:00 | 2013-12-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | G.2 Gap analysis | 2013-12-03 08:00 | 2013-12-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Follow-up HL Solution for NW based DLP workshop | 2013-12-05 08:00 | 2013-12-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | HL Solution for NW based DLP Document writing | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  |  | 0 |  |  | 6537.6001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | G.1 Solution Design | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | G.2 Gap analysis | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | HL Solution for NW based DLP Document review | 2013-12-11 08:00 | 2013-12-17 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | HL Solution for NW based DLP Fix document | 2013-12-18 08:00 | 2013-12-24 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | HL Solution for NW based DLP approval | 2013-12-25 08:00 | 2014-01-07 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2013-08-05 08:00 |  | TP Name | T4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Data Loss Prevention System | 2013-04-10 08:00 | 2014-01-07 17:00 | 195d |  |  | 0 |  |  | 584951.7689 |  | 83d | [5 empty] | 1116295.2167 |  | 61.17% |  | 357801.9458 | 313804.8047
1 | MS Kick off meeting | 2013-04-10 08:00 | 2013-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-04-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | DLP workshop | 2013-04-15 08:00 | 2013-04-15 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-04-15 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | study existing documentation | 2013-04-16 08:00 | 2013-04-22 17:00 | 5d |  | 0 | 0 | 408.6 | 16344.0002 | 16344.0002 | 2013-04-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 16344.0002 | 16344.0002 | 100 | 100 | 100 | 100 | 100 | 100
120 | Milestones | 2013-05-03 17:00 | 2013-12-30 17:00 | 171d |  |  | 0 |  |  | 0 |  | 65d | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | MS Start specific design | 2013-05-03 17:00 | 2013-05-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-05-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
5 | MS testing start | 2013-07-05 17:00 | 2013-07-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | MS testing end | 2013-09-13 17:00 | 2013-09-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | MS Deployment start | 2013-09-30 17:00 | 2013-09-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | MS Deployment end | 2013-12-30 17:00 | 2013-12-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | A. DLP Strategy | 2013-05-10 08:00 | 2013-07-24 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 61d | [5 empty] | 68317.921 |  | 97.44% |  | 65294.281 | 67010.401
9 | Define DLP Strategy output | 2013-05-10 08:00 | 2013-05-10 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-10 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
10 | Initial DLP Strategy workshop | 2013-05-16 08:00 | 2013-05-20 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-16 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
129 | DLP Strategy Document writing | 2013-05-21 08:00 | 2013-06-18 17:00 | 21d |  |  | 0 |  |  | 31053.6005 |  | 5d | [5 empty] | 31053.6005 |  | 100% |  | 31053.6005 | 31053.6005
11 | A.1 Technical and Organizational inputs | 2013-05-21 08:00 | 2013-05-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
12 | A.2 Data loss/leakage prevention Strategy | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
15 | Follow-up DLP Strategy workshop | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-05-21 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
13 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-10 08:00 | 2013-06-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
14 | A.4 Overarching technical policies | 2013-06-12 08:00 | 2013-06-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-24 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
130 | DLP Strategy Document writing | 2013-06-21 08:00 | 2013-06-26 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 2d | [5 empty] | 13075.2002 |  | 100% |  | 13075.2002 | 13075.2002
16 | A.1 Technical and Organizational inputs | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
17 | A.2 Data loss/leakage prevention Strategy | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
18 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
19 | A.4 Overarching technical policies | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
20 | DLP Strategy Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-06-25 08:00 | 6d | 3922.5601 | 0 | 0 | 0 | 0 | 3922.5601 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 120 | 100 | 100 | 120 | 100
21 | DLP Strategy Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-15 10:00 | 8d 5h | 5638.6801 | 0 | 0 | 0 | 0 | 5638.6801 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 172.5 | 100 | 100 | 172.5 | 100
22 | DLP Strategy approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-07-29 10:00 | 4d 6h | 1552.68 | 1716.12 | 5d 2h | 0 | 0 | 1552.68 | 1716.12 | 47.5% | Started | 1552.68 | 3268.8 | 100 | 47.5 | 47.5 | 100 | 47.5 | 47.5
122 | B. High level implementation plan | 2013-05-09 08:00 | 2013-07-24 17:00 | 55d |  |  | 0 |  |  | 67010.401 |  | 53d 3h | [5 empty] | 75877.0211 |  | 100% |  | 67010.401 | 67010.401
23 | Define HL Implementation plan output | 2013-05-09 08:00 | 2013-05-09 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-09 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
24 | Initial HL Implementation plan workshop | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-13 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
131 | HL Implementation plan Document writing | 2013-05-23 08:00 | 2013-06-03 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 8d | [5 empty] | 39225.6006 |  | 100% |  | 26150.4004 | 26150.4004
25 | B.1 Roadmap towards a full DLP implementation | 2013-05-23 08:00 | 2013-05-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-23 08:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 200 | 100 | 100 | 200 | 100
26 | B.2 Communication plan to stakeholders | 2013-05-27 08:00 | 2013-05-28 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
27 | B.3 integration in exisiting architecture | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-29 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
28 | B.4 Security controls for the enforcement of the policy | 2013-05-31 08:00 | 2013-06-03 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-31 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
29 | Follow-up HL Implementation plan workshop | 2013-06-12 08:00 | 2013-06-14 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-06-11 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
132 | HL Implementation plan Document writing | 2013-06-17 08:00 | 2013-06-20 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 3d | [5 empty] | 11440.8002 |  | 100% |  | 13075.2002 | 13075.2002
30 | B.1 Roadmap towards a full DLP implementation | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-14 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
31 | B.2 Communication plan to stakeholders | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-14 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
32 | B.3 integration in existing architecture | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
33 | B.4 Security controls for the enforcement of the policy | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 1d | 1634.4 | 0 | 0 | 0 | 0 | 1634.4 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 50 | 100 | 100 | 50 | 100
34 | HL Implementation plan Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-01 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
35 | HL Implementation plan Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-15 10:00 | 6d | 3922.5601 | 0 | 0 | 0 | 0 | 3922.5601 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 120 | 100 | 100 | 120 | 100
36 | HL Implementation plan approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-07-23 10:00 | 1h | 40.86 | 0 | 0 | 0 | 0 | 40.86 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 1.25 | 100 | 100 | 1.25 | 100
123 | D. Technical directives | 2013-06-27 08:00 | 2013-09-10 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 57d | [5 empty] | 111752.1017 |  | 80.79% |  | 54139.5008 | 60472.8009
37 | Define Technical directives output | 2013-06-27 08:00 | 2013-06-27 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-07-01 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
38 | Initial Technical directives workshop | 2013-06-28 08:00 | 2013-07-02 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-13 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
133 | Technical directives Document writing | 2013-07-03 08:00 | 2013-07-18 17:00 | 12d |  |  | 0 |  |  | 22881.6003 |  | 6d | [5 empty] | 65376.001 |  | 100% |  | 22881.6003 | 22881.6003
39 | D.1 Device/Port control rules | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-16 08:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 400 | 100 | 100 | 400 | 100
40 | D.2 DLP rules | 2013-07-09 08:00 | 2013-07-10 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 250 | 100 | 100 | 250 | 100
41 | D.3 Encryption rules | 2013-07-17 08:00 | 2013-07-18 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 250 | 100 | 100 | 250 | 100
42 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 6d | 19612.8003 | 0 | 0 | 0 | 0 | 19612.8003 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 300 | 100 | 100 | 300 | 100
43 | Rule set v1 | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 1h | 408.6 | 0 | 0 | 0 | 0 | 408.6 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 12.5 | 100 | 100 | 12.5 | 100
44 | Follow-up Technical directives workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-07-22 08:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
134 | Technical directives Document writing | 2013-07-24 08:00 | 2013-07-26 17:00 | 3d |  |  | 0 |  |  | 13075.2002 |  | 5d 1h | [5 empty] | 24720.3004 |  | 76.56% |  | 10010.7001 | 13075.2002
45 | D.1 Device /Port control rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 250 | 100 | 100 | 250 | 100
46 | D.2 DLP rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 250 | 100 | 100 | 250 | 100
47 | D.3 Encryption rules | 2013-07-25 08:00 | 2013-07-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 4d | 6537.6001 | 6537.6001 | 4d | 0 | 0 | 6537.6001 | 6537.6001 | 50% | Started | 1634.4 | 3268.8 | 100 | 200 | 50 | 100 | 200 | 50
48 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-08-01 16:00 | 1d 1h | 1838.7 | 1430.1 | 7h | 0 | 0 | 1838.7 | 1430.1 | 56.25% | Started | 1838.7 | 3268.8 | 100 | 56.25 | 56.25 | 100 | 56.25 | 56.25
49 | Technical directives Document review | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 3268.8 | 100 |  | 0 | 100 |  | 0
50 | Technical directives Fix document | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Technical directives approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | C. High Level Solution Design for Data Tagging and Information Classification | 2013-05-03 08:00 | 2013-09-10 17:00 | 93d |  |  | 0 |  |  | 67010.401 |  | 53d | [5 empty] | 84988.8013 |  | 83.2% |  | 55751.2009 | 35956.8005
52 | Define Data tagging HL Solution output | 2013-07-04 08:00 | 2013-07-04 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-06-19 09:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 200 | 100 | 100 | 200 | 100
53 | Initial Data tagging HL Solution workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-17 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
135 | DLP Data tagging HL Solution Document writing | 2013-07-26 08:00 | 2013-08-06 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 5d | [5 empty] | 13075.2002 |  | 100% |  | 26150.4004 | 19612.8003
54 | C.1 High-level solution design | 2013-07-26 08:00 | 2013-07-29 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-22 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
55 | C.2 Organization & Roles | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
56 | C.3 Discovery of Classified Information | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
57 | C.4 Control for tagging and classification | 2013-08-05 08:00 | 2013-08-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-28 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 50 | 100 | 100 | 50 | 100
58 | Follow-up Data tagging HL Solution workshop | 2013-08-07 08:00 | 2013-08-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-07-11 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 4903.2001 | 0 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
136 | DLP Data tagging HL Solution Document writing | 2013-05-03 08:00 | 2013-08-13 17:00 | 73d |  |  | 0 |  |  | 13075.2002 |  | 15d | [5 empty] | 52300.8008 |  | 88.89% |  | 11622.4003 | 3268.8
59 | C.1 High-level solution design | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 8d | 13075.2002 | 1634.4 | 1d | 0 | 0 | 13075.2002 | 1634.4 | 88.89% | Started | 2905.6001 | 0 | 100 | 400 | 88.8889 | 100 | 400 | 88.8889
60 | C.2 Organization & Roles | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 8d | 13075.2002 | 1634.4 | 1d | 0 | 0 | 13075.2002 | 1634.4 | 88.89% | Started | 2905.6001 | 3268.8 | 100 | 400 | 88.8889 | 100 | 400 | 88.8889
61 | C.3 Discovery of Classified Information | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 8d | 13075.2002 | 1634.4 | 1d | 0 | 0 | 13075.2002 | 1634.4 | 88.89% | Started | 2905.6001 | 0 | 100 | 400 | 88.8889 | 100 | 400 | 88.8889
62 | C.4 Control for tagging and classification | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 8d | 13075.2002 | 1634.4 | 1d | 0 | 0 | 13075.2002 | 1634.4 | 88.89% | Started | 2905.6001 | 0 | 100 | 400 | 88.8889 | 100 | 400 | 88.8889
63 | DLP Data tagging HL Solution Document review | 2013-08-14 08:00 | 2013-08-20 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | DLP Data tagging HL Solution Fix document | 2013-08-21 08:00 | 2013-08-27 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | DLP Data tagging HL Solution approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | H. Migration Strategy and a high level Implementation Package | 2013-05-03 08:00 | 2013-11-12 17:00 | 138d |  |  | 0 |  |  | 97737.1215 |  | 64d | [5 empty] | 693639.3704 |  | 54.18% |  | 52954.5609 | 9806.4001
66 | Define Migration Strategy output | 2013-08-20 08:00 | 2013-08-20 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Initial Migration Strategy workshop | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 |  | 0 | 0 | 9806.4001 | 3d | 0 | 0 | 0 | 9806.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Migration Strategy Document writing | 2013-05-03 08:00 | 2013-09-23 17:00 | 102d |  |  | 0 |  |  | 39225.6006 |  | 52d | [5 empty] | 679910.4102 |  | 100% |  | 39225.6006 | 6537.6001
68 | H.1 Preparation guide | 2013-09-10 08:00 | 2013-09-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 46d | 150364.8022 | 0 | 0 | 0 | 0 | 150364.8022 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 2300 | 100 | 100 | 2300 | 100
69 | H.2 Installation guide | 2013-09-12 08:00 | 2013-09-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 52d | 169977.6025 | 0 | 0 | 0 | 0 | 169977.6025 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 2600 | 100 | 100 | 2600 | 100
70 | H.5 Uninstallation guide | 2013-09-16 08:00 | 2013-09-17 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 52d | 169977.6025 | 0 | 0 | 0 | 0 | 169977.6025 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 2600 | 100 | 100 | 2600 | 100
71 | H.6 Training Needs Analysis | 2013-09-18 08:00 | 2013-09-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 12d | 39225.6006 | 0 | 0 | 0 | 0 | 39225.6006 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 600 | 100 | 100 | 600 | 100
72 | H.7 Dashboards | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 22d | 71913.6011 | 0 | 0 | 0 | 0 | 71913.6011 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 1100 | 100 | 100 | 1100 | 100
73 | H.8 Measurement Methods | 2013-09-20 08:00 | 2013-09-23 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 24d | 78451.2012 | 0 | 0 | 0 | 0 | 78451.2012 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 1200 | 100 | 100 | 1200 | 100
74 | Follow-up Migration Strategy workshop | 2013-09-30 08:00 | 2013-10-02 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-06-25 08:00 | 2d | 3268.8 | 1634.4 | 1d | 0 | 0 | 3268.8 | 1634.4 | 66.67% | Started | 3268.8001 | 0 | 100 | 66.6667 | 66.6667 | 100 | 66.6667 | 66.6667
138 | Migration Strategy Document writing | 2013-05-07 08:00 | 2013-10-08 17:00 | 111d |  |  | 0 |  |  | 17651.5203 |  | 64d | [5 empty] | 10460.1602 |  | 59.26% |  | 10460.1602 | 3268.8
75 | H.1 Preparation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-28 08:00 | 1d | 1634.4 | 1634.4 | 1d | 0 | 0 | 1634.4 | 1634.4 | 50% | Started | 1634.4 | 0 | 100 | 50 | 50 | 100 | 50 | 50
76 | H.2 Installation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-28 08:00 | 1d | 1634.4 | 1634.4 | 1d | 0 | 0 | 1634.4 | 1634.4 | 50% | Started | 1634.4 | 0 | 100 | 50 | 50 | 100 | 50 | 50
77 | H.3 Configuration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-02 08:00 | 1d | 1634.4 | 1634.4 | 1d | 0 | 0 | 1634.4 | 1634.4 | 50% | Started | 1634.4 | 0 | 100 | 50 | 50 | 100 | 50 | 50
78 | H.4 Migration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-02 08:00 | 1d | 1634.4 | 1634.4 | 1d | 0 | 0 | 1634.4 | 1634.4 | 50% | Started | 1634.4 | 0 | 100 | 50 | 50 | 100 | 50 | 50
79 | H.5 Uninstallation guide | 2013-05-07 08:00 | 2013-05-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
80 | H.6 Training Needs Analysis | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 81.72 | 1307.52 | 1307.52 | 2013-06-28 08:00 | 1d | 653.76 | 653.76 | 1d | 0 | 0 | 653.76 | 653.76 | 50% | Started | 653.76 | 0 | 100 | 50 | 50 | 100 | 50 | 50
81 | Migration Strategy Document review | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Migration Strategy Fix document | 2013-10-16 08:00 | 2013-10-22 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Migration Strategy approval | 2013-10-30 08:00 | 2013-11-12 17:00 | 10d |  | 0 | 0 | 204.3 | 16344.0002 | 16344.0002 |  | 0 | 0 | 16344.0002 | 10d | 0 | 0 | 0 | 16344.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | E. DLP Control and Enforcement | 2013-08-14 08:00 | 2013-10-25 17:00 | 53d |  |  | 0 |  |  | 81393.1213 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
84 | Define DLP Control and Enforcement output | 2013-08-14 08:00 | 2013-08-14 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Initial DLP Control and Enforcement workshop | 2013-08-15 08:00 | 2013-08-19 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 |  | 0 | 0 | 9806.4001 | 3d | 0 | 0 | 0 | 9806.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | DLP Control and Enforcement Document writing | 2013-08-21 08:00 | 2013-08-30 17:00 | 8d |  | 0 | 0 | 408.6 | 26150.4004 | 26150.4004 |  | 0 | 0 | 26150.4004 | 8d | 0 | 0 | 0 | 26150.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | E.1 Comparion systems | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Follow-up DLP Control and Enforcement workshop | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | DLP Control and Enforcement Document writing | 2013-09-24 08:00 | 2013-09-27 17:00 | 4d |  | 0 | 0 | 408.6 | 13075.2002 | 13075.2002 |  | 0 | 0 | 13075.2002 | 4d | 0 | 0 | 0 | 13075.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | E.1 Comparion systems | 2013-09-24 08:00 | 2013-09-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | DLP Control and Enforcement Document review | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | DLP Control and Enforcement Fix document | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | DLP Control and Enforcement approval | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 98.064 | 7845.1202 | 7845.1202 |  | 0 | 0 | 7845.1202 | 10d | 0 | 0 | 0 | 7845.1202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | F. Centralized Management and Monitoring Architecture for DLP | 2013-04-12 08:00 | 2013-11-22 17:00 | 161d |  |  | 0 |  |  | 81720.0012 |  | 74d | [5 empty] | 62107.2009 |  | 52.67% |  | 43039.2009 | 53935.2008
94 | Define Mgt & Monitoring Architecture output | 2013-04-12 08:00 | 2013-04-12 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
95 | Initial Mgt & Monitoring Architecture workshop | 2013-04-15 08:00 | 2013-04-17 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-24 08:00 | 6d | 19612.8003 | 0 | 0 | 0 | 0 | 19612.8003 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 200 | 100 | 100 | 200 | 100
139 | Mgt & Monitoring Architecture Document writing | 2013-04-18 08:00 | 2013-10-14 17:00 | 128d |  |  | 0 |  |  | 32688.0005 |  | 74d | [5 empty] | 29419.2004 |  | 61.67% |  | 20157.6006 | 26150.4004
96 | F.1 Definition of organisation & roles | 2013-04-23 08:00 | 2013-04-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
97 | F.2 log specs & formats | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-07-04 14:00 | 1d | 3268.8 | 9806.4001 | 3d | 0 | 0 | 3268.8 | 9806.4001 | 25% | Started | 1634.4 | 6537.6001 | 100 | 50 | 25 | 100 | 50 | 25
98 | F.3 Central management design | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 2d | 6537.6001 | 3268.8 | 1d | 0 | 0 | 6537.6001 | 3268.8 | 66.67% | Started | 4358.4002 | 6537.6001 | 100 | 100 | 66.6667 | 100 | 100 | 66.6667
99 | F.4 Log collection design | 2013-10-11 08:00 | 2013-10-14 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-25 08:00 | 2d | 6537.6001 | 3268.8 | 1d | 0 | 0 | 6537.6001 | 3268.8 | 66.67% | Started | 4358.4002 | 0 | 100 | 100 | 66.6667 | 100 | 100 | 66.6667
100 | F.5 Integration | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-07-04 14:00 | 2d | 6537.6001 | 6537.6001 | 2d | 0 | 0 | 6537.6001 | 6537.6001 | 50% | Started | 3268.8 | 6537.6001 | 100 | 100 | 50 | 100 | 100 | 50
101 | Follow-up Mgt & Monitoring Architecture workshop | 2013-04-22 08:00 | 2013-04-24 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 4903.2001 | 100 |  | 0 | 100 |  | 0
140 | Mgt & Monitoring Architecture Document writing | 2013-04-25 08:00 | 2013-11-01 17:00 | 137d |  |  | 0 |  |  | 16344.0002 |  | 72d | [5 empty] | 9806.4001 |  | 60% |  | 9806.4001 | 9806.4001
102 | F.1 Definition of organisation & roles | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
103 | F.2 log specs & formats | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 3268.8 | 100 |  | 0 | 100 |  | 0
104 | F.3 Central management design | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
105 | F.4 Log collection design | 2013-10-29 08:00 | 2013-10-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-29 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
106 | F.5 Integration | 2013-10-31 08:00 | 2013-11-01 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Mgt & Monitoring Architecture Document review | 2013-10-22 08:00 | 2013-10-28 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Mgt & Monitoring Architecture Fix document | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 204.3 | 8172.0001 | 8172.0001 |  | 0 | 0 | 8172.0001 | 5d | 0 | 0 | 0 | 8172.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Mgt & Monitoring Architecture approval | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | G. High Level Solution for Network based DLP | 2013-11-25 08:00 | 2014-01-07 17:00 | 32d |  |  | 0 |  |  | 36447.1205 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Define HL Solution for NW based DLP output | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Initial HL Solution for NW based DLP workshop | 2013-11-26 08:00 | 2013-11-28 17:00 | 3d |  | 0 | 0 | 20.43 | 490.32 | 490.32 |  | 0 | 0 | 490.32 | 3d | 0 | 0 | 0 | 490.32 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HL Solution for NW based DLP Document writing | 2013-11-29 08:00 | 2013-12-04 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
112 | G.1 Solution Design | 2013-11-29 08:00 | 2013-12-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | G.2 Gap analysis | 2013-12-03 08:00 | 2013-12-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Follow-up HL Solution for NW based DLP workshop | 2013-12-05 08:00 | 2013-12-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | HL Solution for NW based DLP Document writing | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  |  | 0 |  |  | 6537.6001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | G.1 Solution Design | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | G.2 Gap analysis | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | HL Solution for NW based DLP Document review | 2013-12-11 08:00 | 2013-12-17 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | HL Solution for NW based DLP Fix document | 2013-12-18 08:00 | 2013-12-24 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | HL Solution for NW based DLP approval | 2013-12-25 08:00 | 2014-01-07 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2013-09-02 08:00 |  | TP Name | T5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Data Loss Prevention System | 2013-04-10 08:00 | 2014-01-07 17:00 | 195d |  |  | 0 |  |  | 584951.7689 |  | 103d | [5 empty] | 1183428.1977 |  | 69.63% |  | 407330.9426 | 395851.6859
1 | MS Kick off meeting | 2013-04-10 08:00 | 2013-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-04-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | DLP workshop | 2013-04-15 08:00 | 2013-04-15 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-04-15 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | study existing documentation | 2013-04-16 08:00 | 2013-04-22 17:00 | 5d |  | 0 | 0 | 408.6 | 16344.0002 | 16344.0002 | 2013-04-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 16344.0002 | 16344.0002 | 100 | 100 | 100 | 100 | 100 | 100
120 | Milestones | 2013-05-03 17:00 | 2013-12-30 17:00 | 171d |  |  | 0 |  |  | 0 |  | 85d | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | MS Start specific design | 2013-05-03 17:00 | 2013-05-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-05-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
5 | MS testing start | 2013-07-05 17:00 | 2013-07-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | MS testing end | 2013-09-13 17:00 | 2013-09-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | MS Deployment start | 2013-09-30 17:00 | 2013-09-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | MS Deployment end | 2013-12-30 17:00 | 2013-12-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | A. DLP Strategy | 2013-05-10 08:00 | 2013-07-24 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 61d | [5 empty] | 68317.921 |  | 100% |  | 67010.401 | 67010.401
9 | Define DLP Strategy output | 2013-05-10 08:00 | 2013-05-10 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-10 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
10 | Initial DLP Strategy workshop | 2013-05-16 08:00 | 2013-05-20 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-16 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
129 | DLP Strategy Document writing | 2013-05-21 08:00 | 2013-06-18 17:00 | 21d |  |  | 0 |  |  | 31053.6005 |  | 5d | [5 empty] | 31053.6005 |  | 100% |  | 31053.6005 | 31053.6005
11 | A.1 Technical and Organizational inputs | 2013-05-21 08:00 | 2013-05-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
12 | A.2 Data loss/leakage prevention Strategy | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
15 | Follow-up DLP Strategy workshop | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-05-21 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
13 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-10 08:00 | 2013-06-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
14 | A.4 Overarching technical policies | 2013-06-12 08:00 | 2013-06-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-24 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
130 | DLP Strategy Document writing | 2013-06-21 08:00 | 2013-06-26 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 2d | [5 empty] | 13075.2002 |  | 100% |  | 13075.2002 | 13075.2002
16 | A.1 Technical and Organizational inputs | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
17 | A.2 Data loss/leakage prevention Strategy | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
18 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
19 | A.4 Overarching technical policies | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
20 | DLP Strategy Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-06-25 08:00 | 6d | 3922.5601 | 0 | 0 | 0 | 0 | 3922.5601 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 120 | 100 | 100 | 120 | 100
21 | DLP Strategy Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-15 10:00 | 8d 5h | 5638.6801 | 0 | 0 | 0 | 0 | 5638.6801 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 172.5 | 100 | 100 | 172.5 | 100
22 | DLP Strategy approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-07-29 10:00 | 4d 6h | 1552.68 | 0 | 0 | 0 | 0 | 1552.68 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 47.5 | 100 | 100 | 47.5 | 100
122 | B. High level implementation plan | 2013-05-09 08:00 | 2013-07-24 17:00 | 55d |  |  | 0 |  |  | 67010.401 |  | 53d 3h | [5 empty] | 75877.0211 |  | 100% |  | 67010.401 | 67010.401
23 | Define HL Implementation plan output | 2013-05-09 08:00 | 2013-05-09 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-09 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
24 | Initial HL Implementation plan workshop | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-13 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
131 | HL Implementation plan Document writing | 2013-05-23 08:00 | 2013-06-03 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 8d | [5 empty] | 39225.6006 |  | 100% |  | 26150.4004 | 26150.4004
25 | B.1 Roadmap towards a full DLP implementation | 2013-05-23 08:00 | 2013-05-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-23 08:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 200 | 100 | 100 | 200 | 100
26 | B.2 Communication plan to stakeholders | 2013-05-27 08:00 | 2013-05-28 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
27 | B.3 integration in exisiting architecture | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-29 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
28 | B.4 Security controls for the enforcement of the policy | 2013-05-31 08:00 | 2013-06-03 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-31 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
29 | Follow-up HL Implementation plan workshop | 2013-06-12 08:00 | 2013-06-14 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-06-11 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
132 | HL Implementation plan Document writing | 2013-06-17 08:00 | 2013-06-20 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 3d | [5 empty] | 11440.8002 |  | 100% |  | 13075.2002 | 13075.2002
30 | B.1 Roadmap towards a full DLP implementation | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-14 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
31 | B.2 Communication plan to stakeholders | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-14 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
32 | B.3 integration in existing architecture | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
33 | B.4 Security controls for the enforcement of the policy | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 1d | 1634.4 | 0 | 0 | 0 | 0 | 1634.4 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 50 | 100 | 100 | 50 | 100
34 | HL Implementation plan Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-01 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
35 | HL Implementation plan Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-15 10:00 | 6d | 3922.5601 | 0 | 0 | 0 | 0 | 3922.5601 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 120 | 100 | 100 | 120 | 100
36 | HL Implementation plan approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-07-23 10:00 | 1h | 40.86 | 0 | 0 | 0 | 0 | 40.86 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 1.25 | 100 | 100 | 1.25 | 100
123 | D. Technical directives | 2013-06-27 08:00 | 2013-09-10 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 77d | [5 empty] | 128545.5619 |  | 97.13% |  | 65087.5775 | 64722.241
37 | Define Technical directives output | 2013-06-27 08:00 | 2013-06-27 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-07-01 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
38 | Initial Technical directives workshop | 2013-06-28 08:00 | 2013-07-02 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-13 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
133 | Technical directives Document writing | 2013-07-03 08:00 | 2013-07-18 17:00 | 12d |  |  | 0 |  |  | 22881.6003 |  | 6d | [5 empty] | 65376.001 |  | 100% |  | 22881.6003 | 22881.6003
39 | D.1 Device/Port control rules | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-16 08:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 400 | 100 | 100 | 400 | 100
40 | D.2 DLP rules | 2013-07-09 08:00 | 2013-07-10 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 250 | 100 | 100 | 250 | 100
41 | D.3 Encryption rules | 2013-07-17 08:00 | 2013-07-18 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 250 | 100 | 100 | 250 | 100
42 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 6d | 19612.8003 | 0 | 0 | 0 | 0 | 19612.8003 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 300 | 100 | 100 | 300 | 100
43 | Rule set v1 | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 1h | 408.6 | 0 | 0 | 0 | 0 | 408.6 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 12.5 | 100 | 100 | 12.5 | 100
44 | Follow-up Technical directives workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-07-22 08:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
134 | Technical directives Document writing | 2013-07-24 08:00 | 2013-07-26 17:00 | 3d |  |  | 0 |  |  | 13075.2002 |  | 8d | [5 empty] | 32688.0005 |  | 100% |  | 13075.2002 | 13075.2002
45 | D.1 Device /Port control rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 250 | 100 | 100 | 250 | 100
46 | D.2 DLP rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 250 | 100 | 100 | 250 | 100
47 | D.3 Encryption rules | 2013-07-25 08:00 | 2013-07-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 8d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 400 | 100 | 100 | 400 | 100
48 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-08-01 16:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
49 | Technical directives Document review | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-08 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
50 | Technical directives Fix document | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-15 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
51 | Technical directives approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-08-22 14:00 | 7d | 2288.16 | 3268.8 | 10d | 0 | 0 | 2288.16 | 3268.8 | 41.18% | Started | 1345.9765 | 980.64 | 100 | 70 | 41.1765 | 100 | 70 | 41.1765
124 | C. High Level Solution Design for Data Tagging and Information Classification | 2013-05-03 08:00 | 2013-09-10 17:00 | 93d |  |  | 0 |  |  | 67010.401 |  | 73d | [5 empty] | 94468.3214 |  | 97.56% |  | 65376.001 | 64722.241
52 | Define Data tagging HL Solution output | 2013-07-04 08:00 | 2013-07-04 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-06-19 09:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 200 | 100 | 100 | 200 | 100
53 | Initial Data tagging HL Solution workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-17 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
135 | DLP Data tagging HL Solution Document writing | 2013-07-26 08:00 | 2013-08-06 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 5d | [5 empty] | 13075.2002 |  | 100% |  | 26150.4004 | 26150.4004
54 | C.1 High-level solution design | 2013-07-26 08:00 | 2013-07-29 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-22 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
55 | C.2 Organization & Roles | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
56 | C.3 Discovery of Classified Information | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
57 | C.4 Control for tagging and classification | 2013-08-05 08:00 | 2013-08-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-28 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
58 | Follow-up Data tagging HL Solution workshop | 2013-08-07 08:00 | 2013-08-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-07-11 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
136 | DLP Data tagging HL Solution Document writing | 2013-05-03 08:00 | 2013-08-13 17:00 | 73d |  |  | 0 |  |  | 13075.2002 |  | 9d | [5 empty] | 58838.4009 |  | 100% |  | 13075.2002 | 13075.2002
59 | C.1 High-level solution design | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
60 | C.2 Organization & Roles | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
61 | C.3 Discovery of Classified Information | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
62 | C.4 Control for tagging and classification | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
63 | DLP Data tagging HL Solution Document review | 2013-08-14 08:00 | 2013-08-20 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-09 08:00 | 2d | 1307.52 | 0 | 0 | 0 | 0 | 1307.52 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 40 | 100 | 100 | 40 | 100
64 | DLP Data tagging HL Solution Fix document | 2013-08-21 08:00 | 2013-08-27 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-16 08:00 | 2d | 1307.52 | 0 | 0 | 0 | 0 | 1307.52 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 40 | 100 | 100 | 40 | 100
65 | DLP Data tagging HL Solution approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-08-23 08:00 | 1d | 326.88 | 326.88 | 1d | 0 | 0 | 326.88 | 326.88 | 50% | Started | 1634.4 | 980.64 | 100 | 10 | 50 | 100 | 10 | 50
125 | H. Migration Strategy and a high level Implementation Package | 2013-05-03 08:00 | 2013-11-12 17:00 | 138d |  |  | 0 |  |  | 97737.1215 |  | 84d | [5 empty] | 698542.5704 |  | 59.2% |  | 57857.7609 | 13075.2002
66 | Define Migration Strategy output | 2013-08-20 08:00 | 2013-08-20 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-08-20 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
67 | Initial Migration Strategy workshop | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 |  | 0 | 0 | 9806.4001 | 3d | 0 | 0 | 0 | 9806.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Migration Strategy Document writing | 2013-05-03 08:00 | 2013-09-23 17:00 | 102d |  |  | 0 |  |  | 39225.6006 |  | 52d | [5 empty] | 679910.4102 |  | 100% |  | 39225.6006 | 6537.6001
68 | H.1 Preparation guide | 2013-09-10 08:00 | 2013-09-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 46d | 150364.8022 | 0 | 0 | 0 | 0 | 150364.8022 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 2300 | 100 | 100 | 2300 | 100
69 | H.2 Installation guide | 2013-09-12 08:00 | 2013-09-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 52d | 169977.6025 | 0 | 0 | 0 | 0 | 169977.6025 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 2600 | 100 | 100 | 2600 | 100
70 | H.5 Uninstallation guide | 2013-09-16 08:00 | 2013-09-17 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 52d | 169977.6025 | 0 | 0 | 0 | 0 | 169977.6025 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 2600 | 100 | 100 | 2600 | 100
71 | H.6 Training Needs Analysis | 2013-09-18 08:00 | 2013-09-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 12d | 39225.6006 | 0 | 0 | 0 | 0 | 39225.6006 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 600 | 100 | 100 | 600 | 100
72 | H.7 Dashboards | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 22d | 71913.6011 | 0 | 0 | 0 | 0 | 71913.6011 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 1100 | 100 | 100 | 1100 | 100
73 | H.8 Measurement Methods | 2013-09-20 08:00 | 2013-09-23 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 24d | 78451.2012 | 0 | 0 | 0 | 0 | 78451.2012 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 1200 | 100 | 100 | 1200 | 100
74 | Follow-up Migration Strategy workshop | 2013-09-30 08:00 | 2013-10-02 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-06-25 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 0 | 100 | 100 | 100 | 100 | 100 | 100
138 | Migration Strategy Document writing | 2013-05-07 08:00 | 2013-10-08 17:00 | 111d |  |  | 0 |  |  | 17651.5203 |  | 84d | [5 empty] | 10460.1602 |  | 59.26% |  | 10460.1602 | 3268.8
75 | H.1 Preparation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-28 08:00 | 1d | 1634.4 | 1634.4 | 1d | 0 | 0 | 1634.4 | 1634.4 | 50% | Started | 1634.4 | 0 | 100 | 50 | 50 | 100 | 50 | 50
76 | H.2 Installation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-28 08:00 | 1d | 1634.4 | 1634.4 | 1d | 0 | 0 | 1634.4 | 1634.4 | 50% | Started | 1634.4 | 0 | 100 | 50 | 50 | 100 | 50 | 50
77 | H.3 Configuration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-02 08:00 | 1d | 1634.4 | 1634.4 | 1d | 0 | 0 | 1634.4 | 1634.4 | 50% | Started | 1634.4 | 0 | 100 | 50 | 50 | 100 | 50 | 50
78 | H.4 Migration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-02 08:00 | 1d | 1634.4 | 1634.4 | 1d | 0 | 0 | 1634.4 | 1634.4 | 50% | Started | 1634.4 | 0 | 100 | 50 | 50 | 100 | 50 | 50
79 | H.5 Uninstallation guide | 2013-05-07 08:00 | 2013-05-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
80 | H.6 Training Needs Analysis | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 81.72 | 1307.52 | 1307.52 | 2013-06-28 08:00 | 1d | 653.76 | 653.76 | 1d | 0 | 0 | 653.76 | 653.76 | 50% | Started | 653.76 | 0 | 100 | 50 | 50 | 100 | 50 | 50
81 | Migration Strategy Document review | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Migration Strategy Fix document | 2013-10-16 08:00 | 2013-10-22 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Migration Strategy approval | 2013-10-30 08:00 | 2013-11-12 17:00 | 10d |  | 0 | 0 | 204.3 | 16344.0002 | 16344.0002 |  | 0 | 0 | 16344.0002 | 10d | 0 | 0 | 0 | 16344.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | E. DLP Control and Enforcement | 2013-08-14 08:00 | 2013-10-25 17:00 | 53d |  |  | 0 |  |  | 81393.1213 |  | 13d | [5 empty] | 16344.0002 |  | 16.06% |  | 13075.2002 | 45763.2007
84 | Define DLP Control and Enforcement output | 2013-08-14 08:00 | 2013-08-14 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-08-14 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 200 | 100 | 100 | 200 | 100
85 | Initial DLP Control and Enforcement workshop | 2013-08-15 08:00 | 2013-08-19 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-08-28 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
86 | DLP Control and Enforcement Document writing | 2013-08-21 08:00 | 2013-08-30 17:00 | 8d |  | 0 | 0 | 408.6 | 26150.4004 | 26150.4004 |  | 0 | 0 | 26150.4004 | 8d | 0 | 0 | 0 | 26150.4004 | 0% | Not Started | 0 | 26150.4004 | 100 |  | 0 | 100 |  | 0
87 | E.1 Comparion systems | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 6537.6001 | 100 |  | 0 | 100 |  | 0
88 | Follow-up DLP Control and Enforcement workshop | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | DLP Control and Enforcement Document writing | 2013-09-24 08:00 | 2013-09-27 17:00 | 4d |  | 0 | 0 | 408.6 | 13075.2002 | 13075.2002 |  | 0 | 0 | 13075.2002 | 4d | 0 | 0 | 0 | 13075.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | E.1 Comparion systems | 2013-09-24 08:00 | 2013-09-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | DLP Control and Enforcement Document review | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | DLP Control and Enforcement Fix document | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | DLP Control and Enforcement approval | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 98.064 | 7845.1202 | 7845.1202 |  | 0 | 0 | 7845.1202 | 10d | 0 | 0 | 0 | 7845.1202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | F. Centralized Management and Monitoring Architecture for DLP | 2013-04-12 08:00 | 2013-11-22 17:00 | 161d |  |  | 0 |  |  | 81720.0012 |  | 94d | [5 empty] | 81720.0012 |  | 64% |  | 52300.8008 | 53935.2008
94 | Define Mgt & Monitoring Architecture output | 2013-04-12 08:00 | 2013-04-12 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
95 | Initial Mgt & Monitoring Architecture workshop | 2013-04-15 08:00 | 2013-04-17 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-24 08:00 | 6d | 19612.8003 | 0 | 0 | 0 | 0 | 19612.8003 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 200 | 100 | 100 | 200 | 100
139 | Mgt & Monitoring Architecture Document writing | 2013-04-18 08:00 | 2013-10-14 17:00 | 128d |  |  | 0 |  |  | 32688.0005 |  | 94d | [5 empty] | 49032.0007 |  | 90% |  | 29419.2004 | 26150.4004
96 | F.1 Definition of organisation & roles | 2013-04-23 08:00 | 2013-04-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
97 | F.2 log specs & formats | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-07-04 14:00 | 3d | 9806.4001 | 3268.8 | 1d | 0 | 0 | 9806.4001 | 3268.8 | 75% | Started | 4903.2001 | 6537.6001 | 100 | 150 | 75 | 100 | 150 | 75
98 | F.3 Central management design | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
99 | F.4 Log collection design | 2013-10-11 08:00 | 2013-10-14 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-25 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 150 | 100 | 100 | 150 | 100
100 | F.5 Integration | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-07-04 14:00 | 3d | 9806.4001 | 3268.8 | 1d | 0 | 0 | 9806.4001 | 3268.8 | 75% | Started | 4903.2001 | 6537.6001 | 100 | 150 | 75 | 100 | 150 | 75
101 | Follow-up Mgt & Monitoring Architecture workshop | 2013-04-22 08:00 | 2013-04-24 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 |  | 0 | 0 | 4903.2001 | 3d | 0 | 0 | 0 | 4903.2001 | 0% | Not Started | 0 | 4903.2001 | 100 |  | 0 | 100 |  | 0
140 | Mgt & Monitoring Architecture Document writing | 2013-04-25 08:00 | 2013-11-01 17:00 | 137d |  |  | 0 |  |  | 16344.0002 |  | 92d | [5 empty] | 9806.4001 |  | 60% |  | 9806.4001 | 9806.4001
102 | F.1 Definition of organisation & roles | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
103 | F.2 log specs & formats | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 3268.8 | 100 |  | 0 | 100 |  | 0
104 | F.3 Central management design | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
105 | F.4 Log collection design | 2013-10-29 08:00 | 2013-10-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-29 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
106 | F.5 Integration | 2013-10-31 08:00 | 2013-11-01 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Mgt & Monitoring Architecture Document review | 2013-10-22 08:00 | 2013-10-28 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Mgt & Monitoring Architecture Fix document | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 204.3 | 8172.0001 | 8172.0001 |  | 0 | 0 | 8172.0001 | 5d | 0 | 0 | 0 | 8172.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Mgt & Monitoring Architecture approval | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | G. High Level Solution for Network based DLP | 2013-11-25 08:00 | 2014-01-07 17:00 | 32d |  |  | 0 |  |  | 36447.1205 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
110 | Define HL Solution for NW based DLP output | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 1d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Initial HL Solution for NW based DLP workshop | 2013-11-26 08:00 | 2013-11-28 17:00 | 3d |  | 0 | 0 | 20.43 | 490.32 | 490.32 |  | 0 | 0 | 490.32 | 3d | 0 | 0 | 0 | 490.32 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HL Solution for NW based DLP Document writing | 2013-11-29 08:00 | 2013-12-04 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
112 | G.1 Solution Design | 2013-11-29 08:00 | 2013-12-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | G.2 Gap analysis | 2013-12-03 08:00 | 2013-12-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 |  | 0 | 0 | 6537.6001 | 2d | 0 | 0 | 0 | 6537.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Follow-up HL Solution for NW based DLP workshop | 2013-12-05 08:00 | 2013-12-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | HL Solution for NW based DLP Document writing | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  |  | 0 |  |  | 6537.6001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | G.1 Solution Design | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | G.2 Gap analysis | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | HL Solution for NW based DLP Document review | 2013-12-11 08:00 | 2013-12-17 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | HL Solution for NW based DLP Fix document | 2013-12-18 08:00 | 2013-12-24 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | HL Solution for NW based DLP approval | 2013-12-25 08:00 | 2014-01-07 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2013-10-07 08:00 |  | TP Name | T6
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Data Loss Prevention System | 2013-04-10 08:00 | 2014-01-07 17:00 | 195d |  |  | 0 |  |  | 584951.7689 |  | 128d | [5 empty] | 1288520.1192 |  | 84.8% |  | 496040.4074 | 480186.7272
1 | MS Kick off meeting | 2013-04-10 08:00 | 2013-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-04-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | DLP workshop | 2013-04-15 08:00 | 2013-04-15 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-04-15 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | study existing documentation | 2013-04-16 08:00 | 2013-04-22 17:00 | 5d |  | 0 | 0 | 408.6 | 16344.0002 | 16344.0002 | 2013-04-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 16344.0002 | 16344.0002 | 100 | 100 | 100 | 100 | 100 | 100
120 | Milestones | 2013-05-03 17:00 | 2013-12-30 17:00 | 171d |  |  | 0 |  |  | 0 |  | 110d | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | MS Start specific design | 2013-05-03 17:00 | 2013-05-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-05-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
5 | MS testing start | 2013-07-05 17:00 | 2013-07-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | MS testing end | 2013-09-13 17:00 | 2013-09-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-09-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
7 | MS Deployment start | 2013-09-30 17:00 | 2013-09-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-10-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | MS Deployment end | 2013-12-30 17:00 | 2013-12-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | A. DLP Strategy | 2013-05-10 08:00 | 2013-07-24 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 61d | [5 empty] | 68317.921 |  | 100% |  | 67010.401 | 67010.401
9 | Define DLP Strategy output | 2013-05-10 08:00 | 2013-05-10 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-10 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
10 | Initial DLP Strategy workshop | 2013-05-16 08:00 | 2013-05-20 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-16 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
129 | DLP Strategy Document writing | 2013-05-21 08:00 | 2013-06-18 17:00 | 21d |  |  | 0 |  |  | 31053.6005 |  | 5d | [5 empty] | 31053.6005 |  | 100% |  | 31053.6005 | 31053.6005
11 | A.1 Technical and Organizational inputs | 2013-05-21 08:00 | 2013-05-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
12 | A.2 Data loss/leakage prevention Strategy | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
15 | Follow-up DLP Strategy workshop | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-05-21 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
13 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-10 08:00 | 2013-06-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
14 | A.4 Overarching technical policies | 2013-06-12 08:00 | 2013-06-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-24 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
130 | DLP Strategy Document writing | 2013-06-21 08:00 | 2013-06-26 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 2d | [5 empty] | 13075.2002 |  | 100% |  | 13075.2002 | 13075.2002
16 | A.1 Technical and Organizational inputs | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
17 | A.2 Data loss/leakage prevention Strategy | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
18 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
19 | A.4 Overarching technical policies | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
20 | DLP Strategy Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-06-25 08:00 | 6d | 3922.5601 | 0 | 0 | 0 | 0 | 3922.5601 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 120 | 100 | 100 | 120 | 100
21 | DLP Strategy Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-15 10:00 | 8d 5h | 5638.6801 | 0 | 0 | 0 | 0 | 5638.6801 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 172.5 | 100 | 100 | 172.5 | 100
22 | DLP Strategy approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-07-29 10:00 | 4d 6h | 1552.68 | 0 | 0 | 0 | 0 | 1552.68 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 47.5 | 100 | 100 | 47.5 | 100
122 | B. High level implementation plan | 2013-05-09 08:00 | 2013-07-24 17:00 | 55d |  |  | 0 |  |  | 67010.401 |  | 53d 3h | [5 empty] | 75877.0211 |  | 100% |  | 67010.401 | 67010.401
23 | Define HL Implementation plan output | 2013-05-09 08:00 | 2013-05-09 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-09 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
24 | Initial HL Implementation plan workshop | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-13 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
131 | HL Implementation plan Document writing | 2013-05-23 08:00 | 2013-06-03 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 8d | [5 empty] | 39225.6006 |  | 100% |  | 26150.4004 | 26150.4004
25 | B.1 Roadmap towards a full DLP implementation | 2013-05-23 08:00 | 2013-05-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-23 08:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 200 | 100 | 100 | 200 | 100
26 | B.2 Communication plan to stakeholders | 2013-05-27 08:00 | 2013-05-28 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
27 | B.3 integration in exisiting architecture | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-29 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
28 | B.4 Security controls for the enforcement of the policy | 2013-05-31 08:00 | 2013-06-03 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-31 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
29 | Follow-up HL Implementation plan workshop | 2013-06-12 08:00 | 2013-06-14 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-06-11 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
132 | HL Implementation plan Document writing | 2013-06-17 08:00 | 2013-06-20 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 3d | [5 empty] | 11440.8002 |  | 100% |  | 13075.2002 | 13075.2002
30 | B.1 Roadmap towards a full DLP implementation | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-14 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
31 | B.2 Communication plan to stakeholders | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-14 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
32 | B.3 integration in existing architecture | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
33 | B.4 Security controls for the enforcement of the policy | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 1d | 1634.4 | 0 | 0 | 0 | 0 | 1634.4 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 50 | 100 | 100 | 50 | 100
34 | HL Implementation plan Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-01 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
35 | HL Implementation plan Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-15 10:00 | 6d | 3922.5601 | 0 | 0 | 0 | 0 | 3922.5601 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 120 | 100 | 100 | 120 | 100
36 | HL Implementation plan approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-07-23 10:00 | 1h | 40.86 | 0 | 0 | 0 | 0 | 40.86 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 1.25 | 100 | 100 | 1.25 | 100
123 | D. Technical directives | 2013-06-27 08:00 | 2013-09-10 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 87d 5h | [5 empty] | 131814.362 |  | 100% |  | 67010.401 | 67010.401
37 | Define Technical directives output | 2013-06-27 08:00 | 2013-06-27 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-07-01 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
38 | Initial Technical directives workshop | 2013-06-28 08:00 | 2013-07-02 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-13 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
133 | Technical directives Document writing | 2013-07-03 08:00 | 2013-07-18 17:00 | 12d |  |  | 0 |  |  | 22881.6003 |  | 6d | [5 empty] | 65376.001 |  | 100% |  | 22881.6003 | 22881.6003
39 | D.1 Device/Port control rules | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-16 08:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 400 | 100 | 100 | 400 | 100
40 | D.2 DLP rules | 2013-07-09 08:00 | 2013-07-10 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 250 | 100 | 100 | 250 | 100
41 | D.3 Encryption rules | 2013-07-17 08:00 | 2013-07-18 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 250 | 100 | 100 | 250 | 100
42 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 6d | 19612.8003 | 0 | 0 | 0 | 0 | 19612.8003 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 300 | 100 | 100 | 300 | 100
43 | Rule set v1 | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 1h | 408.6 | 0 | 0 | 0 | 0 | 408.6 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 12.5 | 100 | 100 | 12.5 | 100
44 | Follow-up Technical directives workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-07-22 08:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
134 | Technical directives Document writing | 2013-07-24 08:00 | 2013-07-26 17:00 | 3d |  |  | 0 |  |  | 13075.2002 |  | 8d | [5 empty] | 32688.0005 |  | 100% |  | 13075.2002 | 13075.2002
45 | D.1 Device /Port control rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 250 | 100 | 100 | 250 | 100
46 | D.2 DLP rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 250 | 100 | 100 | 250 | 100
47 | D.3 Encryption rules | 2013-07-25 08:00 | 2013-07-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 8d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 400 | 100 | 100 | 400 | 100
48 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-08-01 16:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
49 | Technical directives Document review | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-08 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
50 | Technical directives Fix document | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-15 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
51 | Technical directives approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-08-22 14:00 | 17d | 5556.9601 | 0 | 0 | 0 | 0 | 5556.9601 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 170 | 100 | 100 | 170 | 100
124 | C. High Level Solution Design for Data Tagging and Information Classification | 2013-05-03 08:00 | 2013-09-10 17:00 | 93d |  |  | 0 |  |  | 67010.401 |  | 69d | [5 empty] | 94795.2014 |  | 100% |  | 67010.401 | 67010.401
52 | Define Data tagging HL Solution output | 2013-07-04 08:00 | 2013-07-04 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-06-19 09:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 200 | 100 | 100 | 200 | 100
53 | Initial Data tagging HL Solution workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-17 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
135 | DLP Data tagging HL Solution Document writing | 2013-07-26 08:00 | 2013-08-06 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 5d | [5 empty] | 13075.2002 |  | 100% |  | 26150.4004 | 26150.4004
54 | C.1 High-level solution design | 2013-07-26 08:00 | 2013-07-29 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-22 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
55 | C.2 Organization & Roles | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
56 | C.3 Discovery of Classified Information | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
57 | C.4 Control for tagging and classification | 2013-08-05 08:00 | 2013-08-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-28 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
58 | Follow-up Data tagging HL Solution workshop | 2013-08-07 08:00 | 2013-08-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-07-11 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
136 | DLP Data tagging HL Solution Document writing | 2013-05-03 08:00 | 2013-08-13 17:00 | 73d |  |  | 0 |  |  | 13075.2002 |  | 9d | [5 empty] | 58838.4009 |  | 100% |  | 13075.2002 | 13075.2002
59 | C.1 High-level solution design | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
60 | C.2 Organization & Roles | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
61 | C.3 Discovery of Classified Information | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
62 | C.4 Control for tagging and classification | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
63 | DLP Data tagging HL Solution Document review | 2013-08-14 08:00 | 2013-08-20 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-09 08:00 | 2d | 1307.52 | 0 | 0 | 0 | 0 | 1307.52 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 40 | 100 | 100 | 40 | 100
64 | DLP Data tagging HL Solution Fix document | 2013-08-21 08:00 | 2013-08-27 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-16 08:00 | 2d | 1307.52 | 0 | 0 | 0 | 0 | 1307.52 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 40 | 100 | 100 | 40 | 100
65 | DLP Data tagging HL Solution approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-08-23 08:00 | 2d | 653.76 | 0 | 0 | 0 | 0 | 653.76 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 20 | 100 | 100 | 20 | 100
125 | H. Migration Strategy and a high level Implementation Package | 2013-05-03 08:00 | 2013-11-12 17:00 | 138d |  |  | 0 |  |  | 97737.1215 |  | 109d | [5 empty] | 704099.5305 |  | 71.57% |  | 69952.321 | 68317.921
66 | Define Migration Strategy output | 2013-08-20 08:00 | 2013-08-20 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-08-20 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
67 | Initial Migration Strategy workshop | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-09-02 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
137 | Migration Strategy Document writing | 2013-05-03 08:00 | 2013-09-23 17:00 | 102d |  |  | 0 |  |  | 39225.6006 |  | 52d | [5 empty] | 679910.4102 |  | 100% |  | 39225.6006 | 39225.6006
68 | H.1 Preparation guide | 2013-09-10 08:00 | 2013-09-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 46d | 150364.8022 | 0 | 0 | 0 | 0 | 150364.8022 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 2300 | 100 | 100 | 2300 | 100
69 | H.2 Installation guide | 2013-09-12 08:00 | 2013-09-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 52d | 169977.6025 | 0 | 0 | 0 | 0 | 169977.6025 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 2600 | 100 | 100 | 2600 | 100
70 | H.5 Uninstallation guide | 2013-09-16 08:00 | 2013-09-17 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 52d | 169977.6025 | 0 | 0 | 0 | 0 | 169977.6025 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 2600 | 100 | 100 | 2600 | 100
71 | H.6 Training Needs Analysis | 2013-09-18 08:00 | 2013-09-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 12d | 39225.6006 | 0 | 0 | 0 | 0 | 39225.6006 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 600 | 100 | 100 | 600 | 100
72 | H.7 Dashboards | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 22d | 71913.6011 | 0 | 0 | 0 | 0 | 71913.6011 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 1100 | 100 | 100 | 1100 | 100
73 | H.8 Measurement Methods | 2013-09-20 08:00 | 2013-09-23 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 24d | 78451.2012 | 0 | 0 | 0 | 0 | 78451.2012 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 1200 | 100 | 100 | 1200 | 100
74 | Follow-up Migration Strategy workshop | 2013-09-30 08:00 | 2013-10-02 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-06-25 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
138 | Migration Strategy Document writing | 2013-05-07 08:00 | 2013-10-08 17:00 | 111d |  |  | 0 |  |  | 17651.5203 |  | 109d | [5 empty] | 12748.3202 |  | 72.22% |  | 12748.3202 | 11113.9202
75 | H.1 Preparation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-28 08:00 | 1d | 1634.4 | 1634.4 | 1d | 0 | 0 | 1634.4 | 1634.4 | 50% | Started | 1634.4 | 3268.8 | 100 | 50 | 50 | 100 | 50 | 50
76 | H.2 Installation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-28 08:00 | 1d | 1634.4 | 1634.4 | 1d | 0 | 0 | 1634.4 | 1634.4 | 50% | Started | 1634.4 | 3268.8 | 100 | 50 | 50 | 100 | 50 | 50
77 | H.3 Configuration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-02 08:00 | 1d | 1634.4 | 1634.4 | 1d | 0 | 0 | 1634.4 | 1634.4 | 50% | Started | 1634.4 | 0 | 100 | 50 | 50 | 100 | 50 | 50
78 | H.4 Migration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-02 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
79 | H.5 Uninstallation guide | 2013-05-07 08:00 | 2013-05-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
80 | H.6 Training Needs Analysis | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 81.72 | 1307.52 | 1307.52 | 2013-06-28 08:00 | 2d | 1307.52 | 0 | 0 | 0 | 0 | 1307.52 | 0 | 100% | Finished | 1307.52 | 1307.52 | 100 | 100 | 100 | 100 | 100 | 100
81 | Migration Strategy Document review | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Migration Strategy Fix document | 2013-10-16 08:00 | 2013-10-22 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Migration Strategy approval | 2013-10-30 08:00 | 2013-11-12 17:00 | 10d |  | 0 | 0 | 204.3 | 16344.0002 | 16344.0002 |  | 0 | 0 | 16344.0002 | 10d | 0 | 0 | 0 | 16344.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | E. DLP Control and Enforcement | 2013-08-14 08:00 | 2013-10-25 17:00 | 53d |  |  | 0 |  |  | 81393.1213 |  | 38d | [5 empty] | 73548.0011 |  | 62.25% |  | 50666.4008 | 70279.201
84 | Define DLP Control and Enforcement output | 2013-08-14 08:00 | 2013-08-14 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-08-14 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 200 | 100 | 100 | 200 | 100
85 | Initial DLP Control and Enforcement workshop | 2013-08-15 08:00 | 2013-08-19 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-08-28 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
86 | DLP Control and Enforcement Document writing | 2013-08-21 08:00 | 2013-08-30 17:00 | 8d |  | 0 | 0 | 408.6 | 26150.4004 | 26150.4004 | 2013-09-02 08:00 | 8d | 26150.4004 | 0 | 0 | 0 | 0 | 26150.4004 | 0 | 100% | Finished | 26150.4004 | 26150.4004 | 100 | 100 | 100 | 100 | 100 | 100
87 | E.1 Comparion systems | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-09-02 08:00 | 8d | 26150.4004 | 0 | 0 | 0 | 0 | 26150.4004 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 400 | 100 | 100 | 400 | 100
88 | Follow-up DLP Control and Enforcement workshop | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-09-18 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
89 | DLP Control and Enforcement Document writing | 2013-09-24 08:00 | 2013-09-27 17:00 | 4d |  | 0 | 0 | 408.6 | 13075.2002 | 13075.2002 |  | 0 | 0 | 13075.2002 | 4d | 0 | 0 | 0 | 13075.2002 | 0% | Not Started | 0 | 13075.2002 | 100 |  | 0 | 100 |  | 0
90 | E.1 Comparion systems | 2013-09-24 08:00 | 2013-09-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 3268.8 | 100 |  | 0 | 100 |  | 0
91 | DLP Control and Enforcement Document review | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 3268.8 | 100 |  | 0 | 100 |  | 0
92 | DLP Control and Enforcement Fix document | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | DLP Control and Enforcement approval | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 98.064 | 7845.1202 | 7845.1202 |  | 0 | 0 | 7845.1202 | 10d | 0 | 0 | 0 | 7845.1202 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | F. Centralized Management and Monitoring Architecture for DLP | 2013-04-12 08:00 | 2013-11-22 17:00 | 161d |  |  | 0 |  |  | 81720.0012 |  | 119d | [5 empty] | 97083.3615 |  | 78.8% |  | 64395.361 | 53935.2008
94 | Define Mgt & Monitoring Architecture output | 2013-04-12 08:00 | 2013-04-12 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
95 | Initial Mgt & Monitoring Architecture workshop | 2013-04-15 08:00 | 2013-04-17 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-24 08:00 | 6d | 19612.8003 | 0 | 0 | 0 | 0 | 19612.8003 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 200 | 100 | 100 | 200 | 100
139 | Mgt & Monitoring Architecture Document writing | 2013-04-18 08:00 | 2013-10-14 17:00 | 128d |  |  | 0 |  |  | 32688.0005 |  | 56d 5h | [5 empty] | 55569.6008 |  | 100% |  | 32688.0005 | 26150.4004
96 | F.1 Definition of organisation & roles | 2013-04-23 08:00 | 2013-04-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
97 | F.2 log specs & formats | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-07-04 14:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 200 | 100 | 100 | 200 | 100
98 | F.3 Central management design | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
99 | F.4 Log collection design | 2013-10-11 08:00 | 2013-10-14 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-25 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 150 | 100 | 100 | 150 | 100
100 | F.5 Integration | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-07-04 14:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 200 | 100 | 100 | 200 | 100
101 | Follow-up Mgt & Monitoring Architecture workshop | 2013-04-22 08:00 | 2013-04-24 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-10-01 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
140 | Mgt & Monitoring Architecture Document writing | 2013-04-25 08:00 | 2013-11-01 17:00 | 137d |  |  | 0 |  |  | 16344.0002 |  | 117d | [5 empty] | 13075.2002 |  | 80% |  | 13075.2002 | 9806.4001
102 | F.1 Definition of organisation & roles | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
103 | F.2 log specs & formats | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-04 08:00 | 1d | 1634.4 | 1634.4 | 1d | 0 | 0 | 1634.4 | 1634.4 | 50% | Started | 1634.4 | 3268.8 | 100 | 50 | 50 | 100 | 50 | 50
104 | F.3 Central management design | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
105 | F.4 Log collection design | 2013-10-29 08:00 | 2013-10-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-29 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
106 | F.5 Integration | 2013-10-31 08:00 | 2013-11-01 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-04 08:00 | 1d | 1634.4 | 1634.4 | 1d | 0 | 0 | 1634.4 | 1634.4 | 50% | Started | 1634.4 | 0 | 100 | 50 | 50 | 100 | 50 | 50
107 | Mgt & Monitoring Architecture Document review | 2013-10-22 08:00 | 2013-10-28 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-10-04 08:00 | 1d | 653.76 | 2615.04 | 4d | 0 | 0 | 653.76 | 2615.04 | 20% | Started | 653.76 | 0 | 100 | 20 | 20 | 100 | 20 | 20
108 | Mgt & Monitoring Architecture Fix document | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 204.3 | 8172.0001 | 8172.0001 |  | 0 | 0 | 8172.0001 | 5d | 0 | 0 | 0 | 8172.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Mgt & Monitoring Architecture approval | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | G. High Level Solution for Network based DLP | 2013-11-25 08:00 | 2014-01-07 17:00 | 32d |  |  | 0 |  |  | 36447.1205 |  | 16d 4h | [5 empty] | 23371.9203 |  | 64.13% |  | 23371.9203 | 0
110 | Define HL Solution for NW based DLP output | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-09-12 13:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
111 | Initial HL Solution for NW based DLP workshop | 2013-11-26 08:00 | 2013-11-28 17:00 | 3d |  | 0 | 0 | 20.43 | 490.32 | 490.32 | 2013-09-13 13:00 | 3d | 490.32 | 0 | 0 | 0 | 0 | 490.32 | 0 | 100% | Finished | 490.32 | 0 | 100 | 100 | 100 | 100 | 100 | 100
141 | HL Solution for NW based DLP Document writing | 2013-11-29 08:00 | 2013-12-04 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 4d | [5 empty] | 13075.2002 |  | 100% |  | 13075.2002 | 0
112 | G.1 Solution Design | 2013-11-29 08:00 | 2013-12-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-09-25 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 100 | 100 | 100 | 100 | 100
113 | G.2 Gap analysis | 2013-12-03 08:00 | 2013-12-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-09-27 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 100 | 100 | 100 | 100 | 100
114 | Follow-up HL Solution for NW based DLP workshop | 2013-12-05 08:00 | 2013-12-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-01 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
142 | HL Solution for NW based DLP Document writing | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  |  | 0 |  |  | 6537.6001 |  | 2d | [5 empty] | 3268.8 |  | 50% |  | 3268.8 | 0
115 | G.1 Solution Design | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-03 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
116 | G.2 Gap analysis | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 2d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | HL Solution for NW based DLP Document review | 2013-12-11 08:00 | 2013-12-17 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | HL Solution for NW based DLP Fix document | 2013-12-18 08:00 | 2013-12-24 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | HL Solution for NW based DLP approval | 2013-12-25 08:00 | 2014-01-07 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 10d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2013-11-04 08:00 |  | TP Name | T7
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Data Loss Prevention System | 2013-04-10 08:00 | 2014-01-07 17:00 | 195d |  |  | 0 |  |  | 584951.7689 |  | 148d | [5 empty] | 1401947.4809 |  | 93.89% |  | 549212.8882 | 525623.048
1 | MS Kick off meeting | 2013-04-10 08:00 | 2013-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-04-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | DLP workshop | 2013-04-15 08:00 | 2013-04-15 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-04-15 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | study existing documentation | 2013-04-16 08:00 | 2013-04-22 17:00 | 5d |  | 0 | 0 | 408.6 | 16344.0002 | 16344.0002 | 2013-04-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 16344.0002 | 16344.0002 | 100 | 100 | 100 | 100 | 100 | 100
120 | Milestones | 2013-05-03 17:00 | 2013-12-30 17:00 | 171d |  |  | 0 |  |  | 0 |  | 130d | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | MS Start specific design | 2013-05-03 17:00 | 2013-05-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-05-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
5 | MS testing start | 2013-07-05 17:00 | 2013-07-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | MS testing end | 2013-09-13 17:00 | 2013-09-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-09-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
7 | MS Deployment start | 2013-09-30 17:00 | 2013-09-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-10-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | MS Deployment end | 2013-12-30 17:00 | 2013-12-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | A. DLP Strategy | 2013-05-10 08:00 | 2013-07-24 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 61d | [5 empty] | 68317.921 |  | 100% |  | 67010.401 | 67010.401
9 | Define DLP Strategy output | 2013-05-10 08:00 | 2013-05-10 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-10 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
10 | Initial DLP Strategy workshop | 2013-05-16 08:00 | 2013-05-20 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-16 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
129 | DLP Strategy Document writing | 2013-05-21 08:00 | 2013-06-18 17:00 | 21d |  |  | 0 |  |  | 31053.6005 |  | 5d | [5 empty] | 31053.6005 |  | 100% |  | 31053.6005 | 31053.6005
11 | A.1 Technical and Organizational inputs | 2013-05-21 08:00 | 2013-05-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
12 | A.2 Data loss/leakage prevention Strategy | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
15 | Follow-up DLP Strategy workshop | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-05-21 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
13 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-10 08:00 | 2013-06-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
14 | A.4 Overarching technical policies | 2013-06-12 08:00 | 2013-06-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-24 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
130 | DLP Strategy Document writing | 2013-06-21 08:00 | 2013-06-26 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 2d | [5 empty] | 13075.2002 |  | 100% |  | 13075.2002 | 13075.2002
16 | A.1 Technical and Organizational inputs | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
17 | A.2 Data loss/leakage prevention Strategy | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
18 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
19 | A.4 Overarching technical policies | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
20 | DLP Strategy Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-06-25 08:00 | 6d | 3922.5601 | 0 | 0 | 0 | 0 | 3922.5601 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 120 | 100 | 100 | 120 | 100
21 | DLP Strategy Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-15 10:00 | 8d 5h | 5638.6801 | 0 | 0 | 0 | 0 | 5638.6801 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 172.5 | 100 | 100 | 172.5 | 100
22 | DLP Strategy approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-07-29 10:00 | 4d 6h | 1552.68 | 0 | 0 | 0 | 0 | 1552.68 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 47.5 | 100 | 100 | 47.5 | 100
122 | B. High level implementation plan | 2013-05-09 08:00 | 2013-07-24 17:00 | 55d |  |  | 0 |  |  | 67010.401 |  | 53d 3h | [5 empty] | 75877.0211 |  | 100% |  | 67010.401 | 67010.401
23 | Define HL Implementation plan output | 2013-05-09 08:00 | 2013-05-09 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-09 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
24 | Initial HL Implementation plan workshop | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-13 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
131 | HL Implementation plan Document writing | 2013-05-23 08:00 | 2013-06-03 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 8d | [5 empty] | 39225.6006 |  | 100% |  | 26150.4004 | 26150.4004
25 | B.1 Roadmap towards a full DLP implementation | 2013-05-23 08:00 | 2013-05-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-23 08:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 200 | 100 | 100 | 200 | 100
26 | B.2 Communication plan to stakeholders | 2013-05-27 08:00 | 2013-05-28 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
27 | B.3 integration in exisiting architecture | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-29 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
28 | B.4 Security controls for the enforcement of the policy | 2013-05-31 08:00 | 2013-06-03 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-31 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
29 | Follow-up HL Implementation plan workshop | 2013-06-12 08:00 | 2013-06-14 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-06-11 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
132 | HL Implementation plan Document writing | 2013-06-17 08:00 | 2013-06-20 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 3d | [5 empty] | 11440.8002 |  | 100% |  | 13075.2002 | 13075.2002
30 | B.1 Roadmap towards a full DLP implementation | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-14 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
31 | B.2 Communication plan to stakeholders | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-14 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
32 | B.3 integration in existing architecture | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
33 | B.4 Security controls for the enforcement of the policy | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 1d | 1634.4 | 0 | 0 | 0 | 0 | 1634.4 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 50 | 100 | 100 | 50 | 100
34 | HL Implementation plan Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-01 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
35 | HL Implementation plan Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-15 10:00 | 6d | 3922.5601 | 0 | 0 | 0 | 0 | 3922.5601 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 120 | 100 | 100 | 120 | 100
36 | HL Implementation plan approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-07-23 10:00 | 1h | 40.86 | 0 | 0 | 0 | 0 | 40.86 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 1.25 | 100 | 100 | 1.25 | 100
123 | D. Technical directives | 2013-06-27 08:00 | 2013-09-10 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 87d 5h | [5 empty] | 131814.362 |  | 100% |  | 67010.401 | 67010.401
37 | Define Technical directives output | 2013-06-27 08:00 | 2013-06-27 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-07-01 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
38 | Initial Technical directives workshop | 2013-06-28 08:00 | 2013-07-02 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-13 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
133 | Technical directives Document writing | 2013-07-03 08:00 | 2013-07-18 17:00 | 12d |  |  | 0 |  |  | 22881.6003 |  | 6d | [5 empty] | 65376.001 |  | 100% |  | 22881.6003 | 22881.6003
39 | D.1 Device/Port control rules | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-16 08:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 400 | 100 | 100 | 400 | 100
40 | D.2 DLP rules | 2013-07-09 08:00 | 2013-07-10 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 250 | 100 | 100 | 250 | 100
41 | D.3 Encryption rules | 2013-07-17 08:00 | 2013-07-18 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 250 | 100 | 100 | 250 | 100
42 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 6d | 19612.8003 | 0 | 0 | 0 | 0 | 19612.8003 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 300 | 100 | 100 | 300 | 100
43 | Rule set v1 | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 1h | 408.6 | 0 | 0 | 0 | 0 | 408.6 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 12.5 | 100 | 100 | 12.5 | 100
44 | Follow-up Technical directives workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-07-22 08:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
134 | Technical directives Document writing | 2013-07-24 08:00 | 2013-07-26 17:00 | 3d |  |  | 0 |  |  | 13075.2002 |  | 8d | [5 empty] | 32688.0005 |  | 100% |  | 13075.2002 | 13075.2002
45 | D.1 Device /Port control rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 250 | 100 | 100 | 250 | 100
46 | D.2 DLP rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 250 | 100 | 100 | 250 | 100
47 | D.3 Encryption rules | 2013-07-25 08:00 | 2013-07-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 8d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 400 | 100 | 100 | 400 | 100
48 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-08-01 16:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
49 | Technical directives Document review | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-08 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
50 | Technical directives Fix document | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-15 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
51 | Technical directives approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-08-22 14:00 | 17d | 5556.9601 | 0 | 0 | 0 | 0 | 5556.9601 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 170 | 100 | 100 | 170 | 100
124 | C. High Level Solution Design for Data Tagging and Information Classification | 2013-05-03 08:00 | 2013-09-10 17:00 | 93d |  |  | 0 |  |  | 67010.401 |  | 69d | [5 empty] | 94795.2014 |  | 100% |  | 67010.401 | 67010.401
52 | Define Data tagging HL Solution output | 2013-07-04 08:00 | 2013-07-04 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-06-19 09:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 200 | 100 | 100 | 200 | 100
53 | Initial Data tagging HL Solution workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-17 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
135 | DLP Data tagging HL Solution Document writing | 2013-07-26 08:00 | 2013-08-06 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 5d | [5 empty] | 13075.2002 |  | 100% |  | 26150.4004 | 26150.4004
54 | C.1 High-level solution design | 2013-07-26 08:00 | 2013-07-29 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-22 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
55 | C.2 Organization & Roles | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
56 | C.3 Discovery of Classified Information | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
57 | C.4 Control for tagging and classification | 2013-08-05 08:00 | 2013-08-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-28 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
58 | Follow-up Data tagging HL Solution workshop | 2013-08-07 08:00 | 2013-08-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-07-11 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
136 | DLP Data tagging HL Solution Document writing | 2013-05-03 08:00 | 2013-08-13 17:00 | 73d |  |  | 0 |  |  | 13075.2002 |  | 9d | [5 empty] | 58838.4009 |  | 100% |  | 13075.2002 | 13075.2002
59 | C.1 High-level solution design | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
60 | C.2 Organization & Roles | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
61 | C.3 Discovery of Classified Information | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
62 | C.4 Control for tagging and classification | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
63 | DLP Data tagging HL Solution Document review | 2013-08-14 08:00 | 2013-08-20 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-09 08:00 | 2d | 1307.52 | 0 | 0 | 0 | 0 | 1307.52 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 40 | 100 | 100 | 40 | 100
64 | DLP Data tagging HL Solution Fix document | 2013-08-21 08:00 | 2013-08-27 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-16 08:00 | 2d | 1307.52 | 0 | 0 | 0 | 0 | 1307.52 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 40 | 100 | 100 | 40 | 100
65 | DLP Data tagging HL Solution approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-08-23 08:00 | 2d | 653.76 | 0 | 0 | 0 | 0 | 653.76 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 20 | 100 | 100 | 20 | 100
125 | H. Migration Strategy and a high level Implementation Package | 2013-05-03 08:00 | 2013-11-12 17:00 | 138d |  |  | 0 |  |  | 97737.1215 |  | 129d | [5 empty] | 713579.0507 |  | 78.93% |  | 77143.6811 | 86296.3213
66 | Define Migration Strategy output | 2013-08-20 08:00 | 2013-08-20 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-08-20 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
67 | Initial Migration Strategy workshop | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-09-02 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
137 | Migration Strategy Document writing | 2013-05-03 08:00 | 2013-09-23 17:00 | 102d |  |  | 0 |  |  | 39225.6006 |  | 52d | [5 empty] | 679910.4102 |  | 100% |  | 39225.6006 | 39225.6006
68 | H.1 Preparation guide | 2013-09-10 08:00 | 2013-09-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 46d | 150364.8022 | 0 | 0 | 0 | 0 | 150364.8022 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 2300 | 100 | 100 | 2300 | 100
69 | H.2 Installation guide | 2013-09-12 08:00 | 2013-09-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 52d | 169977.6025 | 0 | 0 | 0 | 0 | 169977.6025 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 2600 | 100 | 100 | 2600 | 100
70 | H.5 Uninstallation guide | 2013-09-16 08:00 | 2013-09-17 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 52d | 169977.6025 | 0 | 0 | 0 | 0 | 169977.6025 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 2600 | 100 | 100 | 2600 | 100
71 | H.6 Training Needs Analysis | 2013-09-18 08:00 | 2013-09-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 12d | 39225.6006 | 0 | 0 | 0 | 0 | 39225.6006 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 600 | 100 | 100 | 600 | 100
72 | H.7 Dashboards | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 22d | 71913.6011 | 0 | 0 | 0 | 0 | 71913.6011 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 1100 | 100 | 100 | 1100 | 100
73 | H.8 Measurement Methods | 2013-09-20 08:00 | 2013-09-23 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 24d | 78451.2012 | 0 | 0 | 0 | 0 | 78451.2012 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 1200 | 100 | 100 | 1200 | 100
74 | Follow-up Migration Strategy workshop | 2013-09-30 08:00 | 2013-10-02 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-06-25 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
138 | Migration Strategy Document writing | 2013-05-07 08:00 | 2013-10-08 17:00 | 111d |  |  | 0 |  |  | 17651.5203 |  | 42d | [5 empty] | 17651.5203 |  | 100% |  | 17651.5203 | 17651.5203
75 | H.1 Preparation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-28 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
76 | H.2 Installation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-28 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
77 | H.3 Configuration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-02 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
78 | H.4 Migration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-02 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
79 | H.5 Uninstallation guide | 2013-05-07 08:00 | 2013-05-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
80 | H.6 Training Needs Analysis | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 81.72 | 1307.52 | 1307.52 | 2013-06-28 08:00 | 2d | 1307.52 | 0 | 0 | 0 | 0 | 1307.52 | 0 | 100% | Finished | 1307.52 | 1307.52 | 100 | 100 | 100 | 100 | 100 | 100
81 | Migration Strategy Document review | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-10-23 08:00 | 7d | 4576.3201 | 1961.28 | 3d | 0 | 0 | 4576.3201 | 1961.28 | 70% | Started | 2288.16 | 3268.8 | 100 | 140 | 70 | 100 | 140 | 70
82 | Migration Strategy Fix document | 2013-10-16 08:00 | 2013-10-22 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 3268.8 | 100 |  | 0 | 100 |  | 0
83 | Migration Strategy approval | 2013-10-30 08:00 | 2013-11-12 17:00 | 10d |  | 0 | 0 | 204.3 | 16344.0002 | 16344.0002 |  | 0 | 0 | 16344.0002 | 10d | 0 | 0 | 0 | 16344.0002 | 0% | Not Started | 0 | 4903.2001 | 100 |  | 0 | 100 |  | 0
126 | E. DLP Control and Enforcement | 2013-08-14 08:00 | 2013-10-25 17:00 | 53d |  |  | 0 |  |  | 81393.1213 |  | 58d | [5 empty] | 150037.9222 |  | 85.01% |  | 69189.6011 | 81393.1213
84 | Define DLP Control and Enforcement output | 2013-08-14 08:00 | 2013-08-14 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-08-14 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 200 | 100 | 100 | 200 | 100
85 | Initial DLP Control and Enforcement workshop | 2013-08-15 08:00 | 2013-08-19 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-08-28 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
86 | DLP Control and Enforcement Document writing | 2013-08-21 08:00 | 2013-08-30 17:00 | 8d |  | 0 | 0 | 408.6 | 26150.4004 | 26150.4004 | 2013-09-02 08:00 | 8d | 26150.4004 | 0 | 0 | 0 | 0 | 26150.4004 | 0 | 100% | Finished | 26150.4004 | 26150.4004 | 100 | 100 | 100 | 100 | 100 | 100
87 | E.1 Comparion systems | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-09-02 08:00 | 8d | 26150.4004 | 0 | 0 | 0 | 0 | 26150.4004 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 400 | 100 | 100 | 400 | 100
88 | Follow-up DLP Control and Enforcement workshop | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-09-18 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
89 | DLP Control and Enforcement Document writing | 2013-09-24 08:00 | 2013-09-27 17:00 | 4d |  | 0 | 0 | 408.6 | 13075.2002 | 13075.2002 | 2013-10-07 10:00 | 19d | 62107.2009 | 0 | 0 | 0 | 0 | 62107.2009 | 0 | 100% | Finished | 13075.2002 | 13075.2002 | 100 | 475 | 100 | 100 | 475 | 100
90 | E.1 Comparion systems | 2013-09-24 08:00 | 2013-09-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-07 10:00 | 8d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 400 | 100 | 100 | 400 | 100
91 | DLP Control and Enforcement Document review | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-11-01 10:00 | 2d | 1307.52 | 653.76 | 1d | 0 | 0 | 1307.52 | 653.76 | 66.67% | Started | 2179.2001 | 3268.8 | 100 | 40 | 66.6667 | 100 | 40 | 66.6667
92 | DLP Control and Enforcement Fix document | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 |  | 0 | 0 | 3268.8 | 5d | 0 | 0 | 0 | 3268.8 | 0% | Not Started | 0 | 3268.8 | 100 |  | 0 | 100 |  | 0
93 | DLP Control and Enforcement approval | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 98.064 | 7845.1202 | 7845.1202 |  | 0 | 0 | 7845.1202 | 10d | 0 | 0 | 0 | 7845.1202 | 0% | Not Started | 0 | 7845.1202 | 100 |  | 0 | 100 |  | 0
127 | F. Centralized Management and Monitoring Architecture for DLP | 2013-04-12 08:00 | 2013-11-22 17:00 | 161d |  |  | 0 |  |  | 81720.0012 |  | 138d | [5 empty] | 114408.0017 |  | 100% |  | 81720.0012 | 70279.201
94 | Define Mgt & Monitoring Architecture output | 2013-04-12 08:00 | 2013-04-12 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
95 | Initial Mgt & Monitoring Architecture workshop | 2013-04-15 08:00 | 2013-04-17 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-24 08:00 | 6d | 19612.8003 | 0 | 0 | 0 | 0 | 19612.8003 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 200 | 100 | 100 | 200 | 100
139 | Mgt & Monitoring Architecture Document writing | 2013-04-18 08:00 | 2013-10-14 17:00 | 128d |  |  | 0 |  |  | 32688.0005 |  | 56d 5h | [5 empty] | 55569.6008 |  | 100% |  | 32688.0005 | 32688.0005
96 | F.1 Definition of organisation & roles | 2013-04-23 08:00 | 2013-04-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
97 | F.2 log specs & formats | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-07-04 14:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 200 | 100 | 100 | 200 | 100
98 | F.3 Central management design | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
99 | F.4 Log collection design | 2013-10-11 08:00 | 2013-10-14 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-25 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
100 | F.5 Integration | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-07-04 14:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 200 | 100 | 100 | 200 | 100
101 | Follow-up Mgt & Monitoring Architecture workshop | 2013-04-22 08:00 | 2013-04-24 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-10-01 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
140 | Mgt & Monitoring Architecture Document writing | 2013-04-25 08:00 | 2013-11-01 17:00 | 137d |  |  | 0 |  |  | 16344.0002 |  | 118d | [5 empty] | 16344.0002 |  | 100% |  | 16344.0002 | 16344.0002
102 | F.1 Definition of organisation & roles | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
103 | F.2 log specs & formats | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-04 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
104 | F.3 Central management design | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
105 | F.4 Log collection design | 2013-10-29 08:00 | 2013-10-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-29 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
106 | F.5 Integration | 2013-10-31 08:00 | 2013-11-01 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-04 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
107 | Mgt & Monitoring Architecture Document review | 2013-10-22 08:00 | 2013-10-28 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-10-04 08:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
108 | Mgt & Monitoring Architecture Fix document | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 204.3 | 8172.0001 | 8172.0001 | 2013-10-11 08:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 8172.0001 | 0 | 100 | 100 | 100 | 100 | 100 | 100
109 | Mgt & Monitoring Architecture approval | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-10-18 08:00 | 10d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
128 | G. High Level Solution for Network based DLP | 2013-11-25 08:00 | 2014-01-07 17:00 | 32d |  |  | 0 |  |  | 36447.1205 |  | 36d 4h | [5 empty] | 33505.2005 |  | 91.93% |  | 33505.2005 | 0
110 | Define HL Solution for NW based DLP output | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-09-12 13:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
111 | Initial HL Solution for NW based DLP workshop | 2013-11-26 08:00 | 2013-11-28 17:00 | 3d |  | 0 | 0 | 20.43 | 490.32 | 490.32 | 2013-09-13 13:00 | 3d | 490.32 | 0 | 0 | 0 | 0 | 490.32 | 0 | 100% | Finished | 490.32 | 0 | 100 | 100 | 100 | 100 | 100 | 100
141 | HL Solution for NW based DLP Document writing | 2013-11-29 08:00 | 2013-12-04 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 4d | [5 empty] | 13075.2002 |  | 100% |  | 13075.2002 | 0
112 | G.1 Solution Design | 2013-11-29 08:00 | 2013-12-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-09-25 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 100 | 100 | 100 | 100 | 100
113 | G.2 Gap analysis | 2013-12-03 08:00 | 2013-12-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-09-27 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 100 | 100 | 100 | 100 | 100
114 | Follow-up HL Solution for NW based DLP workshop | 2013-12-05 08:00 | 2013-12-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-01 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
142 | HL Solution for NW based DLP Document writing | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  |  | 0 |  |  | 6537.6001 |  | 4d | [5 empty] | 6537.6001 |  | 100% |  | 6537.6001 | 0
115 | G.1 Solution Design | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-03 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
116 | G.2 Gap analysis | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-07 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
117 | HL Solution for NW based DLP Document review | 2013-12-11 08:00 | 2013-12-17 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-10-09 08:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
118 | HL Solution for NW based DLP Fix document | 2013-12-18 08:00 | 2013-12-24 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-10-16 08:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
119 | HL Solution for NW based DLP approval | 2013-12-25 08:00 | 2014-01-07 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-11-01 08:00 | 1d | 326.88 | 2941.92 | 9d | 0 | 0 | 326.88 | 2941.92 | 10% | Started | 326.88 | 0 | 100 | 10 | 10 | 100 | 10 | 10

## TP8
| TP Status Date | 2013-12-02 08:00 |  | TP Name | T8
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Data Loss Prevention System | 2013-04-10 08:00 | 2014-01-07 17:00 | 195d |  |  | 0 |  |  | 584951.7689 |  | 168d | [5 empty] | 1425155.9614 |  | 100% |  | 584951.7689 | 555532.5684
1 | MS Kick off meeting | 2013-04-10 08:00 | 2013-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-04-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | DLP workshop | 2013-04-15 08:00 | 2013-04-15 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-04-15 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | study existing documentation | 2013-04-16 08:00 | 2013-04-22 17:00 | 5d |  | 0 | 0 | 408.6 | 16344.0002 | 16344.0002 | 2013-04-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 16344.0002 | 16344.0002 | 100 | 100 | 100 | 100 | 100 | 100
120 | Milestones | 2013-05-03 17:00 | 2013-12-30 17:00 | 171d |  |  | 0 |  |  | 0 |  | 150d | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | MS Start specific design | 2013-05-03 17:00 | 2013-05-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-05-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
5 | MS testing start | 2013-07-05 17:00 | 2013-07-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | MS testing end | 2013-09-13 17:00 | 2013-09-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-09-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
7 | MS Deployment start | 2013-09-30 17:00 | 2013-09-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-10-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | MS Deployment end | 2013-12-30 17:00 | 2013-12-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | A. DLP Strategy | 2013-05-10 08:00 | 2013-07-24 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 61d | [5 empty] | 68317.921 |  | 100% |  | 67010.401 | 67010.401
9 | Define DLP Strategy output | 2013-05-10 08:00 | 2013-05-10 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-10 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
10 | Initial DLP Strategy workshop | 2013-05-16 08:00 | 2013-05-20 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-16 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
129 | DLP Strategy Document writing | 2013-05-21 08:00 | 2013-06-18 17:00 | 21d |  |  | 0 |  |  | 31053.6005 |  | 5d | [5 empty] | 31053.6005 |  | 100% |  | 31053.6005 | 31053.6005
11 | A.1 Technical and Organizational inputs | 2013-05-21 08:00 | 2013-05-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
12 | A.2 Data loss/leakage prevention Strategy | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
15 | Follow-up DLP Strategy workshop | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-05-21 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
13 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-10 08:00 | 2013-06-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
14 | A.4 Overarching technical policies | 2013-06-12 08:00 | 2013-06-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-24 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
130 | DLP Strategy Document writing | 2013-06-21 08:00 | 2013-06-26 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 2d | [5 empty] | 13075.2002 |  | 100% |  | 13075.2002 | 13075.2002
16 | A.1 Technical and Organizational inputs | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
17 | A.2 Data loss/leakage prevention Strategy | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
18 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
19 | A.4 Overarching technical policies | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
20 | DLP Strategy Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-06-25 08:00 | 6d | 3922.5601 | 0 | 0 | 0 | 0 | 3922.5601 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 120 | 100 | 100 | 120 | 100
21 | DLP Strategy Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-15 10:00 | 8d 5h | 5638.6801 | 0 | 0 | 0 | 0 | 5638.6801 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 172.5 | 100 | 100 | 172.5 | 100
22 | DLP Strategy approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-07-29 10:00 | 4d 6h | 1552.68 | 0 | 0 | 0 | 0 | 1552.68 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 47.5 | 100 | 100 | 47.5 | 100
122 | B. High level implementation plan | 2013-05-09 08:00 | 2013-07-24 17:00 | 55d |  |  | 0 |  |  | 67010.401 |  | 53d 3h | [5 empty] | 75877.0211 |  | 100% |  | 67010.401 | 67010.401
23 | Define HL Implementation plan output | 2013-05-09 08:00 | 2013-05-09 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-09 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
24 | Initial HL Implementation plan workshop | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-13 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
131 | HL Implementation plan Document writing | 2013-05-23 08:00 | 2013-06-03 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 8d | [5 empty] | 39225.6006 |  | 100% |  | 26150.4004 | 26150.4004
25 | B.1 Roadmap towards a full DLP implementation | 2013-05-23 08:00 | 2013-05-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-23 08:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 200 | 100 | 100 | 200 | 100
26 | B.2 Communication plan to stakeholders | 2013-05-27 08:00 | 2013-05-28 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
27 | B.3 integration in exisiting architecture | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-29 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
28 | B.4 Security controls for the enforcement of the policy | 2013-05-31 08:00 | 2013-06-03 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-31 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
29 | Follow-up HL Implementation plan workshop | 2013-06-12 08:00 | 2013-06-14 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-06-11 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
132 | HL Implementation plan Document writing | 2013-06-17 08:00 | 2013-06-20 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 3d | [5 empty] | 11440.8002 |  | 100% |  | 13075.2002 | 13075.2002
30 | B.1 Roadmap towards a full DLP implementation | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-14 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
31 | B.2 Communication plan to stakeholders | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-14 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
32 | B.3 integration in existing architecture | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
33 | B.4 Security controls for the enforcement of the policy | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 1d | 1634.4 | 0 | 0 | 0 | 0 | 1634.4 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 50 | 100 | 100 | 50 | 100
34 | HL Implementation plan Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-01 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
35 | HL Implementation plan Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-15 10:00 | 6d | 3922.5601 | 0 | 0 | 0 | 0 | 3922.5601 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 120 | 100 | 100 | 120 | 100
36 | HL Implementation plan approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-07-23 10:00 | 1h | 40.86 | 0 | 0 | 0 | 0 | 40.86 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 1.25 | 100 | 100 | 1.25 | 100
123 | D. Technical directives | 2013-06-27 08:00 | 2013-09-10 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 87d 5h | [5 empty] | 131814.362 |  | 100% |  | 67010.401 | 67010.401
37 | Define Technical directives output | 2013-06-27 08:00 | 2013-06-27 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-07-01 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
38 | Initial Technical directives workshop | 2013-06-28 08:00 | 2013-07-02 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-13 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
133 | Technical directives Document writing | 2013-07-03 08:00 | 2013-07-18 17:00 | 12d |  |  | 0 |  |  | 22881.6003 |  | 6d | [5 empty] | 65376.001 |  | 100% |  | 22881.6003 | 22881.6003
39 | D.1 Device/Port control rules | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-16 08:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 400 | 100 | 100 | 400 | 100
40 | D.2 DLP rules | 2013-07-09 08:00 | 2013-07-10 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 250 | 100 | 100 | 250 | 100
41 | D.3 Encryption rules | 2013-07-17 08:00 | 2013-07-18 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 250 | 100 | 100 | 250 | 100
42 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 6d | 19612.8003 | 0 | 0 | 0 | 0 | 19612.8003 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 300 | 100 | 100 | 300 | 100
43 | Rule set v1 | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 1h | 408.6 | 0 | 0 | 0 | 0 | 408.6 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 12.5 | 100 | 100 | 12.5 | 100
44 | Follow-up Technical directives workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-07-22 08:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
134 | Technical directives Document writing | 2013-07-24 08:00 | 2013-07-26 17:00 | 3d |  |  | 0 |  |  | 13075.2002 |  | 8d | [5 empty] | 32688.0005 |  | 100% |  | 13075.2002 | 13075.2002
45 | D.1 Device /Port control rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 250 | 100 | 100 | 250 | 100
46 | D.2 DLP rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 250 | 100 | 100 | 250 | 100
47 | D.3 Encryption rules | 2013-07-25 08:00 | 2013-07-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 8d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 400 | 100 | 100 | 400 | 100
48 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-08-01 16:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
49 | Technical directives Document review | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-08 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
50 | Technical directives Fix document | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-15 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
51 | Technical directives approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-08-22 14:00 | 17d | 5556.9601 | 0 | 0 | 0 | 0 | 5556.9601 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 170 | 100 | 100 | 170 | 100
124 | C. High Level Solution Design for Data Tagging and Information Classification | 2013-05-03 08:00 | 2013-09-10 17:00 | 93d |  |  | 0 |  |  | 67010.401 |  | 69d | [5 empty] | 94795.2014 |  | 100% |  | 67010.401 | 67010.401
52 | Define Data tagging HL Solution output | 2013-07-04 08:00 | 2013-07-04 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-06-19 09:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 200 | 100 | 100 | 200 | 100
53 | Initial Data tagging HL Solution workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-17 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
135 | DLP Data tagging HL Solution Document writing | 2013-07-26 08:00 | 2013-08-06 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 5d | [5 empty] | 13075.2002 |  | 100% |  | 26150.4004 | 26150.4004
54 | C.1 High-level solution design | 2013-07-26 08:00 | 2013-07-29 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-22 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
55 | C.2 Organization & Roles | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
56 | C.3 Discovery of Classified Information | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
57 | C.4 Control for tagging and classification | 2013-08-05 08:00 | 2013-08-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-28 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
58 | Follow-up Data tagging HL Solution workshop | 2013-08-07 08:00 | 2013-08-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-07-11 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
136 | DLP Data tagging HL Solution Document writing | 2013-05-03 08:00 | 2013-08-13 17:00 | 73d |  |  | 0 |  |  | 13075.2002 |  | 9d | [5 empty] | 58838.4009 |  | 100% |  | 13075.2002 | 13075.2002
59 | C.1 High-level solution design | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
60 | C.2 Organization & Roles | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
61 | C.3 Discovery of Classified Information | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
62 | C.4 Control for tagging and classification | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
63 | DLP Data tagging HL Solution Document review | 2013-08-14 08:00 | 2013-08-20 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-09 08:00 | 2d | 1307.52 | 0 | 0 | 0 | 0 | 1307.52 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 40 | 100 | 100 | 40 | 100
64 | DLP Data tagging HL Solution Fix document | 2013-08-21 08:00 | 2013-08-27 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-16 08:00 | 2d | 1307.52 | 0 | 0 | 0 | 0 | 1307.52 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 40 | 100 | 100 | 40 | 100
65 | DLP Data tagging HL Solution approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-08-23 08:00 | 2d | 653.76 | 0 | 0 | 0 | 0 | 653.76 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 20 | 100 | 100 | 20 | 100
125 | H. Migration Strategy and a high level Implementation Package | 2013-05-03 08:00 | 2013-11-12 17:00 | 138d |  |  | 0 |  |  | 97737.1215 |  | 141d 4h | [5 empty] | 722077.9308 |  | 100% |  | 97737.1215 | 97737.1215
66 | Define Migration Strategy output | 2013-08-20 08:00 | 2013-08-20 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-08-20 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
67 | Initial Migration Strategy workshop | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-09-02 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
137 | Migration Strategy Document writing | 2013-05-03 08:00 | 2013-09-23 17:00 | 102d |  |  | 0 |  |  | 39225.6006 |  | 52d | [5 empty] | 679910.4102 |  | 100% |  | 39225.6006 | 39225.6006
68 | H.1 Preparation guide | 2013-09-10 08:00 | 2013-09-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 46d | 150364.8022 | 0 | 0 | 0 | 0 | 150364.8022 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 2300 | 100 | 100 | 2300 | 100
69 | H.2 Installation guide | 2013-09-12 08:00 | 2013-09-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 52d | 169977.6025 | 0 | 0 | 0 | 0 | 169977.6025 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 2600 | 100 | 100 | 2600 | 100
70 | H.5 Uninstallation guide | 2013-09-16 08:00 | 2013-09-17 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 52d | 169977.6025 | 0 | 0 | 0 | 0 | 169977.6025 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 2600 | 100 | 100 | 2600 | 100
71 | H.6 Training Needs Analysis | 2013-09-18 08:00 | 2013-09-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 12d | 39225.6006 | 0 | 0 | 0 | 0 | 39225.6006 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 600 | 100 | 100 | 600 | 100
72 | H.7 Dashboards | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 22d | 71913.6011 | 0 | 0 | 0 | 0 | 71913.6011 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 1100 | 100 | 100 | 1100 | 100
73 | H.8 Measurement Methods | 2013-09-20 08:00 | 2013-09-23 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 24d | 78451.2012 | 0 | 0 | 0 | 0 | 78451.2012 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 1200 | 100 | 100 | 1200 | 100
74 | Follow-up Migration Strategy workshop | 2013-09-30 08:00 | 2013-10-02 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-06-25 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
138 | Migration Strategy Document writing | 2013-05-07 08:00 | 2013-10-08 17:00 | 111d |  |  | 0 |  |  | 17651.5203 |  | 42d | [5 empty] | 17651.5203 |  | 100% |  | 17651.5203 | 17651.5203
75 | H.1 Preparation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-28 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
76 | H.2 Installation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-28 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
77 | H.3 Configuration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-02 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
78 | H.4 Migration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-02 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
79 | H.5 Uninstallation guide | 2013-05-07 08:00 | 2013-05-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
80 | H.6 Training Needs Analysis | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 81.72 | 1307.52 | 1307.52 | 2013-06-28 08:00 | 2d | 1307.52 | 0 | 0 | 0 | 0 | 1307.52 | 0 | 100% | Finished | 1307.52 | 1307.52 | 100 | 100 | 100 | 100 | 100 | 100
81 | Migration Strategy Document review | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-10-23 08:00 | 10d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 200 | 100 | 100 | 200 | 100
82 | Migration Strategy Fix document | 2013-10-16 08:00 | 2013-10-22 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-11-07 08:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
83 | Migration Strategy approval | 2013-10-30 08:00 | 2013-11-12 17:00 | 10d |  | 0 | 0 | 204.3 | 16344.0002 | 16344.0002 | 2013-11-18 13:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 16344.0002 | 16344.0002 | 100 | 20 | 100 | 100 | 20 | 100
126 | E. DLP Control and Enforcement | 2013-08-14 08:00 | 2013-10-25 17:00 | 53d |  |  | 0 |  |  | 81393.1213 |  | 74d 6h | [5 empty] | 161805.6025 |  | 100% |  | 81393.1213 | 81393.1213
84 | Define DLP Control and Enforcement output | 2013-08-14 08:00 | 2013-08-14 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-08-14 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 200 | 100 | 100 | 200 | 100
85 | Initial DLP Control and Enforcement workshop | 2013-08-15 08:00 | 2013-08-19 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-08-28 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
86 | DLP Control and Enforcement Document writing | 2013-08-21 08:00 | 2013-08-30 17:00 | 8d |  | 0 | 0 | 408.6 | 26150.4004 | 26150.4004 | 2013-09-02 08:00 | 8d | 26150.4004 | 0 | 0 | 0 | 0 | 26150.4004 | 0 | 100% | Finished | 26150.4004 | 26150.4004 | 100 | 100 | 100 | 100 | 100 | 100
87 | E.1 Comparion systems | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-09-02 08:00 | 8d | 26150.4004 | 0 | 0 | 0 | 0 | 26150.4004 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 400 | 100 | 100 | 400 | 100
88 | Follow-up DLP Control and Enforcement workshop | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-09-18 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
89 | DLP Control and Enforcement Document writing | 2013-09-24 08:00 | 2013-09-27 17:00 | 4d |  | 0 | 0 | 408.6 | 13075.2002 | 13075.2002 | 2013-10-07 10:00 | 19d | 62107.2009 | 0 | 0 | 0 | 0 | 62107.2009 | 0 | 100% | Finished | 13075.2002 | 13075.2002 | 100 | 475 | 100 | 100 | 475 | 100
90 | E.1 Comparion systems | 2013-09-24 08:00 | 2013-09-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-07 10:00 | 8d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 400 | 100 | 100 | 400 | 100
91 | DLP Control and Enforcement Document review | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-11-01 10:00 | 3d | 1961.28 | 0 | 0 | 0 | 0 | 1961.28 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 60 | 100 | 100 | 60 | 100
92 | DLP Control and Enforcement Fix document | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-11-05 15:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
93 | DLP Control and Enforcement approval | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 98.064 | 7845.1202 | 7845.1202 | 2013-11-12 15:00 | 10d | 7845.1202 | 0 | 0 | 0 | 0 | 7845.1202 | 0 | 100% | Finished | 7845.1202 | 7845.1202 | 100 | 100 | 100 | 100 | 100 | 100
127 | F. Centralized Management and Monitoring Architecture for DLP | 2013-04-12 08:00 | 2013-11-22 17:00 | 161d |  |  | 0 |  |  | 81720.0012 |  | 138d | [5 empty] | 114408.0017 |  | 100% |  | 81720.0012 | 81720.0012
94 | Define Mgt & Monitoring Architecture output | 2013-04-12 08:00 | 2013-04-12 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
95 | Initial Mgt & Monitoring Architecture workshop | 2013-04-15 08:00 | 2013-04-17 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-24 08:00 | 6d | 19612.8003 | 0 | 0 | 0 | 0 | 19612.8003 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 200 | 100 | 100 | 200 | 100
139 | Mgt & Monitoring Architecture Document writing | 2013-04-18 08:00 | 2013-10-14 17:00 | 128d |  |  | 0 |  |  | 32688.0005 |  | 56d 5h | [5 empty] | 55569.6008 |  | 100% |  | 32688.0005 | 32688.0005
96 | F.1 Definition of organisation & roles | 2013-04-23 08:00 | 2013-04-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
97 | F.2 log specs & formats | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-07-04 14:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 200 | 100 | 100 | 200 | 100
98 | F.3 Central management design | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
99 | F.4 Log collection design | 2013-10-11 08:00 | 2013-10-14 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-25 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
100 | F.5 Integration | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-07-04 14:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 200 | 100 | 100 | 200 | 100
101 | Follow-up Mgt & Monitoring Architecture workshop | 2013-04-22 08:00 | 2013-04-24 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-10-01 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
140 | Mgt & Monitoring Architecture Document writing | 2013-04-25 08:00 | 2013-11-01 17:00 | 137d |  |  | 0 |  |  | 16344.0002 |  | 118d | [5 empty] | 16344.0002 |  | 100% |  | 16344.0002 | 16344.0002
102 | F.1 Definition of organisation & roles | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
103 | F.2 log specs & formats | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-04 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
104 | F.3 Central management design | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
105 | F.4 Log collection design | 2013-10-29 08:00 | 2013-10-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-29 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
106 | F.5 Integration | 2013-10-31 08:00 | 2013-11-01 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-04 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
107 | Mgt & Monitoring Architecture Document review | 2013-10-22 08:00 | 2013-10-28 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-10-04 08:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
108 | Mgt & Monitoring Architecture Fix document | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 204.3 | 8172.0001 | 8172.0001 | 2013-10-11 08:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 8172.0001 | 8172.0001 | 100 | 100 | 100 | 100 | 100 | 100
109 | Mgt & Monitoring Architecture approval | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-10-18 08:00 | 10d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
128 | G. High Level Solution for Network based DLP | 2013-11-25 08:00 | 2014-01-07 17:00 | 32d |  |  | 0 |  |  | 36447.1205 |  | 45d 4h | [5 empty] | 36447.1205 |  | 100% |  | 36447.1205 | 7027.9201
110 | Define HL Solution for NW based DLP output | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-09-12 13:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
111 | Initial HL Solution for NW based DLP workshop | 2013-11-26 08:00 | 2013-11-28 17:00 | 3d |  | 0 | 0 | 20.43 | 490.32 | 490.32 | 2013-09-13 13:00 | 3d | 490.32 | 0 | 0 | 0 | 0 | 490.32 | 0 | 100% | Finished | 490.32 | 490.32 | 100 | 100 | 100 | 100 | 100 | 100
141 | HL Solution for NW based DLP Document writing | 2013-11-29 08:00 | 2013-12-04 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 4d | [5 empty] | 13075.2002 |  | 100% |  | 13075.2002 | 3268.8
112 | G.1 Solution Design | 2013-11-29 08:00 | 2013-12-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-09-25 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
113 | G.2 Gap analysis | 2013-12-03 08:00 | 2013-12-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-09-27 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 0 | 100 | 100 | 100 | 100 | 100 | 100
114 | Follow-up HL Solution for NW based DLP workshop | 2013-12-05 08:00 | 2013-12-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-01 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
142 | HL Solution for NW based DLP Document writing | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  |  | 0 |  |  | 6537.6001 |  | 4d | [5 empty] | 6537.6001 |  | 100% |  | 6537.6001 | 0
115 | G.1 Solution Design | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-03 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
116 | G.2 Gap analysis | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-07 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
117 | HL Solution for NW based DLP Document review | 2013-12-11 08:00 | 2013-12-17 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-10-09 08:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
118 | HL Solution for NW based DLP Fix document | 2013-12-18 08:00 | 2013-12-24 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-10-16 08:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100
119 | HL Solution for NW based DLP approval | 2013-12-25 08:00 | 2014-01-07 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-11-01 08:00 | 10d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 0 | 100 | 100 | 100 | 100 | 100 | 100

## TP9
| TP Status Date | 2014-01-06 08:00 |  | TP Name | T9
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Data Loss Prevention System | 2013-04-10 08:00 | 2014-01-07 17:00 | 195d |  |  | 0 |  |  | 584951.7689 |  | 189d | [5 empty] | 1425155.9614 |  | 100% |  | 584951.7689 | 584298.0089
1 | MS Kick off meeting | 2013-04-10 08:00 | 2013-04-09 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-04-10 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | DLP workshop | 2013-04-15 08:00 | 2013-04-15 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-04-15 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
3 | study existing documentation | 2013-04-16 08:00 | 2013-04-22 17:00 | 5d |  | 0 | 0 | 408.6 | 16344.0002 | 16344.0002 | 2013-04-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 16344.0002 | 16344.0002 | 100 | 100 | 100 | 100 | 100 | 100
120 | Milestones | 2013-05-03 17:00 | 2013-12-30 17:00 | 171d |  |  | 0 |  |  | 0 |  | 171d | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | MS Start specific design | 2013-05-03 17:00 | 2013-05-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-05-06 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
5 | MS testing start | 2013-07-05 17:00 | 2013-07-05 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-07-08 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | MS testing end | 2013-09-13 17:00 | 2013-09-13 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-09-16 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
7 | MS Deployment start | 2013-09-30 17:00 | 2013-09-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-10-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | MS Deployment end | 2013-12-30 17:00 | 2013-12-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2013-12-31 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
121 | A. DLP Strategy | 2013-05-10 08:00 | 2013-07-24 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 61d | [5 empty] | 68317.921 |  | 100% |  | 67010.401 | 67010.401
9 | Define DLP Strategy output | 2013-05-10 08:00 | 2013-05-10 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-10 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
10 | Initial DLP Strategy workshop | 2013-05-16 08:00 | 2013-05-20 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-16 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
129 | DLP Strategy Document writing | 2013-05-21 08:00 | 2013-06-18 17:00 | 21d |  |  | 0 |  |  | 31053.6005 |  | 5d | [5 empty] | 31053.6005 |  | 100% |  | 31053.6005 | 31053.6005
11 | A.1 Technical and Organizational inputs | 2013-05-21 08:00 | 2013-05-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
12 | A.2 Data loss/leakage prevention Strategy | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
15 | Follow-up DLP Strategy workshop | 2013-06-14 08:00 | 2013-06-18 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-05-21 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
13 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-10 08:00 | 2013-06-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-21 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
14 | A.4 Overarching technical policies | 2013-06-12 08:00 | 2013-06-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-24 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
130 | DLP Strategy Document writing | 2013-06-21 08:00 | 2013-06-26 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 2d | [5 empty] | 13075.2002 |  | 100% |  | 13075.2002 | 13075.2002
16 | A.1 Technical and Organizational inputs | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
17 | A.2 Data loss/leakage prevention Strategy | 2013-06-21 08:00 | 2013-06-24 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
18 | A.3 Proposed optimization of the need of information sharing and portability | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
19 | A.4 Overarching technical policies | 2013-06-25 08:00 | 2013-06-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
20 | DLP Strategy Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-06-25 08:00 | 6d | 3922.5601 | 0 | 0 | 0 | 0 | 3922.5601 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 120 | 100 | 100 | 120 | 100
21 | DLP Strategy Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-15 10:00 | 8d 5h | 5638.6801 | 0 | 0 | 0 | 0 | 5638.6801 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 172.5 | 100 | 100 | 172.5 | 100
22 | DLP Strategy approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-07-29 10:00 | 4d 6h | 1552.68 | 0 | 0 | 0 | 0 | 1552.68 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 47.5 | 100 | 100 | 47.5 | 100
122 | B. High level implementation plan | 2013-05-09 08:00 | 2013-07-24 17:00 | 55d |  |  | 0 |  |  | 67010.401 |  | 53d 3h | [5 empty] | 75877.0211 |  | 100% |  | 67010.401 | 67010.401
23 | Define HL Implementation plan output | 2013-05-09 08:00 | 2013-05-09 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-09 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
24 | Initial HL Implementation plan workshop | 2013-05-13 08:00 | 2013-05-15 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-05-13 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
131 | HL Implementation plan Document writing | 2013-05-23 08:00 | 2013-06-03 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 8d | [5 empty] | 39225.6006 |  | 100% |  | 26150.4004 | 26150.4004
25 | B.1 Roadmap towards a full DLP implementation | 2013-05-23 08:00 | 2013-05-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-23 08:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 200 | 100 | 100 | 200 | 100
26 | B.2 Communication plan to stakeholders | 2013-05-27 08:00 | 2013-05-28 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
27 | B.3 integration in exisiting architecture | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-29 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
28 | B.4 Security controls for the enforcement of the policy | 2013-05-31 08:00 | 2013-06-03 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-31 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
29 | Follow-up HL Implementation plan workshop | 2013-06-12 08:00 | 2013-06-14 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-06-11 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
132 | HL Implementation plan Document writing | 2013-06-17 08:00 | 2013-06-20 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 3d | [5 empty] | 11440.8002 |  | 100% |  | 13075.2002 | 13075.2002
30 | B.1 Roadmap towards a full DLP implementation | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-14 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
31 | B.2 Communication plan to stakeholders | 2013-06-17 08:00 | 2013-06-18 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-14 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
32 | B.3 integration in existing architecture | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
33 | B.4 Security controls for the enforcement of the policy | 2013-06-19 08:00 | 2013-06-20 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 1d | 1634.4 | 0 | 0 | 0 | 0 | 1634.4 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 50 | 100 | 100 | 50 | 100
34 | HL Implementation plan Document review | 2013-06-27 08:00 | 2013-07-03 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-01 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
35 | HL Implementation plan Fix document | 2013-07-04 08:00 | 2013-07-10 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-07-15 10:00 | 6d | 3922.5601 | 0 | 0 | 0 | 0 | 3922.5601 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 120 | 100 | 100 | 120 | 100
36 | HL Implementation plan approval | 2013-07-11 08:00 | 2013-07-24 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-07-23 10:00 | 1h | 40.86 | 0 | 0 | 0 | 0 | 40.86 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 1.25 | 100 | 100 | 1.25 | 100
123 | D. Technical directives | 2013-06-27 08:00 | 2013-09-10 17:00 | 54d |  |  | 0 |  |  | 67010.401 |  | 87d 5h | [5 empty] | 131814.362 |  | 100% |  | 67010.401 | 67010.401
37 | Define Technical directives output | 2013-06-27 08:00 | 2013-06-27 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-07-01 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
38 | Initial Technical directives workshop | 2013-06-28 08:00 | 2013-07-02 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-13 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
133 | Technical directives Document writing | 2013-07-03 08:00 | 2013-07-18 17:00 | 12d |  |  | 0 |  |  | 22881.6003 |  | 6d | [5 empty] | 65376.001 |  | 100% |  | 22881.6003 | 22881.6003
39 | D.1 Device/Port control rules | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-16 08:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 400 | 100 | 100 | 400 | 100
40 | D.2 DLP rules | 2013-07-09 08:00 | 2013-07-10 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 250 | 100 | 100 | 250 | 100
41 | D.3 Encryption rules | 2013-07-17 08:00 | 2013-07-18 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 5d | 16344.0002 | 0 | 0 | 0 | 0 | 16344.0002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 250 | 100 | 100 | 250 | 100
42 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-03 08:00 | 2013-07-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-16 08:00 | 6d | 19612.8003 | 0 | 0 | 0 | 0 | 19612.8003 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 300 | 100 | 100 | 300 | 100
43 | Rule set v1 | 2013-07-03 08:00 | 2013-07-03 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-06-17 08:00 | 1h | 408.6 | 0 | 0 | 0 | 0 | 408.6 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 12.5 | 100 | 100 | 12.5 | 100
44 | Follow-up Technical directives workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-07-22 08:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
134 | Technical directives Document writing | 2013-07-24 08:00 | 2013-07-26 17:00 | 3d |  |  | 0 |  |  | 13075.2002 |  | 8d | [5 empty] | 32688.0005 |  | 100% |  | 13075.2002 | 13075.2002
45 | D.1 Device /Port control rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 250 | 100 | 100 | 250 | 100
46 | D.2 DLP rules | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 250 | 100 | 100 | 250 | 100
47 | D.3 Encryption rules | 2013-07-25 08:00 | 2013-07-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-26 16:00 | 8d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 400 | 100 | 100 | 400 | 100
48 | D.4 Use-cases Device Control & DLP Encryption | 2013-07-24 08:00 | 2013-07-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-08-01 16:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
49 | Technical directives Document review | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-08 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
50 | Technical directives Fix document | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-15 14:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
51 | Technical directives approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-08-22 14:00 | 17d | 5556.9601 | 0 | 0 | 0 | 0 | 5556.9601 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 170 | 100 | 100 | 170 | 100
124 | C. High Level Solution Design for Data Tagging and Information Classification | 2013-05-03 08:00 | 2013-09-10 17:00 | 93d |  |  | 0 |  |  | 67010.401 |  | 69d | [5 empty] | 94795.2014 |  | 100% |  | 67010.401 | 67010.401
52 | Define Data tagging HL Solution output | 2013-07-04 08:00 | 2013-07-04 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-06-19 09:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 200 | 100 | 100 | 200 | 100
53 | Initial Data tagging HL Solution workshop | 2013-07-19 08:00 | 2013-07-23 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-17 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
135 | DLP Data tagging HL Solution Document writing | 2013-07-26 08:00 | 2013-08-06 17:00 | 8d |  |  | 0 |  |  | 26150.4004 |  | 5d | [5 empty] | 13075.2002 |  | 100% |  | 26150.4004 | 26150.4004
54 | C.1 High-level solution design | 2013-07-26 08:00 | 2013-07-29 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-22 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
55 | C.2 Organization & Roles | 2013-07-30 08:00 | 2013-07-31 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
56 | C.3 Discovery of Classified Information | 2013-08-01 08:00 | 2013-08-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-27 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
57 | C.4 Control for tagging and classification | 2013-08-05 08:00 | 2013-08-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-28 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 50 | 100 | 100 | 50 | 100
58 | Follow-up Data tagging HL Solution workshop | 2013-08-07 08:00 | 2013-08-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-07-11 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
136 | DLP Data tagging HL Solution Document writing | 2013-05-03 08:00 | 2013-08-13 17:00 | 73d |  |  | 0 |  |  | 13075.2002 |  | 9d | [5 empty] | 58838.4009 |  | 100% |  | 13075.2002 | 13075.2002
59 | C.1 High-level solution design | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
60 | C.2 Organization & Roles | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
61 | C.3 Discovery of Classified Information | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
62 | C.4 Control for tagging and classification | 2013-08-12 08:00 | 2013-08-13 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-15 08:00 | 9d | 14709.6002 | 0 | 0 | 0 | 0 | 14709.6002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 450 | 100 | 100 | 450 | 100
63 | DLP Data tagging HL Solution Document review | 2013-08-14 08:00 | 2013-08-20 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-09 08:00 | 2d | 1307.52 | 0 | 0 | 0 | 0 | 1307.52 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 40 | 100 | 100 | 40 | 100
64 | DLP Data tagging HL Solution Fix document | 2013-08-21 08:00 | 2013-08-27 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-08-16 08:00 | 2d | 1307.52 | 0 | 0 | 0 | 0 | 1307.52 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 40 | 100 | 100 | 40 | 100
65 | DLP Data tagging HL Solution approval | 2013-08-28 08:00 | 2013-09-10 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-08-23 08:00 | 2d | 653.76 | 0 | 0 | 0 | 0 | 653.76 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 20 | 100 | 100 | 20 | 100
125 | H. Migration Strategy and a high level Implementation Package | 2013-05-03 08:00 | 2013-11-12 17:00 | 138d |  |  | 0 |  |  | 97737.1215 |  | 141d 4h | [5 empty] | 722077.9308 |  | 100% |  | 97737.1215 | 97737.1215
66 | Define Migration Strategy output | 2013-08-20 08:00 | 2013-08-20 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-08-20 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
67 | Initial Migration Strategy workshop | 2013-09-02 08:00 | 2013-09-04 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-09-02 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
137 | Migration Strategy Document writing | 2013-05-03 08:00 | 2013-09-23 17:00 | 102d |  |  | 0 |  |  | 39225.6006 |  | 52d | [5 empty] | 679910.4102 |  | 100% |  | 39225.6006 | 39225.6006
68 | H.1 Preparation guide | 2013-09-10 08:00 | 2013-09-11 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 46d | 150364.8022 | 0 | 0 | 0 | 0 | 150364.8022 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 2300 | 100 | 100 | 2300 | 100
69 | H.2 Installation guide | 2013-09-12 08:00 | 2013-09-13 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 52d | 169977.6025 | 0 | 0 | 0 | 0 | 169977.6025 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 2600 | 100 | 100 | 2600 | 100
70 | H.5 Uninstallation guide | 2013-09-16 08:00 | 2013-09-17 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 52d | 169977.6025 | 0 | 0 | 0 | 0 | 169977.6025 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 2600 | 100 | 100 | 2600 | 100
71 | H.6 Training Needs Analysis | 2013-09-18 08:00 | 2013-09-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 12d | 39225.6006 | 0 | 0 | 0 | 0 | 39225.6006 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 600 | 100 | 100 | 600 | 100
72 | H.7 Dashboards | 2013-05-03 08:00 | 2013-05-06 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 22d | 71913.6011 | 0 | 0 | 0 | 0 | 71913.6011 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 1100 | 100 | 100 | 1100 | 100
73 | H.8 Measurement Methods | 2013-09-20 08:00 | 2013-09-23 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-05-15 08:00 | 24d | 78451.2012 | 0 | 0 | 0 | 0 | 78451.2012 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 1200 | 100 | 100 | 1200 | 100
74 | Follow-up Migration Strategy workshop | 2013-09-30 08:00 | 2013-10-02 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-06-25 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
138 | Migration Strategy Document writing | 2013-05-07 08:00 | 2013-10-08 17:00 | 111d |  |  | 0 |  |  | 17651.5203 |  | 42d | [5 empty] | 17651.5203 |  | 100% |  | 17651.5203 | 17651.5203
75 | H.1 Preparation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-28 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
76 | H.2 Installation guide | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-06-28 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
77 | H.3 Configuration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-02 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
78 | H.4 Migration guide | 2013-10-07 08:00 | 2013-10-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-07-02 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
79 | H.5 Uninstallation guide | 2013-05-07 08:00 | 2013-05-08 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
80 | H.6 Training Needs Analysis | 2013-10-03 08:00 | 2013-10-04 17:00 | 2d |  | 0 | 0 | 81.72 | 1307.52 | 1307.52 | 2013-06-28 08:00 | 2d | 1307.52 | 0 | 0 | 0 | 0 | 1307.52 | 0 | 100% | Finished | 1307.52 | 1307.52 | 100 | 100 | 100 | 100 | 100 | 100
81 | Migration Strategy Document review | 2013-10-09 08:00 | 2013-10-15 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-10-23 08:00 | 10d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 200 | 100 | 100 | 200 | 100
82 | Migration Strategy Fix document | 2013-10-16 08:00 | 2013-10-22 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-11-07 08:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
83 | Migration Strategy approval | 2013-10-30 08:00 | 2013-11-12 17:00 | 10d |  | 0 | 0 | 204.3 | 16344.0002 | 16344.0002 | 2013-11-18 13:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 16344.0002 | 16344.0002 | 100 | 20 | 100 | 100 | 20 | 100
126 | E. DLP Control and Enforcement | 2013-08-14 08:00 | 2013-10-25 17:00 | 53d |  |  | 0 |  |  | 81393.1213 |  | 74d 6h | [5 empty] | 161805.6025 |  | 100% |  | 81393.1213 | 81393.1213
84 | Define DLP Control and Enforcement output | 2013-08-14 08:00 | 2013-08-14 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-08-14 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 200 | 100 | 100 | 200 | 100
85 | Initial DLP Control and Enforcement workshop | 2013-08-15 08:00 | 2013-08-19 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-08-28 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 100 | 100 | 100 | 100 | 100
86 | DLP Control and Enforcement Document writing | 2013-08-21 08:00 | 2013-08-30 17:00 | 8d |  | 0 | 0 | 408.6 | 26150.4004 | 26150.4004 | 2013-09-02 08:00 | 8d | 26150.4004 | 0 | 0 | 0 | 0 | 26150.4004 | 0 | 100% | Finished | 26150.4004 | 26150.4004 | 100 | 100 | 100 | 100 | 100 | 100
87 | E.1 Comparion systems | 2013-08-21 08:00 | 2013-08-22 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-09-02 08:00 | 8d | 26150.4004 | 0 | 0 | 0 | 0 | 26150.4004 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 400 | 100 | 100 | 400 | 100
88 | Follow-up DLP Control and Enforcement workshop | 2013-09-05 08:00 | 2013-09-09 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-09-18 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
89 | DLP Control and Enforcement Document writing | 2013-09-24 08:00 | 2013-09-27 17:00 | 4d |  | 0 | 0 | 408.6 | 13075.2002 | 13075.2002 | 2013-10-07 10:00 | 19d | 62107.2009 | 0 | 0 | 0 | 0 | 62107.2009 | 0 | 100% | Finished | 13075.2002 | 13075.2002 | 100 | 475 | 100 | 100 | 475 | 100
90 | E.1 Comparion systems | 2013-09-24 08:00 | 2013-09-25 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-07 10:00 | 8d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 400 | 100 | 100 | 400 | 100
91 | DLP Control and Enforcement Document review | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-11-01 10:00 | 3d | 1961.28 | 0 | 0 | 0 | 0 | 1961.28 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 60 | 100 | 100 | 60 | 100
92 | DLP Control and Enforcement Fix document | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-11-05 15:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
93 | DLP Control and Enforcement approval | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 98.064 | 7845.1202 | 7845.1202 | 2013-11-12 15:00 | 10d | 7845.1202 | 0 | 0 | 0 | 0 | 7845.1202 | 0 | 100% | Finished | 7845.1202 | 7845.1202 | 100 | 100 | 100 | 100 | 100 | 100
127 | F. Centralized Management and Monitoring Architecture for DLP | 2013-04-12 08:00 | 2013-11-22 17:00 | 161d |  |  | 0 |  |  | 81720.0012 |  | 138d | [5 empty] | 114408.0017 |  | 100% |  | 81720.0012 | 81720.0012
94 | Define Mgt & Monitoring Architecture output | 2013-04-12 08:00 | 2013-04-12 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-05-07 08:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
95 | Initial Mgt & Monitoring Architecture workshop | 2013-04-15 08:00 | 2013-04-17 17:00 | 3d |  | 0 | 0 | 408.6 | 9806.4001 | 9806.4001 | 2013-06-24 08:00 | 6d | 19612.8003 | 0 | 0 | 0 | 0 | 19612.8003 | 0 | 100% | Finished | 9806.4001 | 9806.4001 | 100 | 200 | 100 | 100 | 200 | 100
139 | Mgt & Monitoring Architecture Document writing | 2013-04-18 08:00 | 2013-10-14 17:00 | 128d |  |  | 0 |  |  | 32688.0005 |  | 56d 5h | [5 empty] | 55569.6008 |  | 100% |  | 32688.0005 | 32688.0005
96 | F.1 Definition of organisation & roles | 2013-04-23 08:00 | 2013-04-24 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
97 | F.2 log specs & formats | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-07-04 14:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 200 | 100 | 100 | 200 | 100
98 | F.3 Central management design | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-23 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
99 | F.4 Log collection design | 2013-10-11 08:00 | 2013-10-14 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-04-25 08:00 | 3d | 9806.4001 | 0 | 0 | 0 | 0 | 9806.4001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 150 | 100 | 100 | 150 | 100
100 | F.5 Integration | 2013-04-18 08:00 | 2013-04-19 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-07-04 14:00 | 4d | 13075.2002 | 0 | 0 | 0 | 0 | 13075.2002 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 200 | 100 | 100 | 200 | 100
101 | Follow-up Mgt & Monitoring Architecture workshop | 2013-04-22 08:00 | 2013-04-24 17:00 | 3d |  | 0 | 0 | 204.3 | 4903.2001 | 4903.2001 | 2013-10-01 08:00 | 3d | 4903.2001 | 0 | 0 | 0 | 0 | 4903.2001 | 0 | 100% | Finished | 4903.2001 | 4903.2001 | 100 | 100 | 100 | 100 | 100 | 100
140 | Mgt & Monitoring Architecture Document writing | 2013-04-25 08:00 | 2013-11-01 17:00 | 137d |  |  | 0 |  |  | 16344.0002 |  | 118d | [5 empty] | 16344.0002 |  | 100% |  | 16344.0002 | 16344.0002
102 | F.1 Definition of organisation & roles | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
103 | F.2 log specs & formats | 2013-04-25 08:00 | 2013-04-26 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-04 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
104 | F.3 Central management design | 2013-04-29 08:00 | 2013-04-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-25 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
105 | F.4 Log collection design | 2013-10-29 08:00 | 2013-10-30 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-04-29 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
106 | F.5 Integration | 2013-10-31 08:00 | 2013-11-01 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-04 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
107 | Mgt & Monitoring Architecture Document review | 2013-10-22 08:00 | 2013-10-28 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-10-04 08:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
108 | Mgt & Monitoring Architecture Fix document | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 204.3 | 8172.0001 | 8172.0001 | 2013-10-11 08:00 | 5d | 8172.0001 | 0 | 0 | 0 | 0 | 8172.0001 | 0 | 100% | Finished | 8172.0001 | 8172.0001 | 100 | 100 | 100 | 100 | 100 | 100
109 | Mgt & Monitoring Architecture approval | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-10-18 08:00 | 10d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
128 | G. High Level Solution for Network based DLP | 2013-11-25 08:00 | 2014-01-07 17:00 | 32d |  |  | 0 |  |  | 36447.1205 |  | 45d 4h | [5 empty] | 36447.1205 |  | 100% |  | 36447.1205 | 35793.3605
110 | Define HL Solution for NW based DLP output | 2013-11-25 08:00 | 2013-11-25 17:00 | 1d |  | 0 | 0 | 408.6 | 3268.8 | 3268.8 | 2013-09-12 13:00 | 1d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
111 | Initial HL Solution for NW based DLP workshop | 2013-11-26 08:00 | 2013-11-28 17:00 | 3d |  | 0 | 0 | 20.43 | 490.32 | 490.32 | 2013-09-13 13:00 | 3d | 490.32 | 0 | 0 | 0 | 0 | 490.32 | 0 | 100% | Finished | 490.32 | 490.32 | 100 | 100 | 100 | 100 | 100 | 100
141 | HL Solution for NW based DLP Document writing | 2013-11-29 08:00 | 2013-12-04 17:00 | 4d |  |  | 0 |  |  | 13075.2002 |  | 4d | [5 empty] | 13075.2002 |  | 100% |  | 13075.2002 | 13075.2002
112 | G.1 Solution Design | 2013-11-29 08:00 | 2013-12-02 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-09-25 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
113 | G.2 Gap analysis | 2013-12-03 08:00 | 2013-12-04 17:00 | 2d |  | 0 | 0 | 408.6 | 6537.6001 | 6537.6001 | 2013-09-27 08:00 | 2d | 6537.6001 | 0 | 0 | 0 | 0 | 6537.6001 | 0 | 100% | Finished | 6537.6001 | 6537.6001 | 100 | 100 | 100 | 100 | 100 | 100
114 | Follow-up HL Solution for NW based DLP workshop | 2013-12-05 08:00 | 2013-12-06 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-01 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
142 | HL Solution for NW based DLP Document writing | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  |  | 0 |  |  | 6537.6001 |  | 4d | [5 empty] | 6537.6001 |  | 100% |  | 6537.6001 | 6537.6001
115 | G.1 Solution Design | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-03 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
116 | G.2 Gap analysis | 2013-12-09 08:00 | 2013-12-10 17:00 | 2d |  | 0 | 0 | 204.3 | 3268.8 | 3268.8 | 2013-10-07 08:00 | 2d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
117 | HL Solution for NW based DLP Document review | 2013-12-11 08:00 | 2013-12-17 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-10-09 08:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
118 | HL Solution for NW based DLP Fix document | 2013-12-18 08:00 | 2013-12-24 17:00 | 5d |  | 0 | 0 | 81.72 | 3268.8 | 3268.8 | 2013-10-16 08:00 | 5d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 3268.8 | 100 | 100 | 100 | 100 | 100 | 100
119 | HL Solution for NW based DLP approval | 2013-12-25 08:00 | 2014-01-07 17:00 | 10d |  | 0 | 0 | 40.86 | 3268.8 | 3268.8 | 2013-11-01 08:00 | 10d | 3268.8 | 0 | 0 | 0 | 0 | 3268.8 | 0 | 100% | Finished | 3268.8 | 2615.04 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
T1 | 2013-04-10 08:00 | 2013-05-06 08:00 | 78451.2012 | 40315.2007 | 42494.4006 | 2013-04-19 15:00 | -38136.0004 | 51.39% | -2179.1999 | 94.87% | -10d 2h | 43.06% | 38.78% | 2014-01-24 15:00 | 2014-09-23 12:00 | 2014-10-21 17:00 | 2014-01-20 15:00 | 2014-09-23 12:00 | 2014-10-20 17:00 | 2014-01-22 10:00 | 2015-01-02 16:00 | 2015-02-05 11:00 | 587130.9688 | 616570.7814 | 1102327.719 | 1307456.7524 | 1159616.0029 | 1375833.0915 | 674505.0951 | 686969.5287 | 0.43056 | 0.94872 | 0.51389 | 0.38776 | -10.25 | 0.94872 | 1 | 0.43056 | 1
T2 | 2013-05-06 08:00 | 2013-06-03 08:00 | 148730.4022 | 155283.7839 | 326880.0049 | 2013-06-11 09:00 | 6553.3817 | 104.4% | -171596.221 | 47.5% | 6d 1h | 116.1% | 60.36% | 2014-01-03 16:00 | 2013-12-26 15:00 | 2014-10-13 09:00 | 2014-01-06 11:00 | 2013-12-26 15:00 | 2014-08-14 09:00 | 2013-12-30 16:00 | 2013-11-29 16:00 | 2014-06-19 12:00 | 756547.9898 | 1231352.2523 | 738414.8774 | 696905.6916 | 1193181.1586 | 1105802.2803 | 1056551.7648 | 1028636.0102 | 1.1612 | 0.47505 | 1.0441 | 0.6036 | 6.125 | 0.47505 | 1 | 1.1612 | 1
T3 | 2013-06-03 08:00 | 2013-07-01 08:00 | 210183.8431 | 273070.3117 | 728370.3709 | 2013-07-23 11:00 | 62886.4685 | 129.9% | -455300.0592 | 37.49% | 16d 3h | 128.2% | 77.11% | 2013-12-09 17:00 | 2013-11-06 09:00 | 2014-10-22 11:00 | 2013-12-13 14:00 | 2013-11-06 09:00 | 2014-06-09 14:00 | 2013-12-16 14:00 | 2013-11-08 09:00 | 2014-06-16 16:00 | 1040251.8281 | 1560263.1215 | 968427.3836 | 971585.4905 | 1368683.1692 | 1377106.9024 | 1285536.1837 | 1288914.8585 | 1.2823 | 0.37491 | 1.2992 | 0.77114 | 16.375 | 0.37491 | 1 | 1.2823 | 1
T4 | 2013-07-01 08:00 | 2013-08-05 08:00 | 313804.8047 | 357801.9458 | 1116295.2167 | 2013-08-20 17:00 | 43997.1411 | 114% | -758493.2709 | 32.05% | 12d | 114.5% | 85.78% | 2013-12-18 11:00 | 2013-12-04 17:00 | 2015-04-27 14:00 | 2013-12-23 11:00 | 2013-12-04 17:00 | 2014-08-22 14:00 | 2013-12-20 17:00 | 2013-12-04 11:00 | 2014-08-20 14:00 | 1343445.0398 | 1824972.9195 | 1315513.546 | 1314752.4305 | 1737830.3166 | 1735455.736 | 1585165.3715 | 1584320.4697 | 1.1446 | 0.32053 | 1.1402 | 0.85778 | 12 | 0.32053 | 1 | 1.1446 | 1
T5 | 2013-08-05 08:00 | 2013-09-02 08:00 | 395851.6859 | 407330.9426 | 1183428.1977 | 2013-09-04 17:00 | 11479.2567 | 102.9% | -776097.2551 | 34.42% | 3d | 102.9% | 86.54% | 2014-01-02 09:00 | 2013-12-31 12:00 | 2015-05-20 14:00 | 2014-01-02 17:00 | 2013-12-31 12:00 | 2014-08-19 11:00 | 2014-01-02 17:00 | 2013-12-31 12:00 | 2014-08-19 10:00 | 1361049.024 | 1699474.1749 | 1356043.3766 | 1356022.0194 | 1684931.1496 | 1684869.1001 | 1552582.2572 | 1552562.72 | 1.0291 | 0.3442 | 1.029 | 0.86537 | 3 | 0.3442 | 1 | 1.0291 | 1
T6 | 2013-09-02 08:00 | 2013-10-07 08:00 | 480186.7272 | 496040.4074 | 1288520.1192 | 2013-10-14 10:00 | 15853.6802 | 103.3% | -792479.7118 | 38.5% | 5d 2h | 104.1% | 93.61% | 2013-12-31 15:00 | 2013-12-30 15:00 | 2015-02-25 11:00 | 2014-01-01 15:00 | 2013-12-30 15:00 | 2014-05-14 16:00 | 2013-12-31 15:00 | 2013-12-27 11:00 | 2014-05-09 09:00 | 1377431.4807 | 1519477.2678 | 1374589.8326 | 1373928.4064 | 1512095.7708 | 1510377.6428 | 1461304.9893 | 1460769.4095 | 1.041 | 0.38497 | 1.033 | 0.93606 | 5.25 | 0.38497 | 1 | 1.041 | 1
T7 | 2013-10-07 08:00 | 2013-11-04 08:00 | 525623.048 | 549212.8882 | 1401947.4809 | 2013-11-25 10:00 | 23589.8403 | 104.5% | -852734.5927 | 39.17% | 15d 2h | 110.3% | 94.03% | 2013-12-27 09:00 | 2013-12-26 14:00 | 2015-02-05 11:00 | 2013-12-30 11:00 | 2013-12-26 14:00 | 2014-03-20 14:00 | 2013-12-17 15:00 | 2013-12-12 15:00 | 2014-02-13 12:00 | 1437686.3616 | 1493176.2826 | 1436151.302 | 1434347.8138 | 1489257.8151 | 1484654.1434 | 1470363.4979 | 1468873.2102 | 1.103 | 0.39175 | 1.0449 | 0.9403 | 15.25 | 0.39175 | 1 | 1.103 | 1
T8 | 2013-11-04 08:00 | 2013-12-02 08:00 | 555532.5684 | 584951.7689 | 1425155.9614 | 2014-01-07 17:00 | 29419.2004 | 105.3% | -840204.1926 | 41.04% | 27d | 116.1% | 100% | 2013-12-25 10:00 | 2013-12-25 10:00 | 2015-01-01 10:00 | 2013-12-26 09:00 | 2013-12-25 10:00 | 2014-01-28 16:00 | 2013-11-29 17:00 | 2013-11-29 17:00 | 2013-11-29 17:00 | 1425155.9614 | 1425155.9614 | 1425155.9614 | 1425155.9614 | 1425155.9614 | 1425155.9614 | 1425155.9614 | 1425155.9614 | 1.1607 | 0.41045 | 1.053 | 1 | 27 | 0.41045 | 1 | 1.1607 | 1
T9 | 2013-12-02 08:00 | 2014-01-06 08:00 | 584298.0089 | 584951.7689 | 1425155.9614 | 2014-01-07 17:00 | 653.76 | 100.1% | -840204.1926 | 41.04% | 2d | 101% | 100% | 2014-01-07 15:00 | 2014-01-07 15:00 | 2015-02-03 12:00 | 2014-01-07 15:00 | 2014-01-07 15:00 | 2014-01-10 11:00 | 2014-01-03 17:00 | 2014-01-03 17:00 | 2014-01-03 17:00 | 1425155.9614 | 1425155.9614 | 1425155.9614 | 1425155.9614 | 1425155.9614 | 1425155.9614 | 1425155.9614 | 1425155.9614 | 1.0104 | 0.41045 | 1.0011 | 1 | 2 | 0.41045 | 1 | 1.0104 | 1